## Sheet1
REPUBLIC OF RWANDA
NORTHERN PROVINCE
BURERA DISTRICT
2019-2020 SINGLE ACTION PLAN
Targets/milestones
S/N | Outcome | Programme | Sub programme | Output | Indicators | Baseline | Source of Data | Q1 | Q2 | Q3 | Q4 | ANNUAL TARGET | ACTIVITIES TO DELIVER | STAKEHOLDERS | BUDGET
Institutional development and performance strengthened
ADMINISTRATIVE AND SUPPORT SERVICES
MANAGEMENT SUPPORT
1 |  |  | Procurement | Annual procurement plan prepared, published and implemented | Number of procurement plan prepared, published and implemented | 2 |  | 1 |  | 1 |  | 2 | To Prepare, publish and implement the annual approved procurement plan | RPPA , District | 621, 000
2 |  |  |  | Project contracts managed | Number of projects managed through tender | [7 empty] | To Manage contracts, produce regular reports there of and keep procurement proceeding records in accordance with the regulations; | DISTRICT | 1000000
3 |  |  | Institutional internal audit | PFM systems enhanced | Percentage of Auditor general's recommendations implemented. | 39 | Administrative data | 55% | 60% | 75% | 85% | 100% | To implement auditor general recommandation | District
4 |  |  |  |  | Number of peer review and learning organised in all NBAs | 134 | Administrative data |  | 98 |  | 39 | 137 | To organise peer review and learning in all NBAs | District | 5000000
5 |  |  |  |  | Number of NBAs audited in line with PFM | 30 | Annual basis report | 6 | 8 | 8 | 8 | 30 | organize and conduct audit in NBAs | DISTRICT | 1000000
6 |  |  | Management administrative assistance | Institutional documents received, distributed and archived securely | Number of documents received and distributed |  | Administrative data
7 |  |  | Legal and advisory services | Notary services to service seekers rended | Number of notary services seekers rended | Dstrict report | [6 empty] | To render notary services to service seekers | District
8 |  |  |  | Contentious dossiers and/or requests emanating from citizens or District’s staff analysed | Number of contentious dossiers request emananting from citizens or District staff analysed | Dstrict report | [6 empty] | To analyze contentious dossiers and/or requests emanating from citizens or District’s staff | District
9 |  |  | Institutional budgeting and financing | Various units of the District in the annual budget preparation are assisted | Number of sessions of annual budget preparation | 2 | District reports | 1 |  | 1 |  | 2 | To assist various unitsof the District in the annual budget preparation | District | 1000000
10 |  |  |  | Budget requests from units compiled into the appropriate software (SMART IFMS, etc.); | Number of Departement supported for working into the appropriate software | 12 | District reports | 12 |  |  |  | 12 | To compile budget requests from units into the appropriate software (SMART IFMS, etc.); | District | 1000000
11 |  |  |  | Monthly and quarterly budget execution reports prepared | Percentage of budget execution consummed | 75% | District reports | 100% | 100% | 100% | 100% | 100% | To consolidate quarterly report on budget consumption | District | 10000000
12 |  |  | Human resources management | All Personnel are Paid Monthly and regularly | Number of payroll listes established | 12 | Administrative data | 3 | 3 | 3 | 3 | 12 | To process and pay salaries for District,Sectors and cells staff | GoR, DISTRICT | 2458764881.1691
13 |  |  |  | Retreat of District staff organized | Number of Session of District staff retreat organised | 1 | Administrative data | 1 |  |  |  | 1 | To prepare and organise retreat staff | District | 5000000
14 |  |  |  | District capacity building plan is implemented | Number of session staff trainings organized | 4 | Administrative data | 1 | 1 | 1 | 1 | 4 | To conduct various trainings for District staff, Sector staff, cell staff and NBAs | DISTRICT | 12500000
15 |  |  |  | Inspection in District departements conducted | Number of inspection conducted | 4 | Administrative data | 1 | 1 | 1 | 1 | 4 | To organize and conduct inspection within district departements | District
17 |  |  | Institution Secretariat | Institutional documents received, distributed and archived securely | Number of documents received and distributed |  | Administrative data | [5 empty] | To receive, register, distribute and archive incoming and out going documents
22 |  |  |  | High ICT quality skills leveraging knowledge developed | Number of institutions (administrative offices, schools, Health facilities, SACCOs) connected to Internet | 52 | Administrative data | Cells identification of signal availability | 10 | 7 |  | 17 Cell offices | Identification of signal 2. connect 17 cell office with 4G | DISTRICT, RISA
23 |  |  | Charroi services | District log book updated | Number of log book updated | 2 | Administrative data | 2 |  |  |  | 2 | To transport District staff and upadate log book | DISTRICT
24 |  |  |  | District vehicule maintainance ensured | Number district vehicule maintained | 2 | Administrative data | 2 |  |  |  | 2 | To process all requirements needd for vehicule maintaince, supervision and reporting | DISTRICT
25 |  |  | Institutional public relations and communications | The branding/publicity and communication plan developed and its implementation plan produced | Number of communication plan produced and implemented | 1 | Administrative data | 1 |  |  |  | 1 | To develop the branding/publicity and communication plan and its implementation plan | District | 500000
26 |  |  |  | The authorities regularly informed on the image of the District within and outside of the District , and accordingly, advise the institution on the management of its image/reputation; | Number of District events published througth website | [7 empty] | To inform the authorities regularly on the image of the District within and outside of the country | District | 500000
27 |  |  | Institutional Planning, Monitoring and evaluation | Guidelines for Integrated Development Planning of the District and monitor compliance by various units elaborated | Number of Districts depatrment supported to develop Integrated planning and its implementation | 12
28 |  |  |  | Technical support in the elaboration of actionable strategies meant to localise national policies and implement the District Council’s decisions provided | Number of sessions held in elabortion of District plans | 2 |  | 1 |  | 1 |  | 2
29 |  |  |  | Strategic plan, action plan and Imihigo and accordingly advise on necessary reviews and or end of programs monitored | Number of Districts plans implemented and monitored | 3 | Administrative data | 3 |  |  |  | 3
30 |  |  |  | The planning, implementation, monitoring and evaluation reports emanating from various units and Sectors of the District supervised and consolidated | Number of performance contract monitored and reported regulary | 76 | Administrative data | 69 |  |  |  | 69
31 |  |  |  | A quality system of aggregated and disaggregated quantitative data consolidation at the District level initiated, operationalized and regular updated | Number of District booklet in statistic figures updated | 1 | Administrative data | 1 |  |  |  | 1 | To consolidate and update Burera Statistcics in Figures
32 |  |  | District and sector councils | Enhanced accountability and feedback to their constituencies | Number of Concillors visit organise to their constituencies | 12 | District Concil commissions | 3 | 3 | 3 | 3 | 12 | To prepare and organise viits of concillors to their constituencies | District | 3000000
34 |  |  |  |  | Number of sector Council reports and feedback produced | 102 | [5 empty] | 102 | To analyse and exploit all reports of 17 sector council, to make sure for feedack to the sector council
35 |  |  |  | The planning, implementation, monitoring and evaluation reports of District council office activities | Number of Units and department supervised in Implementation of District council resolutions | 12 | Administrative data | 12 |  |  |  | 12 | Coordinate the planning, budgeting implemetation, monitoring and evaluation, reporting on District councils office activities
36 |  |  |  | District Council resolution implemented | Percentage of District Council resolution implemented | 85% | Quaterly basis reports | 100% | 100% | 100% | 100% | 100% | 1.District council resolutions shaed 2.Follow up and report on District council resolution implementation | DISTRICT | 200000
37 |  |  | District local Revenue | Tax payers database updated | Number of tax payers database established | 1 | Administrative data | 1 |  |  |  | 1 | To update the Tax payers database
40 |  |  |  | Public accountability enhanced | District Own revenues increased | 903814230 | Administrative data | 227714502 | 167375149 | 255819253 | 313625743 | 964534647 | DISTRICT 1. To update taxpayer files, 2.Tto monitor the own revenus collection RRA: 3. To collect and report the District revenues collection | DISTRICT, RRA
Enhanced rule of law, accountability and business competitiveness environment
GOOD GOVERNANCE
Good Governance and Decentralisation
41 |  |  |  | Service delivery enhanced | Number of cells and Sectors where LGs Revised Standard Service Charters are displayed | N/A | District reports |  | 69 cells and 17 sectors |  |  | 69 cells and 17 sectors | To elaborate and approve service charter at Cell and sectors levels, Display services charter elaborate at Cell and sector levels
42 |  |  |  | Governance month conducted | Reports on governance month | 1 | 1 |  |  |  | 1 |  | Monitoring & evaluation | DISTRICT | 200000
43 |  |  |  | Governance inspection conducted | Report on Governance Inspection | 1 |  |  | 1 |  | 1 |  | To implement and Quaterly report on the available Approved Audit plan | DISTRICT | 2500000
44 |  |  |  | PFM systems enhanced | Percentage of Auditor general's recommendations implemented. | 39% | Administrative data | 55% | 60% | 75% | 85% | 100% | To implement auditor general recommandation | District
45 |  |  |  | Burera District Office constructed | Ha of land expropriated | N/A | Technical reports | Site identified | Files of PAPs prepared and signed | 1 ha |  | 1 ha of land expropriatated | 1. Site identification, people mobilisation, 2. Files of PAPs preparation and signature | DISTRICT | 100000000
46 |  |  |  | CRVS events registered | Percentage of CRVS event (Birth, Death, Marriage and Divorce) timely recorded in the CRVS web application. | 97% | Percentage over which CRVS events (Birth, Death, Marriage and Divorce ) are timely recorded in the CRVS web application. | Birth : 97%; Death: 97%; Marriage: 97% | NSIR | Birth : 100%; Death: 100%; Marriage: 100% Divorce: 100% | Birth : 100%; Death: 100%; Marriage: 100% Divorce: 100% | Birth : 100%; Death: 100%; Marriage: 100% Divorce: 100% |  | NISR Provide technical support and records reports HEALTH CENTERS&HOSPITALS 1. Record in CVRS births and death SECTORS 1. Record in CVRS births, deaths and marriages DISTRICT 1. Monitor records in CVRS from both Sectors and Health facilities
47 |  |  |  | Open day organised and supervised | Number of open day organized | 1 | District reports |  |  |  | 1 | 1 | DISTRICT, JADF
|  |  |  | Umuganda activities planed and implemented | Number of Projects implemented through umuganda initiatives | N/A | District reports | 1 | 1 | 2 | 1 | 5 | DISTRICT, MINALOC, Population | mobilisation and planning of Umuganda
Unity and Reconciliation Preserved and Reinforced & Steadfast Rwandan Identity Fostered
GOOD GOVERNANCE
UNITY AND RECONCILIATION
49 |  |  |  | Unit and reconciliation activities coordinated | Number of sectors in which unit and reconciliation sensitisations in the annual reconciliation month organised and conducted | 17 | District reports |  | 17 |  |  | 17 | To organise and conduct Unit and reconciliation sensitisation at sector level, selection of Abarinzi b'Igihango, organise unity and reconciliation festivities in schools | NURC, DISTRICT | 1838942
50 |  |  |  |  | Number of Unit and reconciliation activities evaluated at sector level | 13 | NURC reports |  |  |  | 13 | 13 | Integrating Unit and reconcilition activities in District Annaul action plan, disseminiting unit and reconcilition activities to the community, monitoring of unit and reconcilition activities | NURC, DISTRICT | 3000000
[5 empty] | Monitor the compliance with unity and reconciliation policy in the 26 th commemoration of Genocide against the Tutsi | 1 |  |  |  | 1 |  | 1 | Reporting on bihavior and acts againts unity and recinciliation program, reporting on appreciated acts on Unity and reconciliation | NURC, DISTRICT
[5 empty] | Number of schools (primary and secondary) in which debates on peace, unity and reconciliation organised nd conducted | 141 | District and MINEDUC reports |  |  |  | 141 | 141 | organise debates on peace,unity and reconciliation in 95 primary schools and in 46 secondary schools | NURC, DISTRICT
[5 empty] | Number of Ndi Umunyarwanda sessions organised and conducted in District and sector council levels | 2 |  |  |  | 1 | 1 | 2 | organise Ndi Umunyarwanda sessions of District and Sector councils , reporting on Ndi Umunyarwanda sessions conducted | NURC, DISTRICT
[5 empty] | Number of Ndi Umunyarwanda interactions sessions organized and held at District, sector, and villages level disagregated by different target groups | 4 | District Administrative data | 1 | 1 | 1 | 1 | 4 | Organize and conduct iteraction sessions on Ndi Umunyarwanda for community at village level and among specific groups at sector and District levels (businessmen, clerges and civil society, District and sector concelors), 2. supervision and reporting | NURC, DISTRICT
[5 empty] | Social reintegration of released ex genocide prisoners monitored | N/A |  |  | 1 |  |  | 1 | Organising dialogues between authorities and released ex genocide prisoners | NURC, DISTRICT
[5 empty] | Outstanding achievements of Abarinzi b'igihango documented in the District | N/A |  |  |  |  | 1 | 1 | Recording Abarinzi b'igihango selected since 2016, collecting their photos, producing booklet getharing Abarinzi b'igihango information | NURC, DISTRICT
[5 empty] | Social hearing programs in the community promoted | 1 | District reports |  | 1 |  |  | 1 | Identifying reintegration and social hearing activities on specific groups, dialogues between authorities and detenues, reintegration of repatriated, reintegration of mhistorical marginalised people
51 |  |  |  |  | Unit and reconciliations Forum activities at sector and District level coordinated | 12 | District reports | 3 | 3 | 3 | 3 | 12 | Conducting the program of Unity and reconcilitation District dialogue platform | NURC, DISTRICT | 1955334
52 |  |  |  | Dialogues and visit to prisoneers organized and conducted | Number of visit organised and dialogues conducted to the detenues | 4 | District reports | 1 | 1 | 1 |  | 4 | Organising visit of authorities to prisoners and ex genocide prisoners | NURC, DISTRICT | 450000
53 |  |  |  | Abarinzi b'Igihango across the District supported | Number of Abarinzi b'Igihango selected, recognised and supported | 13 | District reports |  |  |  |  | 13 | Selecting and recognition of Abarinzi b'Igihango within the District, Empowering Abarinzi b'Igihango with the training, supporting 1 umurinzi w'igihango with kuremera initiative (one cow provided) | NURC, DISTRICT | 1838942
54 |  |  |  | National service organised | Number of participnts in residential National Service (Urugerero ruciye ingando) conducted and monitored at District level (1 Intore per Village | 283 | District reports |  |  |  | 571 | 571 | Organize and conduct in-depth sessions on Ndi Umunyarwanda among: -The community at Sector level; - In business community (enterprises and cooperatives with more that 30 members and staff and among small and medium business holders); - Among non schooling youth; - Among clergies within Districts ( Priests, Sisters, Deacons, Pastors, Imams, etc); - Non governemental organisations staff | NIC,NURC, DISTRICT | 500000
55 |  |  |  | Itorero operationalized in all villages | Number of Itorero ry'Umudugudu operational in all Village mentored and monitored and number of Villages in which Itorero is operational | 571 | District reports |  |  |  |  | 571Villages | organise Itorero ry"umuduudu in all Villages | NIC,NURC, DISTRICT
Improved access to quality Justice
GOOD GOVERNANCE
JUSTICE
57 |  |  |  | % of Judgments executed | Percentage of judgement executed | 85% | District reports | 87% | 87% | 87% | 87% | 87% | Receiving and execute judgements | DISTRIT,
58 |  |  |  | Citizens complains registered trhough tracking system | Percentage of citizens' complains received and resolved via-citizens complaints traking system | 78.9% | District reports | 100% | 100% | 100% | 100% | 100% | Receiveing and resolving citizens complains | DISTRICT
59 |  |  |  | Citizens complains resolved through community outreach | Percentage of citizen demands/complaints received and resolved through Community outreach | 85% | District reports | 85% | 85% | 85% | 85% | 85% | Receiveing and resolving citizens complains through community outreachs | DISTRICT, MINLAOC
60 |  |  |  | Equitable justice increased througth Abunzi Commettees | Percentage of cases received and handled by MAJ staff | 97.3% | District reports | 99.5% | 99.5% | 99.5% | 99.5% | 99.5% | Receiving and handling cases with MAJ staff | DISTRICT, MINJUST
61 |  |  |  | % of cases received and settled by mediation committees " Abunzi" | % of cases received and settled by mediation committees " Abunzi" | 96.1% | District reports | 98% | 98% | 98% | 98% | 98% | reeeiving and resolving cases by mediations committees | DISTRICT, MINLAOC
62 |  |  |  | Governement funds recoverded | % of Governement funds recoverded | MINIJUST Data Report | Recovering legal procedures establishment, to identify funds Government | 34% | 65% | 80% | 90% | 90% | DISTRICT To recover Government funds | DISTRICT, MINJUST
Guaranted safety and security for all persons and their property
GOOD GOVERNANCE
GENERAL POLICING OPERATIONS
64 |  |  |  |  | Number of training sessions organised for DASSO staff | 4 | Administrative data | 1 | 1 | 1 | 1 | 4 | organising training | DISTRICT
Gender mainstreaming enhanced
GOOD GOVERNANCE
FAMILY PROTECTION AND WOMEN EMPOWERNMENT
66 |  |  |  | Improved Family welfare and fight against GBV | Percentage of teenage pregnancies (15-19years) reduced) | N/A | District Administrative data | 6.3 | 6 | 5.5 | 5.3 | 5.3 | Community mobilisation | DISTRICT, MIGEPROF
[5 empty] | Number of GBV, child abuse and human trafficking victims (by sex, and by age received reintegration support | 648 | District reports |  | 15 | 15 | 20 | 50 | identifying beneficiries, support and monitoring | DISTRICT, MIGEPROF
67 |  |  |  | Umugoroba w’Ababyeyi promoted by inspection | Number of Inspection conducted on umugoroba w'ababyeyi | 4 | District Administrative data | 1 | 1 | 1 | 1 | 4 | 1. To conduct inspections on umugoroba w'ababyeyi activities, 2. Rewarding Best villages in Umugoroba w'ababyeyi organizations. | DISTRICT, MIGEPROF | 4667885
68 |  |  |  | Children’s forums from village to District level are operational | Number of session of Elected children form organised | 1 |  |  | 1 | 1 |  | 2 | organise and support children forum training, particiting to the national children summit, TRAINING Inshuti z'Umuryango | DISTRICT, NCC | 16594200
A Healthy, apt, patriotic, productive, and innovative youth
YOUTH, SPORT AND CULTURE
CULTURE
69 |  |  |  | Mourning week organised | Number of mourning week organised | 1 | Administrative data |  |  |  | 1 | 1 | Mouning preparation and organisation | DISTRICT
70 |  |  |  | Jobs created in creative arts and industries | Number of new jobs created in creative arts and industries | N/A | Administrative data |  | 1 | 1 |  | 2 | Identifying creative arts potential to create job, organising talent competitions | DISTRICT
71 |  |  |  | District cultural troups supported | Number of troups supported | 17 | Administrative data |  | 17 |  |  | 17 | Identify thecultural danse troups,organising cultural competitions, culture week preparation and organisation, rewarding best performant | DISTRICT | 1000000
SPORTS AND LEISURE
72 |  |  |  | Sports activities promoted | Number of Mass Sports events organized at Sector level | 12 | Administrative data | 3 | 3 | 3 | 3 | 12 | Community mobilisation
73 |  |  |  |  | Number of new sports facilities created at cell level | 29 | Administrative data |  | 17 |  |  | 17 | Community mobilisation | DISTRICT
74 |  |  |  |  | One Umurenge and schools Cup organized | 1 | District Administrative data |  |  | 1 |  | 1 | 1. Community mobilization 2. Team preparation, 3. Competition organisation and supervision | DISTRICT | 8000000
75 |  |  |  |  | Number of Rwandan participating in sports (mass sports and sports for all) | N/A | District Administrative data | 4500 | 4500 | 4500 | 4500 | 18000 | community mobilisation | DISTRICT
76 |  |  |  |  | Number of space community library and proper archive management availed | N/A | District Administrative data |  |  |  | 1 | 1 | Availing 1 space community library | DISTRICT
Increased productivity and agricultural sustainability
AGRICULTURE
SUSTAINABLE CROP PRODUCTION
77 |  |  |  | Agricultural productivity increased | Land consolidated with priority crops (ha) | Maize: 15,000ha Beans: 20,960ha, Ipotatoes: 14,000ha Wheat: 10,500ha | District Administrative data | N/A | Maize: 14,500ha Beans: 6,745ha, Ipotatoes: 7,000ha Wheat: 3,500ha | Maize:500ha Beans:13,810 Ha, Ipotatoes:7 000ha Wheat:7000ha | N/A | Maize: 15,000ha Beans: 20, 555ha, I.Potatoes: 14,000ha Wheat: 10,500ha | DISTRICT 1. To identify sites, 2. To mobilize farmers and prepare agricultural saisons, 3. To train 34,260 farmers trough Twigire Muhinzi 4. To distribute inputs and maintain sites | MINAGRI/RAB, DISTRICT | 578176200
78 |  |  |  | Use of improved seeds increased | Kg of improved seeds timely delivered and used by farmers | Maize: 145,833.5 Wheat: 216,338 | RAB | Delivery: 279,100Kg of improved seeds available at suppliers warehouses and ready for distribution to farmers for Season A (Maize: 173,730Kg Wheat: 105,370Kg by 30th August 2019 | Improved seed Use Season A (Q2) (Maize: 173,730Kg Wheat: 105,370Kg Tot: 279,100Kg | Delivery: 170,900Kg of improved seeds available at suppliers warehouses and ready for distribution to farmers for Season B (Maize: 26 270Kg Wheat : 144,630Kg by 29th February 2020 | Improved seed Use Season B (Q4) Maize: 26 270Kg Wheat : 144,630Kg Tot : 170,900Kg | Maize: 200,000kg; 'Wheat: 250,000kg) timely delivered and used by farmers | DISTRICT 1. Ensure timely supply of improved seeds to all farmers 2. Farmer mobilization on season preparation (land use consolidation, and inputs use) 3. Organize and monitor the agricultural inputs distribution system involving agro-dealers and districts agronomist. MINAGRI/RAB 1. Follow up seed companies and local seed multipliers to avail seeds on time | MINAGRI/RAB, DISTRICT, Private Agro dealers
79
|  |  |  | Use of inorganic fertilizers increased | Kg of fertilizers timely delivered and used by farmers | UREA: 319,805 DAP: 850,288 NPK: 1079079 KCL+Blends: 176,580 | RAB | Delivery: fertilizers available in suppliers' warehouses and ready for distribution to farmers for Season A : UREA(175,000Kg); DAP (450,000Kg); NPK (900,000Kg); KCL + Blends (125,000kg) by 30th August 2019 | UREA(175,000Kg); DAP (450,000Kg); NPK (900,000Kg); KCL + Blends (125,000kg) | Delivery: fertilizers available in suppliers warehouses and ready for distribution to farmers for Season B: UREA: 175,000 kg, 450,000 KG, NPK; 1,200,000 kg KCL+Blends: 125,000 by 29th February 2020 | UREA(175,000Kg); DAP (450,000Kg); NPK (1,200,000Kg); KCL + Blends (125,000kg) | UREA: 350,000 kg; 'DAP: 900,000 kg; NPK: 2,100,000 kg; KCL+Blends: 378,000 kg) of fertilizers timely delivered and used by farmers | DISTRICT 1. Ensure timely supply of fertilizers to all farmers 2. Farmer mobilization on season preparation (land use consolidation, and inputs use) 3. Organize and monitor the agricultural inputs distribution system involving agro-dealers and districts agronomists. MINAGRI (RAB & NAEB) 1. Follow up on timely fertilizer distribution 2. Provide technical support on fertilizers use for food crops and cash crops 3. Regular monitoring of fertilizers use by farmers | MINAGRI/RAB, DISTRICT, Private Agro dealers
|  |  |  | Area of land protected against erosion increased | Number of ha of radical terraces (RT) constructed | 5,857 ha | Administrative data | 30 | 20 | 30 | 20 | 100 | DISTRICT: 1. Site identification and beneficiaries identification 2. Site identification 3. Terracing activities, supervision and Payment, LODA: 1. Guidences establishment of funds utilisation 2. Funds transfert | DISTRICT, LODA, MINAGRI | 96880000
81 |  |  |  |  | Number of Ha of progressive terraces (PT) improved (Ha ) | 16406 ha | Administrative data | 500 | 150 | 200 | 150 | 1000 | DISTRICT 1. Site identification 2.To mobilize the population for soil erosion controle through Umuganda | RAB,DISTRICT,Local population
82 |  |  |  | Effective and efficient irrigation developed under an Integrated Water Resource Management (IWRM) framework | Ha on Small scale irrigation |  | District report | 50 | Follow up | Follow up | Follow up | 50 | RAB 1. Joint planning with RAB for SSIT to set implementation modalities 2. Implement Small Scale irrigation technologies development 3. Provide technical assistance and monitoring DISTRICT 1. Mobilization of farmers and technical support for irrigation | RAB,DISTRICT,Local population | 16875000
83 |  |  |  | Extension services enhanced | Number of farmers reached | 51391 | District reports | 51390 Farmers registerd in SNS, 17130 farmers trained |  | 17130 farmers trained |  | 51390 Farmers registerd in SNS, 34260 farmers trained | DISTRICT 1.'To register 51,390 farmers in SNS, 2.To train 34,260 farmers | DISTRICT, Farmers organizations
84 |  |  |  | Participatory planning and implementation of enhanced extension services by all stakeholders increased | Number of sessions held | 2 | District reports | 1 |  | 1 |  | 2 Agricultural sessions held | To organise and conduct agricultural planning sessions | RAB,DISTRICT,Agro dealers
Agricultural production for priority crops increased
AGRICULTURE
SUSTAINABLE CRPO PRODUCTION
85 |  |  |  | Drying shelters constructed | Number of Drying shelters constructed | 16 | District Administrative data | Identification of sites and tendering |  | 4 |  | 4 | DISTRICT: 1.Sites identification, 2.Awarding and managing contract, 3.Monitoring and inspections MINAGRI: 1.Provision of technical specifications 2.Transfer of funds to construct drying shelters | RAB, District, Community coooperatives,Private sector | 74938000
86 |  |  |  | Agriculture production post harvest facilities improved | Number of maize hangar dryer locally established | 4 | District Administrative data |  |  | 10 | 7 | 17 | 1) Mobilize Twigire Muhinzi Groupe to establish maize hangar dryers within their community | DISTRICT, LOCAL POPULATION
87 |  |  |  |  | MT of Maize grain well collected and linked with market | 94 MT | District Administrative data |  |  |  | 150 | 150 | 1.To mobilize farmers to undergo maize drying 2) To organize cooperatives to collect maize production at sell point 3)To facilitate cooperatives to sell under contract with big deales. | DISTRICT, RDO
88 |  |  |  | Seeds production increased | MT of seeds locally produced | Wheat: 10MT,Irish Potato: 8750MT | District Report ,RAB |  | Wheat: 25 M, Irish Potato:7,000MT |  | Wheat: 25 MT,Irish Potato: 7,000MT | Wheat: 50 MT,Irish Potato: 14,000MT | 1.Mobilize community to multiply locally needed seeds 2.Agronomist to coordinate FFS and FPs activities and reports | District,RAB,MINAGRI,
Outcome:Increased Cash crops production
AGRICULTURE
CASH CROP PRODUCTION
89 |  |  | 93 | Vegetable production increased | Area of vegetables planted (Ha) | 88 | District Administrative data | 200 | 50 | 200 | 55 | 505 | DISTRICT To mobilise the population ,monitor and report and RAB& NAEB: To provide technical guidances. | NAEB/SOPYRWADistrict, loca farmers
90 |  |  |  | Pyrethrum production increased | Dried Pyrethrum flowers (MT) | 65 | District Administrative data | 10 | 45 | 15 | 0 | 70 | DISTRICT To mobilise the population, Production registeration,monitor and report NAEB: 1. To colaborate in production data collection,To provide technical guidances. | District, loca farmers | 10000000
91 |  |  |  | Horticulture promotion of vegetables | Ha | 88Ha | District reports | 45 | 30 | 25 |  | 100 | To mobilise the population ,monitor and report and 2. RAB& NAEB: To provide technical guidances. | NAEB,COMMUNITY,DISTRICT
92 |  |  |  | .Horticulture promotion of fruits | Ha planted | 30 ha of fruits, | District reports,field | Site and farmers identification | 400000 of avocado trees, | 100000 of avocado trees, |  | 500,000 fruit trees | 1.To interest and facilitate partners to provide planting material 2.To collaborate in distribution 3.To monitor sustainability | NAEB,COMMUNITY,DISTRICT
Outcome: Improved animal production
AGRICULTURE
SUSTAINABLE ANIMAL PRODUCTION
93 |  |  |  | Cows distributed to poor families through Girinka Program | Number of cows distributed to poor families through Girinka | 11847 | District Administrative data | 157 | 375 | 350 | 200 | 1082 | Beneficiries identification and mobilisation for cows sheeds contruction under community approach,Tendering, cows distribution, Field visit to beneficiairies | RAB,District,RDDP/IFAD,community | 243094261
94 |  |  |  | Improved genetics for cows | Number of cows inseminated | 19873 | District Administrative data | 1000 | 1200 | 1200 | 1100 | 4500 | DISTRICT 1. To conduct community mobilisation, 2. To inseminate cows, 3. To organise and conduct field visit to farmers. | RAB,DISTRICT,RDDP | RDDP Budget
95 |  |  |  | Calves registered | Number of AIl born calves registered | 3127 | District Administrative data | 210 | 420 | 630 | 630 | 1890 | DISTRICT: 1. Identify beneficiaries among farmers, 2. To monitor and record calves RDDP: P 3. roviging technical expertise , 4. Providing semen | RAB,DISTRICT,RDDP | RDDP Budget
96 |  |  |  | Number of AI born calves registered | Livestock vaccinated against diseases | LSD: 36 000; BQ: 32 000; RVF: 15 000; Brucellosi: 3 427 | District Administrative data | Campaigns mobilization and vaccine acquisition | LSD: 10 000; BQ: 10 000; Brucellosis:1500; RFV:5 000 | LSD: 10 000; BQ: 10 000; Brucellosis:1500; RFV:5 000 | LSD:16 000, BQ:12 000; Brucellosis:427; RVF: 5 000 | LSD: 36 000, BQ: 32 000; Brucellosis:3 427; RVF: 15 000 | DISTRICT 1. To organise and conduct community mobilization, 2. To vaccinate Cow, 3. To organise and conduct Field visite to farmers | RAB,DISTRICT,RDDP | RDDP Budget
97 |  |  |  | 5.Animal Care Paravets introduced in community | number of Paravets trained | 571 | District, | 571 |  |  |  | 571 | To recruite volunteers,conducting trainings, certificate skilled ones. | District,RDDP,RAB
98 |  |  |  | 6. Milk aggregation points (MCPs) constructed | Number of Milk Aggregate points constructed | N/A | District, | 2 | 3 |  |  | 5 | Site identification, To construct Milk Aggregation points and suprvision, monitoring and reporting | GoR,Local farmers,RDDP
99 |  |  |  | Animal folder and forage plants multiplication sites installed | Number of sites | 30ha | District,field | 30 | 30 | 20 | 20 | 100 ha | 1.To mobilize farmers to plant at every terraces 2.To facilitate in cuttings/seedling provision 3. to disseminate multiplied noutritious forage | RDDP, DISTRICT
100 |  |  |  | 7.Cow sheeds, clushes established in community as animal care BEST practices | 1. Number of cowsheds for poor farmers constructed. |  | District,field | 170 cowsheds, | 170 cowsheds, | 170 cowsheds, | 61 | 571 cowsheds | 1. To construct 5,710 cow sheds for poor families trough community works 2.To construct 571 clushed trough community works to care animals 3.To establish 3 model communal cowsheeds | RDDP, DISTRICT
101 |  |  |  | Small livestock promoted | Number of poultry (sasso and layers) distributed | N/A |  | Beneficiairies identification and tender process | 3000 | 3000 | 3000 | 9000 | To mobilize youth Tendering , Poultry distribution (8000 sasso and 1000 layers) to youth identified, Field visit to beneficiairies | RAB, DISTRICT | 181000000
102 |  |  |  |  | Number of Pig distributed | N/A |  | Beneficiairies identification and tender process | 150 | 150 | 140 | 440 | To mobilize youth, Tendering, 440 Pigs distribution, Field visit to beneficiairies | RAB, DISTRICT
Forest coverage maintained and increased
AGRICULTURE
FORESTRY
103 |  |  |  | Increased area under agro-forestry | Ha of land under agro forestry | 10 920.36ha | District Administrative data | Nursery installation | Nursery installation | 85 |  | 85 | DISTRICT 1. Nursery preparation 2. sites preparation 3. planting and supervision |  | 3706400
105 |  |  |  | Forest cover increased and maintained | Ha of new woodlots established | 3 656.86ha | District Administrative data | Nursery installation | Nursery installation | 25 |  | 25 | Nursery preparation, sites preparation, planting and supervision | MOE, District | 12374706
Increased productive Jobs through entrepreneurship and business development
PRIVATE SECTOR DEVELOPMENT
BUSINESS SUPPORT
106 |  |  |  | Productive Jobs increased | Number of productive jobs created | 13383 | District Administrative data | 1000 | 1500 | 2500 | 1497 | 6497 | DISTRICT 1. Flag ship project identification, 2. Organize and conduct District potentialities awareness campaign, 3. Data collection analysis on job created, 4. Field visit to job holders |  | 1000000
107 |  |  |  | New TVET graduates accessing start up toolkit facility | Number of TVET graduates who received start up toolkit | 172 | District Administrative data | Beneficiairies identification |  | 37 |  | 37 | DISTRICT 1. Mobilize TVET graduates and apprentices to benefit the product for self employment, 2. Field visit to beneficiaries | GOR | 18500000
108 |  |  |  | Cross Border Market Operationalized | Occupancy rate of Cyanika cross border market | 40% | District Administrative data | 45% | 50% | 55% | 60% | 60% | DISTRICT 1. Capacity buliding of tenants, 2. Maintanance of CBM, 3. Community mobilization and monitoring | DISTRICT, RDB | 1000000
[5 empty] | Number of agri business projects for graduates which received start up capital | 2 | District Administrative data |  |  |  | 3 | 3 | beneficiries identification, mobilisation, linkage to Micro fi-nance institutions | DISTRICT, NEP
[5 empty] | Number of model village projects established |  |  |  |  | 1 | 2 | 3 | Project elaboration and analysis, supporting the projects , field visit | DISTRICT
109 |  |  |  | Start-up MSMEs for Youth and Women coached to access finance | Number of start-up MSMEs for Youth and Women coached to access finance | 761 | District Administrative data | 95 | 110 | 102 | 73 | 380 | DISTRICT 1. Youth and Women mobilisation for business creation, 2. linkage to financial institutions, 3. Field visit to beneficiaries and reporting | DISTRICT,RCA,PSF | 5500000
110 |  |  |  | Inspections of cooperatives and SMEs increased | Number of cooperatives and SMEs inspected and coached | 50 | District Administrative data | 24 | 24 | 24 | 24 | 96 | To inspect cooperatives at Sector level for good management and governance | DISTRICT, PSF | 960000
111 |  |  | TRADE AND INDUSTRY | Market Linkage and value chains facilitated | Number of meeting held | 4 meetings held | Quarterly report | 1 | 1 | 1 | 1 | 4 meetings held (from irish potatoes and milk,….. ) | Hold quarterly meeting to facilitate linkages and value chains to ensure smooth market | DISTRICT,MINICOM, MINAGRI | 2000000
112 |  |  |  | Organise and attend One District &Provincial trade fair per year (Made in Rwanda Exhibition) | Number cooperatives & SMEs participating in trade fair | 10 SMEs & Cooperatives participated in trade fairs | District Administrative data |  | 1 |  |  | 1 Made in rwanda exibition organised | Selecting innovative business amoung SMEs & Cooperatives, facilitating 10 SMEs & Cooperatives to participates at District and Provincial trade fairs. | DISTRICT, MINICOM ,MINIYOUTH,PSF | 3000000
Outcome: Increased enrollement of Ejo Heza saving scheme
113 |  |  | FINANCIAL SERVICES | Enrollement of Ejo Heza saving scheme increased | Number of Ejo Heza new members enrolled | 2458 | Ejo Heza report | 1000 | 1517 | 2000 | 2400 | 6917 | Community mobilisation | DISTRICT, MINECOFIN | 20000000
114 |  |  |  |  | Amount saved in Ejo Heza saving scheme | 2702421 | Ejo Heza report | 44391912 | 67342530 | 88783820 | 106540588 | 307058850 | Community mobilization | DISTRICT,MINECOFIN
|  |  |  | Eligible beneficiaries supported through Financial services | Number of loans advanced to eligible beneficiaries under VUP/Financial services to support their Income Generating Activities | N/A | District report | 1. Mobilization 2. Identification of beneficiaries 3. Dissemination of guidelines | 1. Beneficiairies training 2. Loan disbursement | 363 | 726 (Cumulative | 726 loans advanced to eligible beneficiaries under VUP/Financial services | DISTRICT: 1)Targeting list updating, 2) Monitor activities progress and mobilize beneficiaries to access loans 3) Proper management of funds under Financial Services | DISTRICT, SACCOs
|  |  |  | Recovery of Funds provided through Financial Services | % of new loans recovery rate from fiscal year 2019/2020 | N/A | Administrative District data |  |  | 75% | 75% | 75% | DISTRICT 1. Mobilize eligible households for new loans 2. Monitor contracting new loans 3. Monitor paying back of new loans | DISTRICT, SACCOs
|  | 5. ENERGY | IMPROVEMENT OF ACCESS TO ENERGY | Households connected to electricity | Number of new households on-grid connection | 22110 | Quarterly basis reports | 500 | 1500 | 2000 | 2037 | 6037 | District: Community mobilisation, reporting, REG/EUCL: Electrical lines construction and HHs connection | DISTRICT, REG
[5 empty] | Number of new households off-grid connection | 5277 | Quarterly basis reports | 154 | 250 | 250 | 369 | 1023 | Community mobilisation, support to poor households, field visit to beneficiaries | DISTRICT, REG | 36768000
Increased internet connectivity to productive use areas
|  |  | ICT | High ICT quality skills leveraging knowledge developed | Number of institutions (administrative offices, schools, Health facilities, SACCOs) connected to Internet | 52 | District Administrative data | Cells identification of signal availability | 10 | 7 |  | 17 Cell offices | DISTRICT: Identification of signal and connect 17 cell office with 4G
[5 empty] | Number of citizens trained under digital Ambassadors Programmme | N/A | Administrative data |  | 100 | 100 | 100 | 300 | Training and community mobilisation | RDB, RISA, DISTRICT
[5 empty] | Number of citizens who visit served and trained in SAPs and list of services mostly offered | N/A | Administrative data |  | 100 | 100 | 100 | 300 | Training and community mobilisation | MINIICT, RDB
[5 empty] | Number of new SAPs established at cell levels | N/A | Administrative data |  | 4 |  |  | 4 | identifying cell to be established with New SAPS Establishing SAPS at cell leves | MINIICT, RDB, RISA
[5 empty] | Number of existing SAPA operationalised at cell levels | N/A | Administrative data |  | 4 |  |  | 4 | identifying cell to be established with New SAPS Establishing SAPS at cell leves | MINIICT, RDB, RISA
[5 empty] | Number of existing SAPA operationalised at cell levels | N/A | Administrative data |  | 4 |  |  | 4 | identifying cell to be established with New SAPS Establishing SAPS at cell leves | MINIICT, RDB, RISA
Outcome: Increased access to basic infrastructure at the rural level
|  | 11. WATER AND SANITATION | WATER INFRASTRUCTURES | Rehabilitation of old water Supply System | Number of old water supply system rehabilitated at 100% | 2 | Field visit reports | Procurement process and study | Contract signature | 3 (rehabilitated at 20%) | 3 (rehabiliataed at100%) | 3 (rehabilitated at 100%) | DISTRICT 1. Procurement process, 2. Rehabilitation, supervision for 3 old water supply systems.(Mahongora-KajerijeriI 4.41 km ,Nyamirembe-Ndago 2.99 km ,NYyiramikore-Ruyange 2.3 km | DISTRICT, WASSAC | 100000000
|  |  |  | Ruhunde -Rushara Water supply line constructed | Number of km constructed (Water Network) | 19.6 | Field visit reports | Procurement process | 12 | 14 | 16.4 | 42.4 | 1.To construct 42.4km of pipeline on Ruhunde-Rushara 2.To construct water tanks 3.To construct water points. | DISTRICT, WASAC | 600000000
|  |  |  | Increased access to clean drinking water | Nbr of HHs connected to water | 14 724HHs | District Administrative data | Beneficiaries identification | 35 | 35 | 35 | 105 | DISTRICT: To identify and mobilize beneficiaries, WASAC: To connect water drinking to HHs | DISTRICT, WASAC
[5 empty] | Nbr of HHs accessing to clean water | 14 724HHs | District Administrative data | Completion of Ruhunde Rushara water supply system | 750 | 1000 | 1200 | 2950 | DISTRICT: To construct and rehabilitate water supply systems | DISTRICT, WASAC
|  |  | Public water taps operationalized and properly managed |  | Number of public water taps operational | N/A | District/WASAC reports | Identification of non operational water taps | 12 | 20 | 20 | 52 |  | DISTRICT 1. Rehabilitation of non-operational systems and taps 2. Monitor private operators contract compliance 3. Ensure tap managers availability 4. Monitor and ensure regular maintenance of water infrastructure 5. Awareness campaign to the public 6. Recover arrears for the water bills
|  |  |  | Compliance to existing rural water tariff enforced | Percentage of compliance to existing rural water tariffs | N/A | District/WASAC reports | - | 25% | 50% | 100% | 100% |  | DISTRICT 1. Water Price and toll free number written on public taps 2. Public awareness on existing rural water tariffs 3. Regular monitoring and reporting on tariff compliance
|  |  |  | 2. Hyigiene and Sanitation promoted | Number of trained clubs | Trainees identified | number of clubs trained |  | 12 |  |  | 12 | Training hyigens clubs | DISTRICT
Outcome: Increased access to basic infrastructure for rural households
|  |  |  | Roads Maintained | Km of road maintained | 220.3 | District Administrative data | 50 | 70 | 74 | 70 | 264 | Procurement, Road maintenance and supervision. | GoR | 172000000
|  |  |  | Bridges constructed | Number of bridges constructed | 35 | District Administrative data | 13 bridges identified, Procurement process | Contract signed,works started | 7 | 6 | 13 | Bridges identification, Procurement process, Bridges construction. Supervision and reporting | DISTRICT | 70000000
Outcome: Enhanced rural settlements that facilitate access to basic services
|  | 13. HOUSING ,URBAN DEVELOPMENT AND LAND MANAGEMENT | ESTABLISHMENT AND IMPLEMENTATION OF URBAN MASTER PLANS | Rusumo master plan implemented | Km of rods constructed and plots demarcated | Master plan aproved | District Administrative data | Procurement process and Land expropriation | 1 | 1 | 2 | 4 | 1.Land expropriation 2.Roads terracing conastruction andplots demarcation 3.electrical line construction | DISTRICT, RHA | 80000000
|  |  | PROMOTION OF HOUSING AND SETTLEMENT | Households (HHs) from scattered and High Risk Zones (HRZs) relocated | Number of HHs resttled in Imidugudu sites | 3444 | Field visit reports | 1.Plot demarcation and servicing | 38 | 100 | 200 | 338 | 1.Plot demarcation and servicing 2.Community moblisation and support to poor Households, relocate 38 HHs from High tisk zones and 300HHs from scarted settlements | DISTRICT, RHA | 176081083
|  |  |  | IDP Model village established | Kagano IDP Model Village constructed | 5 Houses 4 in 1 and cowshed | District Administrative data | Procurement process and Land expropriation | 20% | 60% | 100% | 100% | 1.Rehabilitation of 4Km of Roads; 2.Construction of Agakiriro; 3. Construction of one complex play ground and social oriented multipurpuse hall 4.Connecting houses to grid electricity; 5.Connecting Households to clean water. | DISTRICT, RHA | 340678678
[5 empty] | Shyaga IDP Model Village Developped | Site identified | District Administrative data | Procurement process and Land expropriation | 25% | 60% | 100% | 100% | 1.Land expropriation 2.Roads terracing construction 3.electrical line construction | DISTRICT, RHA | 110000000
|  |  | LAND USE PLANNING AND MANAGEMENT | 1. Expropriation and compesation on land use for public interests is done | Number of Ha expropriated | Quarterly report | Report on expropriation | 1 | 1 | 1 | 1 | 4 | 1)Targeting &approval of beneficiaries 2)Transferring funds to beneficiaries 3) Beneficiary tracking | LODA, DISTRICT
|  |  |  | Land registered and coverde in sectors | Number of Sectors to be coverd in State Land Registration | 17 | District report |  |  |  |  | 17 | 1)Timely establisment of beneficiary payrolls &payments 2)Timely fund requests from MINECOFIN&LODA 3) Beneficiary payments tracking | LODA, DISTRICT
|  |  |  | land week campaign disagregated and conducted | Number of land week campaign disagregated by districts | 1 | District reports |  |  |  |  | 2 | 1)Targeting &approval of beneficiaries 2)Transferring funds to beneficiaries 3) Beneficiary tracking 4) PW Project planning, execution & monitoring | LODA, DISTRICT
|  |  | Households (HHs) from scattered and High Risk Zones (HRZs) relocated |  | Number of HHs resttled in Imidugudu sites | 3444 | Field visit reports | Beneficiaries identified, Community mobilized | 38HHs from High risk zone | 100HHs from scattered settlements | 200HHs from scattered settlements | 338 | 1.Community mobilisation, relocate 38 HHs from High risk zones and 300 HHs from scattered settlements | DISTRICT, RHA | 176081083
|  |  | IDP Model village established |  | Kagano IDP Model Village constructed | 5 Houses 4 in 1 and cowshed | District Administrative data | Procurement process and Land expropriation | 5% | 60% | 100% | 100% | DISTRICT 1.Rehabilitation of 4Km of Roads; 2.Construction of Agakiriro; 3. Construction of social oriented multipurpose hall 4.Connecting houses to grid electricity; 5.Connecting Households to clean water 6.Monitoring and reporting | DISTRICT, RHA | 340678678
|  |  | Shyaga IDP Model Village Developped |  | Shyaga IDP Model Village Developped | Site identified | District Administrative data | Procurement process and Land expropriation | 1.5ha of land expropriated | 1km of road terrassed | 2km of road terrassed | 1.5ha of land expropriaited and 2km of roads terrassed |  | DISTRICT 1.Land expropriation 2.Terracing of 2km of Roads for plots demarcation | 130000000
Outcome: Extremely poor households have increased access to complementary livelihood development services for economic empowerment
|  | SOCIAL DEVELOPMENT | SOCIAL PROTECTION | 1. All 3,847 eligible households accessed VUP DS support benefit | Number of HH beneficiaries supported with VUP Direct Support (DS) | 3750 | District Administrative data | 3687 |  |  |  | 3687 | DISTRICT 1. To identify DS beneficiaries, 2. To provide DS to beneficiaries, 3. To monitor timely payment, 4. To conduct field visit to DS beneficiaries | LODA, DISTRICT | 531458928
[5 empty] | Percentage of VUP /DS payments made within 10 days after the end of month | 95% | District reports | 100% |  |  |  | 100% | PW Project planning, execution & monitoring to ensure labor instensivity at 70% | LODA, DISTRICT
|  |  |  | 2. Labor intensive cPW and ePW delivered to extremely poor households | Number of HH beneficiaries employed under Classic Public Works (cPWs) | 4489 | District Administrative data | Project preparation and targeting beneficiaries | 6183 |  |  | 6183 | 1)Timely establisment of beneficiary payrolls &payments 2)Timely fund requests from MINECOFIN&LODA 3) Beneficiary payments tracking | LODA, DISTRICT | 1651767820
[5 empty] | Average working days gained by HHs beneficiary employed under VUP PWs | 80 | District Administrative data | Project preparation and targeting beneficiaries | Targeting list |  | 110 worked days per HH per year | 110 worked days per HH per year | 1)Targeting &approval of beneficiaries 2)Transferring funds to beneficiaries 3) Beneficiary tracking | LODA, DISTRICT
[5 empty] | No of eligible households headed by females & males benefiting from VUP-ePW | 638 | District Administrative data | Project preparation and targeting beneficiaries | 1311 |  |  | 1311 | to identify and prepare beneficiaries, to acquiere cows , to visit and monitor the cows health | LODA, DISTRICT | 224715443
[5 empty] | Percentage of timely payments made to VUP beneficiaries ((DS: Within 10 days after the end of the month) ePWs&cPWs: Within 15 days after the end of working period | 100 | District Imihigo report, June 2019 | 100% | 100% | 100% | 100% (DS: Within 10 days after the end of the month) ePWs&cPWs: Within 15 days after the end of working period | 100% (DS: Within 10 days after the end of the month) ePWs&cPWs: Within 15 days after the end of working period | DISTRICT 1. Prepare and submit request/cash flow plans on time 2 Monitor disbursement of funds 3. Transfers funds to beneficiaries 4. Timely sumbmission of OPs to MINECOFIN | DISTRICT.LODA
|  |  |  | Multi- sectoral approach implemented to enhance graduation of vulnerable Households out extreme poverty | Number of cows distributed to poor families through Girinka | 11847 | District Administrative data | 157 | 375 | 350 | 200 | 1082 | DISTRICT 1. identification of Beneficiries 2. Mobilisation for cows sheeds contruction under community approach, 3. Tendering, cows and distribution, 4. Field visit to beneficiairies | DISTRICT 1. identification of Beneficiries 2. Mobilisation for cows sheeds contruction under community approach, 3. Tendering, cows and distribution, 4. Field visit to beneficiairies | 243094261
[5 empty] | Number of extremely poor HHs supported through Social protection to achieve minimum required livelihoods | N/A |  | 878 | 1754.4 | 3070.2 | 3070.2 | 8772 | DISTRICT 1. Support 177 Children (aged 6-14) from vulnerable HHs in Ubudehe Cat.1 to enroll in schools 2. Support 170 people from vulnerable HHs in Ubudehe Category one to access technical/vocational skills 3. Support 585 Eligible HHs in ubudehe cat1 with off/on grid energy 4. Support 85 eligible vulnerable HHs with fertilizers 5. Support 85 HHs in Ubudehe Cat.1 with improved seeds 6. Train 1,350 people from vulnerable Households on financial literacy and small business development 7. Provide training to 481 eligible vulnerable HHs on good agricultural practices 8. Support HHs in Ubudehe Cat.1 to access to clean water 9. Provide loans to people from HHs in category one through VUP/FS to support income generating activities 10. Support 719 beneficiaries under HIMO program |  | 101300000
|  |  |  | Cows distributed to poor families through Girinka Program | Number of cows distributed to poor families through Girinka | 11847 | District Administrative data | 157 | 375 | 350 | 200 | 1082 | Beneficiries identification and mobilisation for cows sheeds contruction under community approach,Tendering, cows distribution, Field visit to beneficiairies | DISTRICT, RAB, STAKEHOLDERS
|  |  |  | Unemployed rural youth groups/cooperatives and/or groups of vulnerable people supported with small livestock | Number of small livestock distributed | 0 | MINAGRI earmarked guidelines 2019-2020 | Beneficiairies identification and tender process | 3000 (sasso and layers); 100 pigs | 3000 (sasso and layers); 100 pigs | 3000 (sasso and layers); 130 pigs | 9000 ( (8000 sasso and 1000 layers); 330 Pigs | DISTRICT 1. To mobilize youth 2. Tendering , 3. Poultry and pigs distribution (8000 sasso and 1000 layers ; 330 pigs) to youth identified, 4. Field visit to beneficiairies | DISTRICT, MINAGRI | 181000000
|  |  |  | PwDs cooperatives fianciallly supported | Number of PwDs Cooperatives financially supported | 3 | District Administrative data | 1 | 1 | 1 | 1 | 4 | DISTRICT 1. To facilitate PwDs to elaborate projects , 2. To select best projects to be fianced, 3. To support best projects and monitor PwDs cooperatives | DISTRICT, NCDP
[5 empty] | Number of PWDs teams facilitated to participate in nationa; championship | 1 | District reports |  | 3 |  |  | 3 | To facilitate PWD teams to participate to national championship | DISTRICT, NCDP
|  |  |  | Genocide survivors provided with adequate shelter | Number of houses for Genocide Survivors constructed | Site identified | District Administrative data | Contract negotiation and Beneficiaries identification | 4(10%) | 4(70%) | 4(100%) | 4 (100%) | DISTRICT: 1. To identify site, 2. To expropriate land, FARG: 1. To transfer funds | DISTRICT, FARG | 141000000
|  |  |  | Linkages between core Social Protection and complementary programs strengthened | Number of eligible HHs beneficiary receiving asset transfers grants under Minimum Package for Graduation (MPG) framework | 774 | District Administrative data | 470 | 470 | 979 |  | 1919 | To providebeneficiary receiving asset transfers grants under Minimum Package for Graduation (MPG) framework | 184000000
|  |  |  | Access to basic needs by HHs in Ubudehe cat1 according to HH profiling and human security assessment repor | Number of eligible HHs in ubudehe cat1 with access to agricultural fertilizers and improved seeds | 12912 | District reports |  |  |  |  | 200 | 1. To identify HH of beneficiaries, 2. To provide guidelines and technical specification for houses rehabilitation 3. shelter rehabilitation, 4. Monitoring (field vist and report) | LODA, DISTRICT | 510000
[5 empty] | Number of eligible HHs in ubudehe cat1 benefited small livestock | 7714 | District Reports |  |  |  |  | 9000 poultry and 440 Pigs | 1. To update the list of HH beneficiaries, 2. To link beneficiaries to off/on grid energy suppliers, 3. To sign contract with suppliers and pay bills, 4. Contract management (suppling off/on grid energy to beneficiaries), 5. Monitoring (field vist and report) | LODA, DISTRICT | 60000000
[5 empty] | Number of eligible HHs in ubudehe cat1 benefited shelter | 1808 | District/DSU |  |  |  |  | 337 | 1. To provide support to teams initiated by PWD, 2. To support PWD teams to participate in National championship | NCPD, DISTRICT | 5000000
[5 empty] | Number of eligible HHs in ubudehe cat1 benefited toilettes | 9729 | Sectors |  |  |  |  | 1000 |  | DISTRICT, SFH | 5000000
[5 empty] | Number of eligible HHs in Ubudehe cat1 benefited from off/on grid energy | 14323 | Sectors |  |  |  |  | 1000 | 1. To held meetings of NCPD Committees; 2. To held NCPD District congress | NCPD, DISTRICT | 3500000
[5 empty] | Number of females and males beneficiries of HIMO projects |  | District reports |  |  | 2115 | 5883 | 7998 | identification and HIMO projects distribution | DISTRICT, LODA
[5 empty] | Number of females and males beneficiries of HIMO projects saving 30%of total earnings |  | District reports |  |  | 2115 | 5883 | 7998 | mobilisation to savings | DISTRICT, SACCO
|  |  |  | PwDs cooperatives fianciallly supported | Number of PwDs Cooperatives financially supported | 3 | District Administrative data | 1 | 1 | 1 | 1 | 4 |  | DISTRICT 1. To facilitate PwDs to elaborate projects , 2. To select best projects to be fianced, 3. To support best projects and monitor PwDs cooperatives
[5 empty] | Number of PWDs teams facilitated to participate in nationa; championship | 1 | District reports |  | 3 |  |  |  | 3 | To facilitate PWD teams to participate to national championship | DISTRICT, NCDP
[5 empty] | Number of NCPD Committee members meetings supported | 16 | NCPD/District | 4 | 4 | 4 | 5 |  | Reintegrate teen mothers into social protection schemes | MIGEPROF | 20000000
[5 empty] | Number of albinos people supported with skin lotion | 25 | NCPD/District | 30 | 30 | 30 | 30 |  | 1. To train people in disaster mitigation, 2. To organize of Management committees at Sector level | MIDMAR, DISTRICT | 2000000
[5 empty] | Pw Ds provided with assistive devices | 5 | NCPD/District | 2 | 5 | 3
|  |  |  | Victims of GBV supported | Number of teen mothers benefited from Social protection schemes | 17 | District/GGU |  | 7 | 10 |  |  | Land expropriation, construction work and supervision | District, CSO
|  |  |  | HHs supported from disaster issues | Number of schools (primary and secondary0 reached out in disaster risk reduction education | N/A | District reports | 6 | 3 | 3 |  | 12 | Sensitisation, identification of schhols at risk of disaster | DISTRICT, MINEMA
|  |  |  | Human security issues addressed in the District | Number of houses and their accessories (toilets and kitchens) constructed for eligible vulnerable HHs (including those in Ubudehe cat.1 ) | 115 | Administrative data | 76 | 79 | 81 | 89 | 325 houses and their accessories (kitchen and toilet) constructed for eligible vulnerable HHs (including those in Ubudehe cat.1 ) | DISTRICT 1. To identify beneficiaries 2. To construct/ rehabilitate kitchen to HH in cat1 3. To monitor and reporting | DISTRICT, MINALOC
[6 empty] | 3417 |  | 88 | 97 | 99 | 107 | 391
[6 empty] | 85 | District Administrative data | Benefciaries identification |  | 85 |  | 85 |  |  | 5100000
[6 empty] | 343 | District report | 142 | 282 | 235 | 282 | 941
[6 empty] | 19944 | District report | 513.75 | 1027.5 | 856.25 | 1027 | 3425
[5 empty] | Human Security Task Force at District, Sector and Cell level in place | District report |  |  |  | Human Security Task Force at District, Sector and Cell level operationalized | Human Security Task Force at District, Sector and Cell level operationalized |  | District 1. Appointing members and operationalizing Human Security Taskforce at different levels (District, Sector and Cell levels 2. Conduct regular meetings to monitor and report on implementation progress of human security issues identified: (District level: Twice in a quarter, Sector Level: Monthly and at Cell level: Twice/Month)
Increased education infrastructure
EDUCATION
PRIMARY
|  |  |  | Classrooms Constructed | Number of new classrooms constructed under Gor funds | 611 | District Administrative data | 56 (25%) | 56 (100%) |  |  | 56 (100%) | Land expropriation, construction work and supervision | DISTRICT, MINEDUC
|  |  |  | Latrines constructed | Number of New Latrines constructed | 782 | District Administrative data | 28 (25%) | 28 (100%) |  |  | 28 (100%) | Land expropriation, construction work and supervision | DISTRICT, MINEDUC
|  |  |  | Rehabilitation of classrooms under Government funds | Number of classrooms rehabilitated | 42 | District Administrative data | classrooms identified to be rehabiliatated | 12 | 12 | 6 | 30 | To identify classrooms to be rehabilitated, to procede to rehabiliatation, supervision and reporting | DISTRICT, REB, MINEDUC
|  |  |  | Drop out rates in schools reduced | Percentage of students drop outs | Primary 6.8% Lower Sec. 4.2% Upper Sec 6.4% | - |  |  |  | Primary 6.2% Lower Sec. 3.6% Upper Sec 5.8% | Decrease of at least 1.9 for repetition and 0.6 for drop out | MINEDUC 1. Monitor the school attendance rate for students and teachers, highlighting the improvement made between quarters Schools Ensure the use of class register in order to effectively assist students with multiple absenteeism. | DISTRICT, REB, MINEDUC
|  |  |  | All learners attended schools on daily basis | Attendance rate in Primary, secondary and TVET (level 1 to 5) | 90.7% (Primary); 89.1% (Secondary) ; 93.7% TVET (level 1 to5) | Education statistics/ District | 99.9% | 99.9% | 99.9% | 99.9% | 99.9% in Primary, secondary and TVET(level 1 to 5) | District: 1. Inspect schools and implement the recommendations 2. Identify children of primary school age who are out of schools 3. Report on primary, secondary and TVET school enrolment, attendance and completion rates 4. Mobilize parents in holydays 5. Provide lunch to students through School feeding program 7. Proper use of class register (Ibidanago) MINEDUC 1. Monitor reporting of Education statistics | DISTRICT, REB, MINEDUC
Strengthening national administrative data: Civil Registration and vital statistics and Education administrative Statistics
|  |  |  | Education administrative statistics collected and timely registered through School Data Management System (SDMS): Primary Secondary and TVETs | Percentage of required education information recorded into the SDMS system with accuracy: 1. Students information (Number, Attendance, drop outs, Transition rates, Repetitions, Performance) 2. Schools staff ( Pupil: Trained Teacher ratio) 3. Infrastructures (Pupil Classroom ratio (PCR), Pupils Toilets ratio, Access to water, electricity and internet) | Currently 96% of information on students are in to SDMS | SDMS | Data cleaning and verification of data completeness | Data cleaning and verification of data completeness | Updates the information for 2020 school year | 100% of the required information for Primary, Secondary and TVETs are recorded into SDMS: 1. Students information (Number, Attendance, drop outs, Transition rates, Repetitions, Performance) 2. Schools staff ( Pupil: Trained Teacher ratio) 3. Infrastructures (Pupil Classroom ratio (PCR), Pupils Toilets ratio, Access to water, electricity and internet) | 100% of the required information for Primary, Secondary and TVETs are recorded into SDMS: 1. Students information (Number, Attendance, drop outs, Transition rates, Repetitions, Performance) 2. Schools staff ( Pupil: Trained Teacher ratio) 3. Infrastructures (Pupil Classroom ratio (PCR), Pupils Toilets ratio, Access to water, electricity and internet) | MINEDUC/ DISTRICT 1. Provide technical support to schools /sector and district 2.Capacity building on the use of SDMS 3. Monitoring the use of the SDMS DISTRICT 1. Ensure that all schools are recorded in to the system 2. Measures for re-enllorment of dropped out students and strategy to ensure that they will complete the level. 3. Identification of dropped out students 4. Effectively record students and monitor school attendance rate for students and teachers, | MINEDUC, DISTRICT
Improved performance of students in annual assessments and national examinations.
|  |  |  | Students performance increased in National Examinations: Primary 6, Secondary 3, Secondary 6 | Proportion of Students attaining Higher divisions in National Examinations (from previous Academic year) | Primary 6&S3 Division I: 1%, S3: 9% Division II:15% S3: 16% Division III:48% S3: 16% Division IV:28% S3: 46% Unclassified:8% S3: 13% Senior 6 • Pass with at least 2 principle passes: 57% • Pass without 2 principle pass: 32% • Fail: 11% | - |  |  | Primary 6&S3 Division I: 4%, S3: 15% Division II:119% S3: 23% Division III:51% S3: 13% Division IV:23% S3: 41% Unclassified:3% S3: 3% Senior 6 • Pass with at least 2 principle passes: 67% • Pass without 2 principle pass: 27% • Fail: 6% |  | Primary 6&S3 Division I: 4%, S3: 15% Division II:119% S3: 23% Division III:51% S3: 13% Division IV:23% S3: 41% Unclassified:3% S3: 3% Senior 6 • Pass with at least 2 principle passes: 67% • Pass without 2 principle pass: 27% • Fail: 6% | MINEDUC 1. Analysis of national examinations results. 2. Dissemination of national exams analysis report at districts level DISTRICTS 1. Self assessment of national exam performance and establish individual school improvement plan to improve learning outcomes 2. Conduct and keep record of continous/ formative assessments( end of lesson, end unit and term). 3. Analysis/Self assessment of comprehensive assessment term 1 and term 2 and 3 performance. 4. Establish school improvement plan for improved learning outcomes | MINEDUC, DISTRICT
|  |  |  | Output 14. 2: Students performance increased in: TVET L5 | Proportion of Students attaining Higher divisions in National Examinations (from previous Academic year) | Category I: 4% Category II: 33% Category III: 30% Category IV: 19% Category V: 13% Unclassified: 2% | - |  |  |  |  | Category I: 9% Category II: 37% Category III: 32% Category IV: 14% Category V: 8% Unclassified: 0%
Enhanced teachers welfare and operation of schools
|  |  |  | Teacher's salaries paid on time | Percentage of payments for Teachers’ salaries made on time (Submission of payment requests not later than 15th of every Month) | 60% | OPs | - | 100% | 100% | 100% | 100% of Payments of Teachers' salaries made on time Payment request submitted to MINECOFIN not later than 15th of every Month | District 1. Prepare payroll lists 2. Submission of Payment request to MINECOFIN not later than 15th of every Month MINEDUC: 1. Approval of Teachers placement 2. Verification and approval of payment lists not later than 17th of every month 2. Monitoring and follow up on timeliness of payment of teachers' salaries MINECOFIN 1. Verify and process teachers's salaries not later than 20th of every month | DISTRICT, MINEDUC
|  |  |  | Capitation Grant provided to Schools on time | Percentage of payments for Capitation grant) made on time (Submission of payment requests within 3 weeks of the first month of academic term) | N/A | SDMS | 100% | 100% | 100% | 100% | 100% of Capitation Grant Payments order made on time | DISTRICT 1. Prepare lists of schools benefiting the capitation Grant through SDMS 2. Verify and approve the lists of schools that benefit from capitation grant and submit to MINECOFIN 3. Prepare payment orders after approval of the lists and submit to MINECOFIN (within 3 weeks of the first month of academic term) | DISTRICT, MINEDUC
[5 empty] | Percentage of Schools that utilize capitation grants (funds) as stipulated in the guidelines | N/A | SDMS | 100% | 100% | 100% | 100% | 100% | MINEDUC 1. To prepare and issue to districts guidelines for the use of Capitation Grant 2. To monitor the use of capitation grant DISTRICT To monitor the use of capitation grant in schools
|  |  |  | Capitation Grant timely processed and properly managed | Percentage of Schools that properly utilize capitation grant | N/A | SDMS | 100% | 100% | 100% | 100% | 100% | MINEDUC 1. To prepare and issue to districts guidelines for the use of Capitation Grant 2. To monitor the use of capitation grant DISTRICT To monitor the use of capitation grant in schools | DISTRICT, MINEDUC
|  |  |  | School Inspection improved | Percentage of timely payment of allowances to Sector based School inspectors | N/A | MINEDUC Inspection reports | 100% | 100% | 100% | 100% | 100% | DiSTRICT 1. Timely disburse to Administrative Sectors the required allowances for Sector based School inspectors for each academic term 2. Timely payment of allowances to sector Based school inspectors (ahead of undertaking their missions) 3. Monitoring and reporting on use of allowance funds | DISTRICT, MINEDUC
|  |  |  | Girls rooms fully operationalized in schools | Percentage of secondary schools with fully equipped girls room (Icyumba cy’umukobwa) | N/A | MINEDUC Inspection reports | 100% | 100% | 100% | 100% | 100% | MINEDUC 1. To prepare and issue to districts a checklist of requirements that should be available in the Girls Room DISTRICT To monitor schools and ensure the Girls rooms are fully equipped with required materials | DISTRICT, MINEDUC
SECONDARY EDUCATION
|  |  |  | Teachers salaries in lower and secondary education paid | Payroll list established | 12 | Administrative report | 3 | 3 | 3 | 3 | 12 | To process and pay teachers salaries | DISTRICT, MINEDUC | 777468029
|  |  |  | All lower and secondary scholls subsidised | Number of quarterly transfert made | 4 | Administrative report | 1 | 1 | 1 | 1 | 4 | To process and transert | DISTRICT, MINEDUC | 78707834
|  |  |  | All lower and secondary scholls supported with scholl feeding | Number of transfert made in school feeding program | 4 | Administrative report | 1 | 1 | 1 | 1 | 4 | To support school feeding program | DISTRICT, MINEDUC | 290263727
|  |  |  | School hygien and promoted | Number of hygien inspection conducted | 4 | Administrative report | 1 | 1 | 1 | 1 | 4 | To organise and conduct hygien inspection | DISTRICT, MINEDUC | 6740000
Increased access to adult literacy
TERTIARY AND NON FORMAL EDUCATION
|  |  |  | Instructors are supported with incentive | Number of instructors supported with incentives |  | Administrative data | [5 empty] | To process and pay incentive to instructors | District | 13050000
|  |  |  | Adult literacy and numeracy increased | Number of people trained in adult literacy centers | 10481 | District Administrative data | Identification of beneficiairies | 5625 |  |  | 5625 | community mobilisation, training and rewarding
Improved accessibility and quality of health care
|  | HEALTH | Access to quality Health care | Health staff are remunerated | Number of payments made | 12 | District | 3 | 3 | 3 | 3 | 12 | 1.Update the liste of health staff 2. To process and paye Health Staff. | MSH | 919686795
|  |  |  | DPEM activities implemented | Number of sensition meetings conducted with stakeholders | 4 | District DPEM Reports | 1 | 1 | 1 | 4 |  | To conduct DHMT quarterly meetings | MSH | 920000
|  |  |  | Health staff are remunerated | Report on payments made | 12 | District Reports | 3 | 3 | 3 | 12 |  | To hold a Meeting for findings sharing on DHMT supervision. | MSH | 1728000
|  |  |  | Support the governing bodies and DHMT to carry out their functions effectively | # DHMT integrated supervision conducted | 2 |  | 2 |  |  |  | 2 | To conduct an integrated planning workshop | MSH | 16920000
|  |  |  | Output 9.3: Quality delivery and accessibility at health facility and community level increased | 4th Ante Natal Care (ANC) standard visit attendance (%) | 40.5% | HMIS | 43% | 48% | 55% | 60% | 60% | DISTRICT 1. Mobilization of Men and Women on ANC standard visits 2. Close follow up of pregnant women to ensure appointments are respected MoH 1. Provision of Ante Natal Care facilities and equipment 2. Capacity building (training and mentorship) of health Care Providers | DISTRICT, MINISANTE
|  |  |  | Coverage of Community Based Health Insurance Scheme (CBHI) increased | Percentage of people covered under Community Based Health Insurance Scheme (CBHI) | 88.24 | District Administrative data | 50% | 90% | 100% |  | 100% | DISTRICT Community mobilization
|  |  |  | Assisted deliveries at Health facilities increased | Percentage of assisted deliveries at health facilities | 83.8% | HMIS | 85% | 86% | 88% |  |  | 1. Mobilize community to establish Scooking demostration at village level and 2. Make follow up | NECDP, District
Outcome: Reduced malnutrition among children
|  |  |  | Joint action plan to eliminate malnutrition implemented | Proportion of Children who were in Red or Orange and Yellow colors (indicating risk levels of Child acute malnutrition as per MUAC screening) who graduate to Green color | N/A |  | 90% | 95% | 97% | 99% | 99% | 1.Conduct PDH Session 2. Conduct Nutrition Week 3. Mentorship and Supervision 4. Construct 85 kitchen gardens for eligible HHs in ubudehe cat1 | NECDP, District
|  |  |  | Home-based ECD operationalized at Village level | Number of villages with functional ECDs (Home based or Community Based or Center Based) serving at least 50% of eligible children (Aged under 6 Years) | 234 | District report | 571 home based ECDs operational | 571 home based ECDs operational | 571home based ECDs operational | 571 home based ECDs operational | 571 home based ECDs operational | DISTRICT 1. Children U5 meet 2 days per 2. Operationalize Village kitchen (Igikoni cy'Umudugudu) operationalized and attended by eligible parents (whose Children are Under 5 age) least twice per month 3. Conduct cooking demostrations | NECDP, District
|  |  |  | Optimal growth for all children under 5 monitored | Percentage of < 5 years children screened for acute malnutrition |  | HMIS and NECDP reports |  |  |  | 95% | 95% | MoH/CHWs 1. Avail equipments 2. Screening of children District 1. Mobilize parents 2.follow up with health centers to ensure growth monitoring is done | NECDP, District
[5 empty] | Percentage of < 2 years children screened using length mat for stunting visualisation |  |  |  |  | 50% | 95% | 95% | MoH/CHWs 1. Avail equipments 2. Screening of children District 1. Mobilize parents 2.follow up with health centers to ensure growth monitoring is done | DISTRICT, MINISANTE
|  |  |  | Rate of stunting among children <2 years is reduced | Percentage of stunting among children <2 years | 34.9% | MCCH Report |  |  |  | 31.72% | 31.72% | MoH/CHWs 1. Avail equipments 2. Screening of children 3. Follow up for children at risk District 1. Mobilize parents 2.follow up with health centers to ensure growth monitoring is done | DISTRICT, MINISANTE
|  |  |  | Early childhood development promoted | Number of ECDs constructed (low cost) | 1 | District Administrative data | Expropriation and site installation | 2 (10%) | 2 (40%) | 2 (100%) | 2(100%) | DISTRICT 1. Land expropriation, 2. Construction work by community approach, 3. ECDs equipment | DISTRICT, MIGEPROF | 58000000
Outcome:Increased contraceptive Prevalence
|  |  |  | Modern family planning uptake increased | % of married women up taking modern contraceptive methods | 42.09% | DISTRICT ADMINISTRATIVE DATA | 45% | 50% | 54.6% | 56% | 56% | 1.Avail the land 2.Expropriation 3.Construction works | District&Partners
Outcome:Infrastructure and medical equipment norms and standards strengthened
|  |  |  | Nyamicucu Health Post upgraded and operationalized | Nbr of health posts upgraded | Study | District Report |  | 1 |  | 2 |  | 1.Tenders process 2.Renovation works Follow-up | District &MoH
|  |  |  | ECDs Centers constructed (low cost) | Number of ECDs constructed (low cost) | 1 | District Administrative data | Expropriation and site installation | 2 (10%) | 2 (40%) | 2 (100%) | 2(100%) | 1. Land expropriation, 2. Construction work by community approach, 3. ECDs equipment | DISTRICT, MIGEPROF | 58000000
Increased Coverage of Community Based Health Insurance
|  |  |  | Mutuelle de santé campaigns conducted | Nbr of mutuelle de santé campaigns conducted and citizens satisfaction with health services increased | 88.24% | CRC | 60% | 78% | 80% | 100% | 100% | Community Mobilisation | DISTRICT
Outcome:Improved Referral System
|  |  |  | Health facilities are equiped with ambulance vehicles | Number of ambulance purchased |  | District reports | Tender process | Supply of ambulance | 1 | - | 1 ambulance car purchased | DISTRICT 1. Mobilization of funds to acquire ambulances 2. Purchase ambulance MoH 1. Mobilization of funds to acquire ambulances 2. Development and provision of terms of reference to acquire ambulance | DISTRICT, MINISANTE | 57000000
Maternal, Child and Infant mortality reduced
|  |  |  | Assisted deliveries at Health facilities increased | Percentage of births attended by skilled health professionals | 93.93% | District Administrative data | 91% | 92% | 93% | 95% | 95% | DISTRICT Community mobilization | DISTRICT, MINISANTE
|  |  |  | Family Planning (FP) services provided | FP modern method utilization rate (%) | 42.09% | District Administrative data | 45% | 50% | 52.5% | 54.6% | 54.6% |  | DISTRICT, MINISANTE
Reduced burden of communicable and non-communicable diseases among Rwandan population
|  |  |  | Access Viral Hepatitis prevention and treatment services inreased | Percentage of Adults aged 15 Years and above screened for Hepatitis C | 40% |  |  | 50% | 70% | 80% | 80% | MINISANTE/RBC 1. Procurement and distribution consumables, reagents and required equipment for screening; 2. Strengthen the cold chain across the supply chain 3. Capacity building of health care providers DISTRICT 1. Population mobilization and sensitization 2. Follow up of the Program implementation at health facility level | DISTRICT, MINISANTE/RBC
|  |  |  | NCDs early detection and management is integrated at community level | Percentage of eligible people (Aged 35 and above for women; and 40 years and above for Men) who received at least one NCDs community check up |  |  |  | 40% | 70% | 85% | 85% | MINISANTE/RBC 1. Training of health care providers from health centers and district hospitals on community check up service package DISTRICT 1. Population mobilization and sensitization 2. Follow up of the Program implementation | DISTRICT, MINISANTE/RBC