## Sheet1
GATSIBO DISTRICT IMIHIGO 2019/ 2020
No | Outputs | Indicator | Baseline | Source of Data | Targets/milestones |  |  |  | Annual Target | Activities & Responsible Stakeholders | Achievement | Percentage |  | Challenge
[5 empty] | Q1 | Q2 | Q3 | Q4 |  |  | Achievements Q1 ,Q2 and Q3 | % for Q1, Q2 &Q3 target | % for Annual target
ECONOMIC TRANSFORMATION PILLAR
SECTOR: AGRICULTURE
Outcome 1: Agricultural production for priority crops increased
1 | Agricultural productivity increased through land use Management and input use | Ha of land consolidated on priority crops | Maize: 13,913 ha Rice : 2,582 ha Beans: 13,950 ha Soybeans: 764 ha Cassava: 760 ha | Administrative data | Maize: 1500 ha Rice : 1,130 ha Beans: 537 ha Soybeans: 50 ha Cassava: 100 ha | Maize: 12930 ha Rice : 0ha Beans: 800 ha Soybeans: 50ha Cassava: 392 ha | Maize: 337 ha Rice : 1,291 ha Beans: 13,430 ha Soybeans: 400 ha Cassava: 212 ha | _ | Maize: 14,767 ha Rice : 2421 ha Beans: 14,767 ha Soybeans: 500 ha Cassava: 704 ha | DISTRICT 1. Seasons preparation meetings, 2. Sites Identification, 3. Monitoring the distribution of and utilization of inputs 4.Monitoring harvesting process 5. Train 35,580 farmers through Twigire Muhinzi MINAGRI/RAB 1. Tendering of improved seeds (with service providers). 2. Transfer of earmarked for improved seeds on time 3. Supervision of seeds distribution | Maize: 15,143/14767 ha=102.5% Rice : 2,420/2,421 ha=100% Beans: 16,301/14,767 ha=110.4% Soybeans: 492/500ha=98.3% Cassava: 692/704ha=98% | 101.9 | 101.9
2 |  | Kg of improved seeds timely delivered and used by farmers | 257,661 Kg of maize, and 49,077 Kg of soya beans | Administrative data | Delivery: Improved seeds available at agro dealers shops and ready for distribution to farmers for Season A(Q2) Maize: 225,000 Kg Soybeans: 10,000 Kg by 30th August 2019 | Improved seed Use Season A (Q2) Maize: 225,000 Kg Soybean: 10,000Kg | Delivery: Improved seeds available at agro dealers shops and ready for distribution to farmers for Season B (Q4) Maize: 43,022 Kg Soybean: 30,820 Kg by 29th February 2020 | Improved seed Use Season B (Q4) Maize: 43,022Kg Soybean: 30,820 Kg | Maize: 268,022 Kg Soybean: 40,820 Kg timely delivered and used by farmers | DISTRICT 1. Ensure timely supply of improved seeds to all farmers 2. Farmer mobilization on season preparation (land use consolidation, and inputs use) 3. Organize and monitor the agricultural inputs distribution system involving agro-dealers and districts agronomist. MINAGRI/RAB 1. Follow up seed companies and local seed multipliers to avail seeds on time | Season A: Maize seeds: 246,276/268,022 Kg=92% Soybean seeds: 20,220/40,820Kg50% supplied to frmaers | 71 | 71 | Insufficient capacity of agrodealers
3 |  | Kg of fertilizers timely delivered and used by farmers | 524,356kg of DAP, 423,799 kg and 525,082kg of NPK | Administrative data | Delivery: Fertilizers available in agro dealers shops and ready for distribution to farmers for Season A : UREA: 343,393 Kg DAP: 686,786Kg NPK: 151,445Kg by 30th August 2019 | Fertilizers Use Season A (Q2) : UREA: 343,393 Kg DAP: 686,786Kg NPK: 151,445Kg | Delivery: Fertilizers available in agro dealers shops and ready for distribution to farmers for Season B : UREA: 20,515 kg DAP: 41,036 Kg NPK:68,840 Kg by 29th February 2020 and Lime 928,000kg and compost 1,987,000Kg will be supplied by contractor | Fertilizers Use Season B (Q4) : UREA: 20,515 kg DAP: 41,036 Kg NPK: 68,840 Kg | (DAP: 727,822 Kg; Urea:363,808 Kg; NPK: 220,285 Kg), Lime 928,000kg and compost 1,987,000Kg | DISTRICT 1. Ensure timely supply of fertilizers to all farmers 2. Farmer mobilization on season preparation (land use consolidation, and inputs use) 3. Organize and monitor the agricultural inputs distribution system involving agro-dealers and districts agronomists. MINAGRI (RAB) 1. Follow up on timely fertilizer distribution 2. Provide technical support on fertilizers use for food crops and cash crops 3. Regular monitoring of fertilizers use by farmers | Season A: UREA 536,484/363,808Kg=147% DAP: 626,720/727,822Kg=86% NPK: 556,471/220,285Kg=253% supplied to farmer Season B: Lime 928.000/928,000kg =100% and compost 1,987,000/1,987,000Kg =75% | 131 | 131
4 | Use of organic fertilizers increased | % of Households with compost pit | N/A | Administrative data |  |  | 50% | 100% | 100% Households with compost pit | DISTRICT 1.Mobilise citizens to construct a compost pit at each Household 2. Provide technical expertise to householders 3. Monitor construction of compost pits by Households | 53,091/100,454 HHs have compost pits | 106 | 52.9
5 |  | Quantity produced per priority crop (per Ha) | •Maize: 4.6T/ha •Rice:5.5T/ ha •Beans:1.5T/ha •Soybeans:1.4T/Ha •Banana:23.1 T/ha | Administrative data | Mobilization of people to use fertilizers (Chemical and Organic) in consolidated areas | Monitoring of distribution and application of inputs | •Maize: 4.8T/ha •Rice: 5.7T/ ha •Beans:1.6T/ha •Soybeans:1.5T/Ha | •Banana: 24 t/ha | •Maize: 4.8T/ha •Rice: 5.7T/ ha •Beans:1.6T/ha •Soybeans:1.5T/Ha •Banana:24T/ha | DISTRICT 1.Mobilisation of people to use fertilizers (Chemical and Organic) and improved seeds 2.Avail stock of fertilizers and seeds in sectors 3.Identification of sites for measuring productivity 4.Follow up of distribution of inputs 5.Recording production of banana produced per quarter MINAGRI/RAB 1. Tendering of fertilizers and improved seeds (with service providers). 2. Transfer of earmarked funds for fertilizers and improved seeds on time 3. Supervision of inputs distribution | •Maize: 4.8/4.8T/ha 100% •Beans:1.3/1.6T/ha=81.3% •Rice: 5.5/5.7T/ ha=95.6% •Soybeans: 1.6/1.5T/Ha=106.7% •Banana:24/24T/ha =100% | 98 | 98
6 | Area of progressive terraces constructed (Ha) | Ha of progressive terraces constructed | 1628 ha | Administrative data | Identification of sites | 42 | 49 | 21 | 112 ha of progressive terraces constructed | DISTRICT 1.Identification of sites 2.Monitoring of Community works 3. Digging trenches in community works | 53.1/91ha of progressive terraces constructed | 58.3 | 47.4 | COVID-19 stoped implementation of Projects
7 | Effective and efficient irrigation developed under an Integrated Water Resource Management (IWRM) framework | Number of Ha under Small Scale Irrigation (SSIT) developed | 209 ha | Administrative data | 143ha irrigated | _ | 10ha | 77ha | 230 ha irrigated on small scale | DISTRICT 1.Mobilization of farmers on the use of irrigation and buying the motor pumps for irrigation. 2.Monitoring the use of moto pumps bought and the areas irrigated MINAGRI/RAB 1. Tendering of motor pumps (with service providers) 2. Transfer of earmarked funds for motor pumps 3. Supervision of motor pumps distribution | 211/153ha irrigated | 208 | 91.6
Outcome 2: Increased Agricultural post-harvest Infrastructures
8 | Drying facilities constructed | Number of Drying facilities constructed | 39 | Administrative data | Tendering process | 10% of Construction 98 drying facilities | 50% of Construction 98 drying facilities | 100% of Construction 98 drying facilities | 98 drying facilities fully constructed | DISTRICT 1. site identification 2.Tendering process 3.Monitoring of construction works | Construction of 98 drying shelters are at 32% (▶8 drying facilities are on finishing level; ▶21 drying facilities are on roofing level ; ▶30 drying facilities are on Elevation level; ▶39 drying facilities are on terracing level). | 64% | 32% | COVID-19 stoped implementation of Projects
9 | Storage facilities constructed | Number of Storage facilities constructed | 17 | Administrative data | Tendering process | 10% of Construction works of storage facilities | 40% of Construction works of storage facilities | 100% of Construction works of storage facilities | 2 storage facilities fully constructed | DISTRICT 1. site identification 2.Tendering process 3.Monitoring of construction works RSSP: 1.Supervision of construction works 2. Pay invoices | 2 storage facilities fully constructed 100% | 100 | 100
Outcome 3: Increased animal productivity
10 | Cows genetics Improved | Number of cows inseminated | 2,805 cows inseminated | Administrative data | 530 | 630 | 630 | 730 | 2,520 cows inseminated | DISTRICT 1.Mobilization of farmers to use AI 2.To purchase semen from RAB 3.Artificial insemination of cows and heifers on natural and artificial heat. RAB 1. To avail the semen, others materials and products related to artificial insemination and hormones on agreed time | 2,026/2,520 cows inseminated | 113 | 80.4%
11 |  | Number of AI born calves registered | 939 new born calves registered | Administrative data | 233 | 239 | 233 | 240 | 945 new born calves registered | DISTRICT: 1.Regestration of new born calves RAB 1. To avail the materials and products related to calves registration | 790/706 new born calves registered | 112 | 80.3
12 | Livestock vaccinated against diseases | Number of livestock vaccinated against diseases | Cows vaccinated for BQ:10,766 LSD 18,214 FMD: 25,720 Brucellosis: 500, | Administrative data | _ | Mobilization of farmers | BQ: 12,766 LSD 25,000 FMD: 35,000, RVF: 13,500 Brucellosis: 500 Rabies: 154 | _ | BQ: 12,766 LSD 25,000 FMD: 35,000, RVF: 13,500 Brucellosis: 500 Rabies: 154 | DISTRICT 1. Mobilization of farmers on disease vaccination 2.To purchase vaccines from RAB 3. Vaccination activity. RAB 1. To avail vaccines, others materials and products related to vaccination on agreed time | BQ: 4,135/12,766=32% LSD: 21,869/25,000= 88% FMD: 25,668/35,000=73.3%, RVF: 13,500/13,500= 100% Brucellosis: 16/500= 3.2% Rabies: 26/154=17% | 75 | 75
13 | Animal production increased | Volume ( Litters) of milk produced | 14,597,704 liters of milk are produced | Administrative data | 2,500,000 litters of milk | 4,100,000litters of milk | 4,500,000 litters of milk | 3,752,219 litters of milk | 14,852,219 liters of milk produced | DISTRICT 1.Mobilize farmers on better farming method for improved production | 13,324,736/11,100,000 liters of milk produced | 120 | 90
Outcome 4: Increased cash crops production
14 | Coffee production Increased | Volume of Fully Washed Coffee produced (MT) | 2,170 tons fully washed coffee | Administrative data | _ | Mobilization and utilization of fertilizers and pesticides | Mobilization of farmers to production to coffee washing station | 1,500 Tons of fully washed Coffee produced | 1,500 Tons of fully washed coffee produced | DISTRICT 1.Mobilization and utilization of fertilizers and pesticides 2.Mobilization of farmers to supply their production to the coffee washing stations NAEB 1.To increase the capacity of existing coffee washing stations and new ones where needed | Mobilization and utilization of fertilizers and pesticides done and 134 tones for fully washed coffee | 100 | 9
15 | Vegetable production increased | Area of vegetables planted (Ha) | 148 ha in command area | Administrative data | 130 Ha | _ | 15 Ha | 55 ha | 200 ha of vegetables planted | DISTRICT 1. Mobilization of farmers to cultivate vegetables RAB 1. To avail improved seeds to the farmers | 198/145 ha of vegetables planted | 136 | 99
SECTOR: Private Sector Development & Youth Employment (To include targets for Exports, Tourism and jobs to be created)
Outcome 5: Increased productive Jobs through entrepreneurship, business development and savings
16 | Productive jobs increased | Number of productive jobs created | 8,164 people employed | Administrative data | 600 | 2800 | 2600 | 1166 | 7,166 new productive jobs created | DISTRICT: 1. Identification of projects which will provide jobs in Gatsibo District. 2. Mobilization of people to create new jobs 3.Follow up on people employed & visit those who have created new jobs | 5,683/6,000 new productive jobs created | 95 | 79
17 | TVET graduates supported to acquire start up toolkits | Number of TVET graduates who received start up toolkit | - | District Administrative data source | Mobilization of youth to acquire toolkits | Mobilization of youth to acquire toolkits | 15 | 25 | 40 TVET graduates supported toolkits | DISTRICT 1. Mobilization of TVET graduates to acquire startup tool kits 2. Identification of TVET graduates in need of toolkits PARTNERS 1. Avail toolkits to TVET graduates | 30/40 TVET graduates supported | 100 | 75
18 | Bankable start up MSMEs projects coached and supported to access finance by Business Development Advisors | Number of start-up MSMEs for youth and Women coached and supported to access finance | - | District Administrative data source | 100 | 150 | 150 | 50 | 450 MSMES coached and supported to access finance | DISTRICT 1. Mobilization of youth and women from Sectors about NEP intervention 2. Link beneficiaries with financial institutions 3. To coordinate the elaboration of projects in collaboration with BDAs 4. Carry out Monitoring | 358/400 MSMES coached supported to access finance | 89.5 | 79
SECTOR: FINANCIAL SECTOR DEVELOPMENT
Outcome 6: Enhanced EJO HEZA Long-term Savings Scheme
19 | Increased Subscription and Savings into Ejo Heza long term saving scheme | Number of Subscribers in Ejo Heza | 2,500 Subscribers in Ejo Heza | Administrative data | 2,000 Subscribers in Ejo Heza | 3,000 Subscribers in Ejo Heza | 1,500 Subscribers in Ejo Heza | 417 Subscribers in Ejo Heza | 6,917 Subscribers in Ejo Heza | DISTRICT 1. Mobilization of people | 13,683/6500 Subscribers in Ejo Heza | 198 | 198
20 |  | Amount saved in Ejo Heza Scheme (Frw) | 2,482,685frw Saved | Administrative data | 30,000,000 Rwf | 50,000,000 Rwf | 100,058,823 Rwf | 127,000,000 Rwf | 307,058,823 Rwf saved in Ejo Heza Saving Scheme | DISTRICT 1. Mobilization of people | 98,593,496 /180,058,823 Rwf saved | 54.7563 | 32
SECTOR: ENERGY (Connections to Productive Use Areas)
Outcome 7: Electricity access to Productive uses increased at 54.2% to 56.9%
21 | Productive use areas connected to electricity (on grid) | Number of Productive use areas connected to electricity | 144/251 productive use connected to electricity line | Administrative data | Revision of study | 10% for construction works of Electrification | 30% for construction works of Electrification | 70% for construction works of Electrification and 30 productive uses electrified | 30 productive uses electrified | DISTRICT 1.Supervision of construction works. REG 1.Expropriation of works 2.Tendering of works 3.Supervision of construction works. 4.Execution of construction works of electrification in different sectors (Gasange, Murambi,....) | construction works of Electrification is 32.9% | 109 | 45.7143 | COVID-19 stoped implementation of Projects
SECTOR: TRANSPORT
Outcome 8: Improved riding quality and level of service for road network
22 | Muhura - Gasange - Njume – Kiramuruzi (30km) and Kiramuruzi-Bwunyu-Nyamarebe (5km) upgraded | Percentage of works of road and Feeder roads upgraded | - | Administrative data | Study of construction works | Study of construction works | 10% of works for upgrading Muhura - Gasange - Njume – Kiramuruzi (30km) and Kiramuruzi-Bwunyu-Nyamarebe (5km) feeder roads | 30% of works for upgrading Muhura - Gasange - Njume – Kiramuruzi (30km) and Kiramuruzi-Bwunyu-Nyamarebe (5km) feeder roads | Muhura - Gasange - Njume – Kiramuruzi (30km) and Kiramuruzi-Bwunyu-Nyamarebe (5km) feeder roads upgraded at 30% | DISTRICT 1.Tendering of works 2.Supervision of construction works. 3.Aprove the payments of works RTDA 1.Expropriation of works 2.Tendering of works 3.Supervision of construction works. 4.Pay works | Design and resettlement action plan (RAP) submitted to world bank for approval | 0 | 0 | World bank and RTDA delayed in approving resettlement action plan
23 | Feeder roads developed | Percentage of works of Feeder roads rehabilitation | - | Administrative data | Tendering of rehabilitation works | Tendering of rehabilitation works | 10% for Rehabilitation of Munini-Kabeza road | 50% for Rehabilitation of Munini-Kabeza road | Munini-Kabeza road rehabilitated at 50% | DISTRICT 1.Expropriation of works 2.Tendering of works 3.Supervision of construction works | Construction of feeder kabeza-Munini feeder road is 18% | 180 | 36 | COVID-19 stoped implementation of Projects
24 |  |  | - | Administrative data | Study of construction works | Study of construction works | 10% of rehabilitation works for Mugera-Nyabicwamba-Gatungo-Nyagihanga-Karungeri (20km) and Rwangingo-Kigasha –Ngarama (9km) | 30% of rehabilitation works for Mugera-Nyabicwamba-Gatungo-Nyagihanga-Karungeri (20km) and Rwangingo-Kigasha –Ngarama (9km) | Mugera-Nyabicwamba-Gatungo-Nyagihanga-Karungeri (20km) and Rwangingo-Kigasha –Ngarama (9km) rehabilitated at 30% | DISTRICT 1.Tendering of works 2.Supervision of construction works. 3.Aprove the payments of works RTDA 1.Expropriation of works 2.Tendering of works 3.Supervision of construction works. 4.Pay works | Design and resettlement action plan (RAP) submitted to world bank for approval | 0 | 0% | World bank and RTDA delayed in approving resettlement action plan
25 |  |  | - | Administrative data | Study of construction works | Study of construction works | 10% of rehabilitation works for Kabarore-Kabeza-Marimba-Nyabicwamba (19 km) | 30% of rehabilitation works for Kabarore-Kabeza-Marimba-Nyabicwamba (19 km) | Kabarore-Kabeza-Marimba-Nyabicwamba (19 km) rehabilitated at 30% | DISTRICT 1.Tendering of works 2.Supervision of construction works. 3.Aprove the payments of works RTDA 1.Expropriation of works 2.Tendering of works 3.Supervision of construction works. 4. Pay works | Design and resettlement action plan (RAP) submitted to world bank for approval | 0 | 0 | World bank and RTDA delayed in approving resettlement action plan
26 |  |  | 194 km rehabilitated | Administrative data | Study and Selection of Community committees to monitor public works | 10% for rehabilitation of 100 km of feeder roads through PW in all Sectors | 50% for rehabilitation of 100 km of feeder roads through PW in all Sectors | 100% for rehabilitation of 100 km of feeder roads through PW in all Sectors | 100 km of feeder roads through PW in all Sectors rehabilitated at 100% | DISTRICT 1. Tendering process 2.Supervision of rehabilitation works. 3.Payment of works | rehabilitation of 100 km of feeder roads through PW is at 73.1% | 146 | 73
SECTOR: ENVIRONMENT AND NATURAL RESOURCES
Outcome 9: Forest coverage maintained and increased
27 | Increased area under agro-forestry | Number of ha of land under agro forestry | 29,946 ha of agro-forest trees Planted | Administrative data | Nursery beds establishment | 2,547 Ha of agroforestry to be planted | _ | Monitoring of planted trees | 2,547 Ha of agroforestry planted | DISTRICT 1.Identification of sites for nursery bed preparation 2.Monitoring of Nursery bed preparation. 3.Monitoring of tree plantation PARTNERS 1.Identification of sites for nursery bed preparation 2.Monitoring of Nursery bed preparation. | 3,436/2547 Ha of agroforestry planted | 135 | 135
28 | Forest cover increased and maintained | Number of ha of new woodlots established | 8,257 ha of forests | Administrative data | Nursery beds establishment | 104ha Woodlot to be planted | Weeding on planted area | Monitoring of planted forest | 104ha Woodlot /forest planted | DISTRICT 1.Identification of sites for nursery bed preparation 2.Monitoring of Nursery bed preparation. 3.Monitoring of tree plantation | 104ha Woodlot /forest planted | 100 | 100
29 | Fruit trees increased | Number of fruit trees planted | 152,175 fruit trees | District Administrative data | Seedlings preparation | 94,000 of fruits distributed to local farmers and planted | Follow-up of planted trees | Follow-up of planted trees | 94,000 fruits trees planted | DISTRICT 1. Preparation of nurseries; 2. Tree distribution and plantation; 3. Monitoring and Evaluation PARTNERS: 1. Availability of Funds; 2. Monitoring and Evaluation | 124,146/94,000 fruits trees planted | 132 | 132
30 | Dumpsite (borrow pit)in Kabarore sector constructed | Percentage of Construction works | Study available | Administrative data | Tendering process completed | 10% | 20% | 50% | dump site (borrow pit) in Kabarore sector constructed at 50% | DISTRICT 1.Expropriation of people's property 2.Tendering works 3.Monitor the construction works | Construction of Dumping site is at 52% | 260.35 | 104.12
SOCIAL TRANSFORMATION PILLAR
SECTOR: HEALTH
Outcome 10: Maternal, Child and Infant mortality reduced
31 | Pregnant women receiving ante natal care (4 standard visits) increased | Percentage of women attending 4 standard ante - natal care visits | 47% | HMIS , June 2019 | 47,5% | 48% | 50% | >60% | >60% of women attending 4 Standard Ante natal care visits | DISTRICT: 1.Conduct Community Mobilization Events, 2.Conduct Supervision or mentorship to monitor quality of ante-natal care services in health facility | 4,334/12,199(35.5%) women attended 4 standard ante - natal care visits | 71.2 | 59.3333
32 | Family Planning (FP) services provided | FP modern method utilization rate (%) | 63.6% | RHMIS ,June 2019 | 63.8% | 64% | 64.5% | 65% | 65% Family planning modern method users | DISTRICT: 1:Conduct community mobilization Events, 2:Conduct supervision or mentorship to monitor quality of Family Planning services and other health related services | 81,677/131,011(62.3%) families use different methods of Family Planning. | 97.3 | 95
33 | Quality delivery and accessibility at health facility and community level increased | Percentage of births attended by skilled health professionals | 93.8% | HMIS, June 2019 | 94% | 94,5% | 94,8% | 95% | 95% Births attended by skilled health professionals | DISTRICT: 1:Conduct Community Mobilization Events, 2:Conduct supervision or mentorship to strengthen the quality of maternal, neonatal and child health care | 10,752/11,227(95.7%) Births attended by skilled health professionals | 100.9494 | 100.7368
Outcome 11: Reduced burden of communicable and non-communicable diseases among Rwandan population
34 | Access to Viral Hepatitis prevention and treatment services increased | Percentage of Adults aged 15 Years and above screened for Hepatitis C | 40% | District report |  |  | 70% | 80% | 80% | MINISANTE/RBC 1. Procurement and distribution consumables, reagents and required equipment for screening; 2. Strengthen the cold chain across the supply chain 3. Capacity building of health care providers DISTRICT 1. Population mobilization and sensitization 2. Follow up of the Program implementation at health facility level | 93,297/133,332(69.9%) people screened | 99.8 | 87.4
35 | NCDs early detection and management is integrated at community level | Percentage of eligible people (Aged 35 and above for women; and 40 years and above for Men) who received at least one NCDs community check up |  | District report |  |  | 70% | 85% | 85% | MINISANTE/RBC 1. Training of health care providers from health centers and district hospitals on community check up service package DISTRICT 1. Population mobilization and sensitization 2. Follow up of the Program implementation | 14254/106114(13.4)people Screened | 19.1429 | 15.7647 | Activities suspended due to COVID-19
Outcome 12: Access to health services increased
36 | Coverage of Community Based Health Insurance Scheme (CBHI) increased | Percentage of people covered under Community Based Health Insurance Scheme (CBHI) | - | Administrative data | 60% | 80% | 100% | 100% | 100% of people covered by health insurance | DISTRICT: 1.Conduct community Mobilization events, 2.Conduct field visits to monitor progress of CBHI Subscription. | 403,348/475,755(84.7%) people covered by health insurance | 84.7 | 84.7%
37 | Gitoki Maternity constructed | Percentage of construction works | - | Administrative data | _ | Tender process and Leveling for construction of Maternity | 50% Construction of Maternity for Gitoki health center | 100% Construction of Maternity for Gitoki health center completed | Maternity fully constructed at Gitoki health center | DISTRICT: 1.Supervision of construction works. 2. Provide funds WORLD VISION: 1.Tendering of health center equipment's 2. Provide funds | Construction works are at roofing level ( 42%) | 84 | 42 | Activities suspended due to COVID-19
38 | Ngarama health center equipped | Percentage of equipment's supplied | Insufficient equipment's/ old equipment's | Administrative data | Tendering of equipment's | Tendering of equipment's | 50% | 100% | All equipment's planned to be provided to Ngarama health center are supplied | DISTRICT: 1.Tendering of health center equipment's 2.Supply of equipment's MINEMA/WORLD BANK 1.Provide funds for equipment's | Contract was signed | 0 | 0 | Activities suspended due to COVID-19
39 | Health facilities are equipped with ambulance vehicles | Number of ambulance purchased |  | District reports |  |  | Tender process | Purchase of at least 1 ambulance | At least 1 ambulance car purchased | DISTRICT 1. Tender process 2. Purchase of ambulance | Tender process is at evaluation stage | 80% | 0 | Activities suspended due to COVID-19
Outcome 13: Reduced malnutrition
40 | Optimal growth for all children under 5 monitored | Percentage of < 5 years children screened for acute malnutrition |  | HMIS |  |  |  | 95% | 95% | MoH/CHWs 1. Avail equipments 2. Screening of children District 1. Mobilize parents 2.follow up with health centers to ensure growth monitoring is done | 56,756/64,128(88.5%)Screened | 93.1579 | 93.1579
41 |  | Percentage of < 2 years children screened using length mat for stunting visualisation |  | NECDP reports |  |  |  | 50% | 95% |  | 1,466/20,023(7.32%) Secreened | 14.64 | 7.7053 | Activities suspended due to COVID-19
42 | Rate of stunting among children <2 years reduced | Percentage of stunting among children <2 years | 33% | MCCH Report |  |  |  | 30.2% | 30.2% | MoH/CHWs 1. Avail equipment's 2. Screening of children 3. Follow up for children at risk District 1. Mobilize parents 2.follow up with health centers to ensure growth monitoring is done | Stunting rate is at 0.66% (132/19.758) | 4575.7576 | 4575.7576
43 | Acute Malnutrition for under five year children reduced | Proportion of Children who were in Red and Yellow colors (indicating risk levels of Child acute malnutrition as per MUAC screening) graduate to Green color | 93,3% | District Administrative data source | 95% | 96% | 96.5% | 99% | 99% of Children who were in Red and Yellow colors (indicating risk levels of Child acute malnutrition as per MUAC screening) graduate to Green color | DISTRICT: 1. Monitoring of Community Screening of malnutrition for under 5 year children, 2. Monitoring of intensive care for malnourished children in health facility 3. Construct kitchen gardens for 316 HHs in Ubudehe Cat 1 | 485/597(81%)of Children who were in Red and Yellow colors (indicating risk levels of Child acute malnutrition as per MUAC screening) graduated to Green color | 83.9378 | 81.8182
44 | Home-based ECD operationalised at Village level | Number of villages with functional ECDs (Home based or Community Based or Center Based) serving at least 50% of eligible children (Aged under 6 Years) |  | District report |  | Mobilization of households | 602 home based ECDs operational | 602 home based ECDs operational | 602 home based ECDs operational | District 1.Distribution of cooking demonstration material in Home based ECD 2. Operationalize Village kitchen (Igikoni cy'Umudugudu) and attended by eligible parents (whose Children are Under 5 age) least twice per month 3. Organise quarterly Peer learning on ECD best practice within the Village 4.Quarterly Supervision on ECD 5. Monitoring and reporting on HBECDs | 518/602(86%) Villages have ECDs | 86 | 86% | Activities suspended due to COVID-19
45 | ECDs Constructed | Percentage of construction works | 45 ECDs | Administrative data | Tendering of works | 10% of Construction of 8 ECDs | 80% of Construction of 8 ECDs | 100% of Construction of 8 ECDs | 8 ECDs fully constructed | DISTRICT: 1.Provide land for ECD construction 2.Tendering of works 3. Monitoring of construction works NECPD 1.Supervision of construction works 2.Provide funds | Construction of 8/8 ECDs is on going, all works at completion stage. | 112.5 | 90
46 | Model inclusive ECD constructed | Percentage of construction works | - | Administrative data | _ | Tendering and 10% of Construction of ECD | 80% of Construction of ECD | 100% of Construction of ECD | Construction of Model inclusive ECDs including Children with Disability to attend the center | DISTRICT 1.Supervision of construction works Hope and Home for Children 1.Tendering of works 2.Monitoring of construction works | MOU Signed, Study of construction works done, Construction permit provided, Tender process in progress | 0 | 0 | Construction works not yet started,
47 | Fruit trees planted to complement initiatives to fight malnutrition | % of households having planted at least 3 new fruit trees |  | Administrative data |  |  | 50% | 100% | 100% | 1. Mobilise households to plant at least 3 fruit trees per each household 2. Facilitate households to access fruits trees | 76,581/105,845 HHs have atleast 3 fruit trees | 144 | 72
SECTOR: EDUCATION
Outcome 14: Increased education infrastructure
48 | New classrooms and toilets constructed | Number of class rooms, and toilets constructed | 2,265 class rooms, 3,137 Toilets for 12YBE constructed | Administrative data | Tendering of works | Tendering of world class rooms and 42 classrooms and 48 Latrines Leveling and roofing of construction works completed | 42 classrooms and 48 Latrines fully constructed 167 classrooms and 198 cubic latrines constructed at 70% | 167 classrooms and 198 cubic latrines fully constructed | 209 New classrooms and new 246 Latrines fully constructed | DISTRICT: 1.Tendering process 2.Identification of Sites; 3.Monitoring construction works; 4. Monitoring distribution of construction materials; 5. Monitoring of construction activities. MINEDUC: 1.Provide construction materials on 42 classrooms and 48 latrines 2.Provision of construction materials MINEMA/WORLD BANK: 1.Provide funds for 55 classrooms and 60 latrines 2.Supervision of construction works | Construction works of 42 classrooms is at 100% ,48 toilets is at 100%, Others are in Tender process | 20 | 20 | COVID-19 stoped implementation of Projects
49 | Two primary schools constructed | Percentage of construction works | - | Administrative data | Tendering of works of new primary school and Completion of Kabusunzu primary school | 10% for Construction of New primary school in Kiziguro Sector primary school | 50% for Construction of New primary school in Kiziguro Sector primary school | 100% for Construction of New primary school in Kiziguro Sector primary school | Construction of New primary school in Kiziguro Sector and Completion of Kabusunzu primary school | DISTRICT: 1.Tendering process 2.Identification of Sites; 3.Monitoring construction works; 5. Monitoring of construction activities. PLAN RWANDA: 1.Supervision of construction works 2.Provide funds | Construction works of new primary school in Kiziguro Sector at finishing level at 95% and construction works for completion of of Kabusunzu primary school completed | 164.64 | 97.5%
50 | Gatsibo TVET extended | Percentage of extension works | - | Administrative data | 90% TVET Hostel and Playing ground constructed and Tendering studies | Tendering of works | 10% of Construction of classes (G+1) and Workshop at Gatsibo TVET | 50% of Construction of classes (G+1) and Workshop at Gatsibo TVET | Completion of Gatsibo TVET Hostel and Playing ground and 50% of Construction of classes (G+1) and Workshop at Gatsibo TVET | DISTRICT: 1.Tendering of consultants and contractor for construction 2. Follow up of construction works | Handover of Gatsibo TVET Hostel and Playing Groung done. Contract signed and advance paid for construction of classes(G+1) and workshop. | 50 | 50 | Rain saison delaying construction works.
51 | Chairs Supplied to schools | Number of chairs supplied | Insufficient chairs | Administrative data | Tendering of chairs | 1500 | 7000 | _ | Supply of 8,500 chairs for students in old schools | DISTRICT: 1.Tendering of chairs 2.Supply of chairs PLAN Rwanda and MINEMA: 1.Provide funds for chairs | 2192 Desks supplied Under District and MINEDUC Funds. Purchase order for supply of 1,521 Desks done under PLAN RWANDA, Tender process (stage of invitation to bid) for supply of 7000 Desks under MINEMA | 31.3 | 25.79 | COVID-19 stoped implementation of Projects
Outcome 15: Increased attendance of students in primary and secondary school
52 | Attendance in primary, TVETs and 12YBE school increased | Net attendance rate in Primary , TVETs and 12YBE schools | District status as of end June 2019 | Administrative data | 99% | 99% | 99% | 99% | 99% in Primary, secondary and TVET( level 1 to 5) | DISTRICT: 1. Inspect schools and implement the recommendations from inspections. 2. Mobilization of parents on school attendance 3. Mobilization of head teacher and Executive secretaries of cells on net attendance 4. School inspection 5. Provide lunch to students through School feeding program for Secondary schools | Net attendance are at 97.9% in Primary, 96.4 % secondary and TVET | 98.1818 | 98.1818
53 | Drop out rates in schools reduced | Percentage of students drop outs | Primary 8.6% Lower Sec. 1.6% Upper Sec 9.7% | SDMS | Data cleaning and verification of data completeness | Data cleaning and verification of data completeness | Update the information for 2020 school year | Primary: 8.0% Lower Sec. 1.0% Upper Sec 9.1% | Primary: 8.0% Lower Sec. 1.0% Upper Sec 9.1% | MINEDUC 1. Monitor the school attendance rate for students and teachers, highlighting the improvement made between quarters District/Schools 1. Ensure the use of class register in order to effectively assist students with multiple absenteeism. | Primary: 292/107,621=0.03% (1,818% achieved) Lower Sec. 104/20,366=0.05% (101% achived) Upper Sec 16/8807=0.02% ( 3,370% achieved) | 100 | 1763
54 | All schools with fully equipped Girl's Room available | Percentage of secondary schools with girl's room |  | Administrative data | Mobilization of Schools to avail girl's room | 30% | 70% | 100% | 100% | DISTRICT To monitor schools and ensure the Girls rooms are fully equipped with required materials MINEDUC 1. To prepare and issue to districts a checklist of requirements that should be available in the Girls Room | 35/69 schools have well equiped girl's room | 68.33 | 68.33
55 | School Inspection improved | Number of Schools inspected | - | Administrative data | 15 schools inspected | 15 schools inspected | 30 schools inspected | 30 schools inspected | 90 Schools inspected | 1.Elaboration of school inspection calendar and concept note, 2.School inspection 3.Submission of reports | 79 schools inspected | 131.6667 | 87.7778
56 |  | Percentage of payments (allowances to Sector based School inspectors) made on time | 100% | MINEDUC Inspection reports | 100% | 100% | 100% | 100% | 100% of allowances to sector based school inspectors paid on timely basis | District 1. Timely disburse to Administrative Sectors the required allowances for Sector based School inspectors for each academic term ((within 3 weeks starting the Academic term) 2. Timely payment of allowances to sector Based school inspectors (ahead of undertaking their missions) | 100% of allowances to sector based school inspectors for the first term paid on time. | 100 | 75
Outcome 16: Increased access to adult literacy
57 | Adult literacy and numeracy increased | Number of people trained in adult literacy centers | 63,747 Adult people trained | Administrative data | Identification of trainees | 2975 | 2975 | 2975 | 2,975 Adult people trained and awarded certificates | DISTRICT: 1.Identification of trainers and trainees 2.Monitoring of teaching activities. 3. Setting and marking final exams | Training of 3341 people is on going | 100 | 70
Outcome 17: Enhanced Teacher's welfare through timely payment of salaries and benefits
58 | Teachers' salaries paid on time | Percentage of payments for Teachers’ salaries made on time (Submission of payment requests not later than 15th of every Month) | 60% | OPs | - | 100% | 100% | 100% | 100% of Payments of Teachers' salaries made on time | District 1. Prepare payroll lists 2. Submission of Payment request to MINECOFIN not later than 15th of every Month MINEDUC: 1. Approval of Teachers placement 2. Verification and approval of payment lists not later than 17th of every month 2. Monitoring and follow up on timeliness of payment of teachers' salaries MINECOFIN 1. Verify and process teachers' salaries not later than 20th of every month | 100% of Payments of Teachers' salaries made on time | 100 | 75
59 | Capitation Grant provided to Schools on time and managed as stipulated in the guidelines | Percentage of payments for Capitation grant) made on time (Submission of payment requests within 3 weeks of the first month of the FY quarter) | N/A | OPs | - | 100% | 100% | 100% | 100% of Capitation Grant Payments made on time | DISTRICT 1. Prepare lists of schools benefiting the capitation Grant prepared by through SDMS 2. Verify and approve the lists of schools that benefit from capitation grant and submit to MINECOFIN 3. Prepare payment orders after approval of the lists and submit to MINECOFIN (within 3 weeks of the first month of FY quarter) MINEDUC 1. Verify the requests on time | 100% of Capitation Grant Payments made on time | 100 | 75
60 |  | Percentage of Schools that utilize capitation grants (funds) as stipulated in the guidelines |  | MINEDUC reports | _ | 100% | 100% | 100% | 100% of Schools that properly utilize capitation grant | MINEDUC 1. To prepare and issue to districts guidelines for the use of Capitation Grant 2. To monitor the use of capitation grant DISTRICT To monitor the use of capitation grant in schools | Capitation grant for Q1 and Q2 are well utilized | 100 | 50
Outcome 18: Strengthening national administrative data: Civil Registration and vital statistics and Education administrative Statistics
61 | Education administrative statistics collected and timely registered through School Data Management System (SDMS): Primary Secondary and TVETs | Percentage of required education information recorded into the SDMS system with accuracy: 1. Students information (Number, Attendance, drop outs, Transition rates, Repetitions, Performance) 2. Schools staff ( Pupil: Trained Teacher ratio) 3. Infrastructures (Pupil Classroom ratio (PCR), Pupils Toilets ratio, Access to water, electricity and internet) | Currently 90.5% of information on students are in to SDMS | SDMS | Data cleaning and verification of data completeness | Data cleaning and verification of data completeness | Update the information for 2020 school year | 100% of the required information for Primary, Secondary and TVETs are recorded into SDMS: 1. Students information (Number, Attendance, drop outs, Transition rates, Repetitions, Performance) 2. Schools staff ( Pupil: Trained Teacher ratio) 3. Infrastructures (Pupil Classroom ratio (PCR), Pupils Toilets ratio, Access to water, electricity and internet) | 100% of the required information for Primary, Secondary and TVETs are recorded into SDMS: 1. Students information (Number, Attendance, drop outs, Transition rates, Repetitions, Performance) 2. Schools staff ( Pupil: Trained Teacher ratio) 3. Infrastructures (Pupil Classroom ratio (PCR), Pupils Toilets ratio, Access to water, electricity and internet) | MINEDUC/ DISTRICT 1. Provide technical support to schools /sector and district 2.Capacity building on the use of SDMS 3. Monitoring the use of the SDMS DISTRICT 1. Ensure that all schools are recorded in to the system 2. Measures for re-enrolment of dropped out students and strategy to ensure that they will complete the level. 3. Identification of dropped out students 4. Effectively record students and monitor school attendance rate for students and teachers, | Data cleaning and verification of data completeness is ongoing: 145,750/145,413=100.2% students, 2757/3236=85% staff, 2,713/2,793 =97% classrooms, 11,792/11,620=101.5% computers, 2456/3,576 =68.7% toilets have been entered in system. | 95.75 | 95.75 | data cleaning ongoing
Outcome 19: Improved performance of students in annual assessments and national examinations.
62 | Students performance in National Examinations ( Primary 6, Secondary 3, Secondary 6) improved | Proportion of Students obtaining Higher grades (Divisions) in National Examinations increased (measured from previous Academic year Exams) | Primary 6: Division I: 2%, Division II: 10% Division III: 31% Division IV: 34% Unclassified: 23% | REB Reports |  | National examinations | National examinations results | Primary 6: Division I: 8%, Division II: 17% Division III: 28% Division IV: 29% Unclassified: 18% | Primary 6: Division I: 8%, Division II: 17% Division III: 28% Division IV: 29% Unclassified: 18% | MINEDUC 1. Analysis of national examinations results. 2. Dissemination of national exams analysis report at districts level DISTRICTS 1. Self assessment of national exam performance and establish individual school improvement plan to improve learning outcomes 2. Conduct and keep record of continuous/ formative assessments( end of lesson, end unit and term). 3. Analysis/Self assessment of comprehensive assessment term 1 and term 2 and 3 performance. 4. Establish school improvement plan for improved learning outcomes | Primary 6: Division I: 2.4%/8%=30% Division II: 16.3%/17%=95.9% Division III: 30.4/28%=108.6% Division IV: 27.1/29%=93.4% Unclassified: 18/23.5= 78.3% | 81.24 | 81.24
63 |  |  | Secondary (S3) Division I: 8% Division II:15% Division III:13% Division IV: 43% Unclassified: 20% Senior 6 • Pass with at least 2 principle passes: 57% • Pass without 2 principle passes: 29% • Fail: 14% | REB Reports |  | National examinations | National examinations results | Secondary (S3): Div. I: 14% Div. II: 22% Div. III: 10% Div. IV: 38% Unclassified: 15% Senior 6 • Pass with at least 2 principle passes: 67% • Pass without 2 principle passes: 24% • Fail: 9% | Secondary (S3): Div. I: 14% Div. II: 22% Div. III: 10% Div. IV: 38% Unclassified: 15% Senior 6 • Pass with at least 2 principle passes: 67% • Pass without 2 principle passes: 24% • Fail: 9% |  | Secondary (S3): Div. I: 7.6/14=54.28% Div. II: 17.29/22=78.59% Div. III: 17.6/10%=176% Div. IV: 42.4/38=111.6% Unclassified: 15/14.4=104.2% Senior 6: Waiting for the results • Pass with at least 2 principle passes: 67% • Pass without 2 principle passes: 24% • Fail: 9% | 52.47% | 52.47
64 | TVETs Students performance in National Examinations increased | Proportion of TVETs Students obtaining Higher grades (Divisions) in National Examinations increased (measured from previous Academic year Exams) | TVET L5: • Category I: 4% • Category II: 25% • Category III: 32% • Category IV: 20% • Category V: 14% • Unclassified: 3% | WDA Reports |  | National examinations |  | • Cat. I: 9% • Cat. II: 30% • Cat. III: 36% • Cat. IV: 17% • Cat. V: 8% • Unclassified: 0% | • Cat. I: 9% • Cat. II: 30% • Cat. III: 36% • Cat. IV: 17% • Cat. V: 8% • Unclassified: 0% |  | • Cat. I: 5.01/9%=55.56 • Cat. II: 25.64/30% = 110.32 • Cat. III: 33.09/36% = 76.01 • Cat. IV: 27.36/17% = 158.82 • Cat. V: 4.87/8% = 60.88 • Unclassified:4.01/ 0.01% = 0.25 | 76.97 | 76.9
SECTOR: SOCIAL PROTECTION
Outcome 20: Increased coverage and delivery of core Social protection programs
65 | Direct Support delivered to extremely poor households headed by females & males without labor (unable to work) | Number of HH beneficiaries supported with VUP Direct Support (DS) | 3230 | Administrative data | 2,903 HH beneficiaries supported with VUP/Direct support | 2,903 HH beneficiaries supported with VUP/Direct support | 2,903 HH beneficiaries supported with VUP/Direct support | 2,903 HH beneficiaries supported with VUP/Direct support | 2,903 HH beneficiaries supported with VUP/Direct support | DISTRICT: 1:Monitoring and Identification of beneficiaries in all sectors and opening their accounts 2 -Requests for DS beneficiaries in all VUP Sectors 3.Disbursement of DS to beneficiaries LODA: 1.Provides guidelines 2.Provide access to the system | 3706/2,903 =127.6% HH beneficiaries supported with VUP/Direct support | 127.6266 | 127.6266
66 | Labor intensive cPW and ePW delivered to extremely poor households | Number of HH beneficiaries employed under Classic Public Works (cPWs) and Expanded Public Works (ePWs) (Number of cPWs/ePWs) | 1,434 ePW beneficiaries employed and 4,624 cPw paid. | Administrative data | 2,306 ePW beneficiaries | 2,306 ePW beneficiaries and 8,043 cPW beneficiaries | 2,306 ePW beneficiaries and 8,043 cPW beneficiaries | 2,306 ePW beneficiaries and 8,043 cPW beneficiaries | 2,306 ePW beneficiaries and 8,043 cPW beneficiaries employed | DISTRICT: 1.Study of PW projects 2.Elaborate targeting list of beneficiaries. 3.Contracts signing 4.Monitoring of works | 2066/2,306=89.5% ePW beneficiaries, 4875/8043=60.6% cPW | 75.05 | 75.05 | 11 projects not Implemented because of lack/cutoff of funds from LODA/DFID
67 | Payments to VUP beneficiaries delivered on time | Percentage of timely payments made to VUP beneficiaries (DS, ePWs and cPWs) | 80% | Administrative data | 100% (DS: Within 10 days after the end of the month) ePWs: Within 15 days after the end of working period ) | 100% (DS: Within 10 days after the end of the month) ePWs & cPWs: Within 15 days after the end of working period ) | 100% (DS: Within 10 days after the end of the month) ePWs & cPWs: Within 15 days after the end of working period ) | 100% (DS: Within 10 days after the end of the month) ePWs&cPWs: Within 15 days after the end of working period ) | 100% (DS: Within 10 days after the end of the month) ePWs&cPWs: Within 15 days after the end of working period ) | DISTRICT: 1. Timely submission of OPs to MINECOFIN (DS: by 15th Day of the month) | DS paid at 102/126=80.9%, ePW paid at 56/80=70% ,cPW at 127/142=89.4% | 80.1 | 80.1
68 | Access to VUP-Financial Services loans increased | Number of loans advanced to eligible beneficiaries under VUP/Financial services to support their Income Generating Activities | 0% | LODA MEIS and District Administrative data source | _ | _ | 100 | 236 | 336 | DISTRICT 1. Mobilization of citizens to prepare micro projects to be financed through VUP-FS 2. Follow up provision of loans to all eligible beneficiaries LODA 1.Provide guidelines on time | 2529/336 projects financed through VUP-FS | 752 | 752
69 | Recovery of loans provided through VUP FS increased | Percentage of loans provided through VUP financial service scheme recovered | 65% | Administration Data | 67% | 68% | 69% | 75% | 75% of loans provided through VUP financial service scheme recovered | 1.Mobilize Population; 2. Organize recovery week | 381,912,112 Fw out of 708,055,204 Frw = 53.9%, Old scheme, 429,146,679 out of 491,113,503 frw = 87.% SACCO Scheme, Average: 70.7% of loans provided through VUP financial service scheme recovered | 102 | 102
Outcome 21: Increased access of extremely poor households to complementary livelihood development services for economic empowerment
70 | Multi- sectoral approach's plan implemented | Number of cows distributed to poor families through Girinka | 21,604 cows and heifers distributed | Administration Data | 150 | 350 | 250 | 250 | 1,000 cows distributed in Girinka program | DISTRICT 1.Identification of beneficiaries 2.Girinka Program tendering process 3.Selection and distribution of cows 4. Prevention and treatment RAB and Others partners 1.Distribution of cows | 797/750 cows distributed in Girinka program | 106.3 | 79.7
71 |  | Number of extremely poor Households supported through Social Protection to achieve minimum required livelihoods | - | Administration Data | Identification of beneficiaries | 1617 | 3641 | 2831.5 | 8,090 extremely poor Households supported through Social Protection to achieve minimum required livelihoods | DISTRICT: 1. 726 children aged 6-14 from vulnerable HHs in ubudehe cat1to enroll in schools 2. Support 4,781 vulnerable individuals in ubudehe cat1 to access technical/vocational skills 3. Support 5,00 vulnerable HHs in ubudehe cat1 with off/on grid energy 4. Support 3136 beneficiaries under HIMO program 5. Provide training to 590 eligible vulnerable HHs on good agricultural practices 6. Support HHs in Ubudehe Cat.1 to access to clean water 7. Train 1,257 people from vulnerable Households on financial literacy and small business development 8. Provide loans to people from HHs in category one through VUP/FS to support income generating activities 9. Support 600 people from vulnerable Households with Basic support to start up small business 10. Support 1,403 HHs in ubudehe cat1 with access to agricultural seeds 11. Support 1,403 HHs in ubudehe cat1 with access to agricultural fertilizers 12. Provide 2,000 small livestock distributed to eligible HHs in ubudehe cat1 13. Rehabilitate 280 kitchen constructed/rehabilitated for eligible HHs in ubudehe cat.1 | 1. 893/726 children aged 6-14 from vulnerable HHs in ubudehe cat1 enrolled in schools = 123% 2. 748/ 4,781 vulnerable individuals in ubudehe cat1 Supported to access technical/vocational skills=15% 3. 138 /500 vulnerable HHs in ubudehe cat1 Supported with off/on grid energy =32% 4. 2948/3136 beneficiaries Supported under HIMO program =94% 5. 590/590 eligible vulnerable HHs trained on good agricultural practices=100% 6. Identification 35/1158 HHs Identified in Ubudehe Cat.1 Supported to access to clean water=3% 7. 1891/1,257 people from vulnerable Households Trained on financial literacy and small business development =150.4% 8. 1009/600 people from HHs in category one Provided loans through VUP/FS to support income generating activities=168.2% 9. 622/600 people from vulnerable House Supported with Basic support to start up small business=103.7% 10.1403/1,403 HHs in ubudehe cat1 Supported with access to agricultural seeds=100% 11.1403/1,403 HHs in ubudehe cat1 Supported with access to agricultural fertilizers=100% 12. 499/2,000 small livestock distributed to eligible HHs in ubudehe cat1=25% 13. 124/280 kitchen constructed/rehabilitated for eligible HHs in ubudehe cat.1=44.3% | 81.2% | 81.2%
72 | Genocide survivors provided with adequate shelter | Number of houses for Genocide Survivors constructed | 238 | Administration Data | Tendering process | 26 houses Leveling completed | 26 houses elevation completed | 26 houses fully constructed | 26 houses constructed for genocide survivors | DISTRICT: 1.Tender construction works 2.Monitoring execution activities | Elevation of 26 houses done and all house are on roofing satage | 44.3 | 44.3 | COVID-19 stoped implementation of Projects
73 | People with disability supported | Number of projects initiated by Cooperatives for people with disability supported | 2 Cooperatives for people with disability supported in FY 2018-19 | District Administrative data source | Mobilization of the members of cooperatives to prepare income generating projects to be financed | Selection of the projects to be financed | 4 Cooperatives/Groups for people with disability supported financially | - | 4 Cooperatives/Groups for people with disability supported financially | District 1. Selection of the projects to be financed 2. Transfer of funds to selected cooperatives/groups 3. Follow up implementation of the projects | 4/4 Projects selected and 4 cooperative supported | 100 | 100
GENDER AND FAMILY PROMOTION
Outcome 22: Family cohesion strengthened
74 | Umugoroba w'Ababyeyi promoted | Number of inspections done by districts on umugoroba w'Ababyeyi conducted (Quarterly basis) | 4 Monitoring & Evaluation sessions of Umugoroba w'Ababyeyi conducted | Administrative data | 1M&E session of Umugoroba w'Ababyeyi conducted | 1M&E session of Umugoroba w'Ababyeyi conducted | 1M&E session of Umugoroba w'Ababyeyi conducted | 1M&E session of Umugoroba w'Ababyeyi conducted | 4 Monitoring & Evaluation sessions of Umugoroba w'Ababyeyi conducted | DISTRICT: 1.Monitoring of Umugoroba w'ababyeyi 2.Evaluation of Umugoroba w'ababyeyi | 3M&3E session of Umugoroba w'Ababyeyi conducted | 100 | 75
75 | Former street Children reunified | Percentage of former street children identified reunified with families | - | Administrative data | _ | 30% | 70% | 100% | 100% | DISTRICT: 1.Identification of street children 2.Reunify children with families 3.Monitoring of Reunified children | 48 children identified and 27 were reunified with families, | 80.4286 | 56.3
76 | Former delinquents from rehabilitation centers reintegrated | Percentage of former delinquents from rehabilitation centers reintegrated into community | - | Administrative data | _ | 30% | 70% | 100% | 100% of former delinquents from rehabilitation centers reintegrated into community | DISTRICT: 1.Identification of children 2. reintegrate children with families 3.Monitoring of reintegrated children | 21/28=75% people reintegrated in Community | 107.1429 | 75
SECTOR: ENERGY
Outcome 23: Increased household access to Electricity
77 | Households connected to electricity | Number of new households on-grid connection | 23,342 households have access to on-grid electricity. | Administrative data | Mobilization of community | 700 | 300 | 2000 | 3000 new HHs connected to on grid electricity | DISTRICT: 1.Mobilization of people on use of electricity 2.Monitoring the electrification works REG: 1.Electrification of House to on-grid connection 2.Monitoring the electrification works | 2,252/3,000 new HHs connected to on grid electricity | 159.1538 | 75
78 |  | Number of new households off-grid connections | 17,334 households have access to off-grid electricity | Administrative data | Mobilisation | 1000 | 1000 | 1000 | 3,000 new HHs connected to off-grid electricity | DISTRICT: 1.Mobilization of people on use of electricity 2.Monitoring the electrification on off-grid works REG: 1.Monitoring the electrification on off-grid works NGOs: 1.Electrification of House to off-grid connection | 1,483new HHs connected to off-grid electricity | 74.15 | 49
SECTOR: WATER AND SANITATION
Outcome 24: Increased access to clean water
79 | Water infrastructure increased | Percentage of construction works | Poor Water pipeline condition | Administrative data | Preparation of MoU | 10% | 20% | 30% | 30% for works of construction of Rwandabarasa water pipeline | DISTRICT: 1.Payment of submitted invoices at District level 2.Follow up of construction activities MLFM Ltd: 1Tendering 2. Execution of rehabilitation activities 3. Speed up the project activities | construction of Rwandabarasa water pipeline is 16.2% | 81 | 54
80 |  | Percentage of construction works | - | Administrative data | _ | Tendering of works | 20% | 40% | 40% for Construction of Minago water source | DISTRICT: 1.Payment of submitted invoices at District level 2.Follow up of construction activities WORLD VISION: 1Tendering 2. Execution of construction activities 3. Speed up the project activities | Contract for Minago water source signed | 0 | 0 | COVID-19 stoped implementation of Projects
81 | Gihengeri water pipeline to Nyabikiri IDP Model Village extended | Percentage of extension works | - | Administrative data | _ | Tendering of works | 10% | 70% | 70% of works for Extension of Gihengeri water pipeline to Nyabikiri IDP Model Village. | DISTRICT: 1.Payment of submitted invoices at District level 2.Follow up of construction activities WORLD VISION: 1Tendering 2. Execution of construction activities 3. Speed up the project activities | Extension of Gihengeri water pipeline is at 50% | 147 | 71 | COVID-19 stoped implementation of Projects
82 | Compliance to existing rural water tariff enforced | Percentage of compliance to existing rural water tariffs |  | Administrative data | Mobilization of water system managers | 100% | 100% | 100% | 100% | District 1. Water Price and toll free number written on public taps 2. Public awareness on existing rural water tariffs 3. Regular monitoring and reporting on tariff compliance | All 469/469 rural water tariffs written | 100 | 100
83 | Public water taps operationalized and properly managed | Number of public water taps operationalized | - | District inventory report | _ | _ | 20 | 22 | 42 of public water taps operationalized | District 1. Rehabilitation of non-operational systems and taps 2. Monitor private operators contract compliance 3. Ensure tap managers availability 4. Monitor and ensure regular maintenance of water infrastructure 5. Awareness campaign to the public 6. Recover arrears for the water bills | 12/20 of public water taps operationalized | 60 | 28.5714 | COVID-19 stoped implementation of Projects
SECTOR: URBANIZATION AND RURAL SETTLEMENT
Outcome 25: Increased access to improved settlement
84 | Households (HHs) living in High Risk Zones (HRZs) relocated | Number of HHs living in High Risk Zone relocated | - | District reports | Beneficiaries identified | Mobilization of community to relocated | 7 | 7 | 14 Households relocated from high risk zone | DISTRICT: 1.Identification of Community to relocated 2.Follow of activities related to relocation activities | 6 /7 Households relocated from high risk zone, | 85.7 | 42.8 | COVID-19 stoped implementation of Projects
HUMAN SECURITY ISSUES ADDRESSED
85 | Human Security Issues addressed | Number of houses and their accessories (toilets and kitchens) constructed for eligible vulnerable HHs (including those in Ubudehe cat.1 ) | 314 | Administrative data | 100 houses and their accessories (kitchen and toilet) constructed | 182 houses and their accessories (kitchen and toilet) constructed | 166 houses and their accessories (kitchen and toilet) constructed | - | 448 houses and their accessories (kitchen and toilet) constructed for eligible vulnerable HHs (including those in Ubudehe cat.1 ) | DISTRICT: 1.Identification beneficiaries 2.Organize community works/Umuganda 3.Folow up of construction of works 4.Provide roofing | 245 Houses completed,131 roofed,19 at roofing,34 at elevation stage and 19 not yet started=95.8 | 95.8 | 91.7
86 |  | Number of poor houses for eligible vulnerable HHs rehabilitated | 972 poor houses rehabilitated | Administrative data | Mobilization of community and partners | 500 | 629 | 1000 | 2,129 poor houses for eligible vulnerable HHs rehabilitated | DISTRICT: 1.Identification beneficiaries 2.Organize community works/Umuganda 3.Folow up of construction of works 4.Provide roofing | 168/629 houses rehabilitated | 26.7 | 7.9 | COVID-19 stoped implementation of Projects
87 |  | Number of latrines constructed for eligible vulnerable HHs (including those in Ubudehe cat.1 ) | - | Administrative data | 2 | _ | _ |  | 2 latrines constructed | DISTRICT: 1.Identification of beneficiaries 3. Follow up of implementation | 2 latrines for eligible vulnerable HHs (including those in Ubudehe cat.1) constructed | 100 | 100
88 |  | Number of poor latrines for eligible vulnerable HHs rehabilitated | 7, 853 poor latrines rehabilitated |  | Mobilization of community and partners | 700 | 2700 | 4157 | 7,557 poor latrines for eligible vulnerable HHs rehabilitated | DISTRICT 1.Mobilization of community 1.Identification of beneficiaries 3. Follow up of implementation PARTNERS: 1.Provide financial support 3. Follow up of implementation | 1470/7557(19.45%) toilets rehabilitated | 54.4444 | 19.45 | Activities suspended due to COVID-19
89 | Operationalization of Human Security Task Force | Number Task Force meetings and inspections conducted | - |  | 2 Task Force meetings for HSI and 1 inspection exercises conducted. | 2 Task Force meetings for HSI and 1 inspection exercises conducted. | 2 Task Force meetings for HSI and 1 inspection exercises conducted. | 2 Task Force meetings for HSI and 1 inspection exercises conducted. | 8 Task Force meetings for HSI and 4 inspection exercises conducted. | DISTRICT 1. Appointing members and operationalizing Human Security Taskforce at different levels (District, Sector and Cell levels) 2. Conduct meetings to monitor and report on implementation progress of human security issues identified: 3.Conduct quarterly Inspections of HSI | 5/6 meetings and 4 /3 inspections conducted (84.25%) | 84.25 | 84.25 | Activities suspended due to COVID-19
TRANSFORMATIONAL GOVERNANCE PILLAR
SECTOR: GOVERNANCE AND DECENTRALIZATION
Outcome 26: Improved governance, service delivery and accountability in Local Government
90 | Citizens demands/complaints received and timely resolved by Local Government | Proportion of Citizen demands/complaints received and timely resolved by Local Government | 91% | Administrative data | 100% | 100% | 100% | 100% | 100% of Citizens' cases received and timely resolved by Local Government | DISTRICT: 1.Conduct outreach program, 2. Reports elaborations 3. Monitor the execution/Implementation of cases resolved | 986/1041 =94,7% of Citizens' cases received and timely resolved by Local Government | 94.63 | 94.64
91 | Quality service delivery institutionalized | Percentage of Irembo services delivered by Local Government within the set timeframe | 99.2 | Irembo Reports | 100% | 100% | 100% | 100% | 100% of Irembo services delivered by Local Government within the set timeframe | DISTRICT: 1. Process and deliver requested services 2. Mobilize citizens on Irembo services | 20,672/21004 of Irembo services delivered by Local Government | 98.4 | 98.4
92 | Mission allowances to LG Staff working at Sector and Cell level paid on time | Percentage of payments (mission allowances) to LG Staff working at Sector and Cell level made on time (by the time of undertaking the missions) | Assessment being conducted | MINALOC Inspection reports | 100% | 100% | 100% | 100% | 100% of Payments of mission Allowances to LG Staff working at Sector and Cell level made on time (by the time of undertaking the missions) | DISTRICT 1. Timely disburse to Administrative Sectors the required allowances for Local Government Staff working at Sector and Cell level 2. Timely payment of allowances (by the time of undertaking the missions) 3. Monitoring and reporting | 881/ 1663 Payments of mission Allowances to LG Staff working at Sector and Cell level made on time | 53% | 53
93 | Citizens satisfied with Service Delivery and increased accountability at local level. | Percentage of CRVS event (Birth, death, Marriage and Divorce) recorded in CRVS Books and Web based application | • Births: 90.7 % • Marriages: 97.4 % • Divorce: 100% •Deaths: 103% registered Recorded in civil registration books and CRVS web based application | Administrative data | • Births: 90% • Marriages: 100% • Divorce:100% •Deaths:100% | • Births: 90% • Marriages: 100% • Divorce:100% •Deaths:100% | • Births: 90% • Marriages: 100% • Divorce:100% •Deaths:100% | • Births: 90% • Marriages: 100% • Divorce:100% •Deaths:100% registered Recorded in civil registration books and CRVS web based application up to end May | • Births: 90% • Marriages: 100% • Divorce:100% •Deaths:100% registered Recorded in civil registration books and CRVS web based application up to end May | DISTRICT: 1.Mobilization of population: 2.Recording CR events in CRVS Web application: 3.Monitoring 4.Quartery Compilation of CRVS web application reports | • Births: 87.1%/ 90% which gives 96.8% • Marriages: 98.7% • Divorce: 86.7% •Deaths: 97% registered/Recorded in civil registration books and CRVS web based appli | 95 | 95
94 | Kiziguro Genocide Memorial site constructed | Percentage of construction works | Memorial site in poor condition | Administrative data | Tendering of Construction works | 10% | 30% | 40% | 40% | DISTRICT: 1.Tendering process 2. Monitoring construction works; | Construction for Kiziguro Memorial site is at 11.8% | 39.3333 | 29.5 | COVID-19 stoped implementation of Projects
Outcome 27: National Values, Ethics and National Service Promoted
95 | Residential National Service strengthened | Percentage of participants (A Level finalist students) trained in residential National Services (Urugerero ruciye ingando) | - | NURC Administrative Report | _ | _ | _ | Trained 50% A Level finalists through Residential National Service | 50% of A Level finalists participated to Residential National services (Urugerero ruciye ingando) 4th intake and deployed | DISTRICT: 1. Identification of sites and list of participants 4. Train participants of Urugerero ruciye ingando 5. Coordinate and monitor Urugerero activities NIC 1.Provide guidelines for residential national service | List of participants identified and participants of Urugerero ruciye ingando trained and correction funds are on going | 100 | 30 | Activities suspended due to COVID-19
96 |  | Itorero operationalized in all villages/schools/working institutions | 602 Itorero at Village | Administrative data | _ | _ | Conduct Training | Itorero operationalized in 602 villages | Itorero operationalized in 602 villages | DISTRICT: 1. Identification of participants 2.Conduct training | Itorero are operationalized in all 602 villages | 100 | 75
Outcome 28: Enhanced transformational leadership within the Local Government
97 | Transformational villages (Imidugudu Ntangarugero) identified and recognized | Number of Transformational villages established (Imidugudu ntangarugero) | - | Administrative data | 1. Selection of 14 transformational villages 2. Identification of activities to be done | 30% of the components to be in 14 transformational villages available | 60% of the components to be in 14 transformational villages available | 100% of the components to be in 14 transformational villages available | 14 Transformational villages identified and recognized | 1. Selection of 14 transformational villages 2. Identification of activities to be done 3. Quarterly monitoring of the implementation process 4. Annual evaluation | 76 % of the components to be in 14 transformational villages are available. | 125 | 76
SECTOR: JUSTICE RECONCILIATION LAW AND ORDER
Outcome 29: Improved access to quality Justice
98 | Justice delivery at local level reinforced | Percentage of cases executable cases received (before 30th May 2020) and executed | 94% Judicial courts executed. | Administrative data | 70% | 80% | 90% | 100% of executable decided cases up to March 2020 are received and executed | 100% of executable decided cases received before 30th March 2020 are executed | DISTRICT: 1.Follow up of resolved cases 2. Execute the cases | 204/242=84,2% of cases executable cases executed | 93.5556 | 83.3
99 |  | Percentage of cases received by mediation committees " Abunzi" up to end May 2020 will be solved | 94.2% cases received and settled by mediation committees(Abunzi) | Administrative data | 70% | 80% | 90% | 97% | 97% of cases received by mediation committees " Abunzi" up to end May 2020 will be solved | DISTRICT: 1.Training of mediator 2.Sectors and cells monitor whether the received cases have been resolved 3.Montly and Quarterly reporting of received and resolved cases | 1056/1085= 97.3% of cases received by mediation committees " resolved | 107.7778 | 97.3
100 | Ndi Umunyarwanda events conducted | Number of Ndi Umunyarwanda interaction sessions organized and held at sector, cell and village level | Ndi Umunyarwanda organized once at Sector and District level | Administrative data | Ndi Umunyarwanda organized once at District and Sector | Ndi Umunyarwanda organized once at Cell | Ndi Umunyarwanda organized once at Village | - | Ndi Umunyarwanda organized once from District to Village level | DISTRICT: 1.Organize meeting for Ndi Umunyarwanda | Ndi Umunyarwanda organized once at District , Sector and Cell level done | 100 | 100
SECTOR: PUBLIC FINANCE MANAGEMENT
Outcome 30: Performance of development projects fast-tracked through improved projects management and coordination
101 | Improved project implementation | Percentage of well performing projects in 2019-2020. | - |  | _ | _ | _ | 100% well performing projects in 2019-2020. | 100% well performing projects in 2019-2020. | District 1. Monitor project implementation and fast track their implementation | Implimentation of projects is on going | 100 | 60 | COVID-19 stoped implementation of Projects
Outcome 31: Increased district own revenues generation capacity from 1,014,448,756 Frw to 1,148,872,296 Frw
102 | District Own revenues increased | Amount of own revenues generated (Frw) | 1,014,448,756 Frw of revenue collected | Administration Data | 234,168,211 of revenue collected | 341,610,767 of revenue collected | 342,916,714 of revenue collected | 230,176,604 of revenue collected | 1,148,872,296 Frw of revenue collected | DISTRICT: 1.Monitor revenue collection in collaboration with Outsourced Companies' Staff. 2.Conduct awareness campaigns to taxpayers RRA: 1.Collect Decentralized Taxes and Fees. 2.Update list of taxpayers | 878,597,924/918,695,692 Frw =96% of revenue collected | 96% | 76%
Outcome 32: Increased transparency and accountability of Public funds in Local Government
103 | Government funds for executable cases recovered | Percentage of Government funds recovered on executable cases | 1,000,000 Rwf recovered in FY 2018-19 | Administrative data | Identification of unrecovered government funds, Procurement process of Professional Court Bailiff | 40% | 70% | 100% | 100% of Government funds recovered on executable cases | DISTRICT : 1. Identification of all government funds not yet paid 2. Recovery of funds | Identification of unrecovered government funds, Procurement process of Professional Court Bailiff and 5,240,250/33,218,224=15% fr recovered | 22% | 15 | Activities suspended due to COVID-19
104 | SACCOs' Non Performing Loans provided to LG Staff recovered | Percentage of SACCOs' Non Performing Loans recovered from LG staff | 84% |  | _ | 90% | 100% | 100% | 100% of SACCOs' Non Performing Loans recovered from LG staff | 1.Mobilize Population;3. Organize recovery week, | Recovery of non performing loans from LG staff is at 91% | 91% | 91%
105 | Public accountability enhanced and PFM strengthened | Percentage of Auditor general's recommendations implemented. | Auditor General report recommendations are implemented at 54% (2016-2017) | Administrative data | 60% | 70% | 70% | 80% | Auditor general recommendations (2017-2018) implemented at 80% | DISTRICT: 1.To follow up the implementation of AOG recommendations | 58.7% of Auditor general's recommendations implemented. | 78.2667 | 73.375
106 |  | Number of NBAs audited by District Internal Auditors. | 20 NBA were audited | Administrative data | Conduct audit at 3 schools, 2HC,One sector and follow up of implementation | Conduct audit at 2HC, 3 schools and follow up of implementation | Conduct audit at 4 schools, One Sectors, follow up of implementation | Conduct audit at 3 schools, One HC and follow up of implementation | Conducted Audit in 20 public institutions (NBAs) (5 Centers, 13 schools, 2 sectors) | DISTRICT: 1. Conduct Audit of NBAs | 16/16 NBAs Audited | 100 | 80
107 | NBAs assessed using peer review and peer learning approach | Percentage of District NBAs assessed using peer review and peer learning approach | - | Administrative data | 10% | 30% | 50% | 75% | 75% | 1. Identification of NBAs to be assessed 2. Conduct joint assessment of NBAs 3. Monitoring of implementation of peer review-peer learning recommendations | 71/115=62% NBAs assessed using peer review and peer learning approach | 124 | 82.6667
Outcome 33: Increased internet connectivity to productive use areas
108 | Internet connection rolled out to Local Government institutions | Number of local administrative institutions (offices, schools, Health facilities, SACCOs) connected to Internet | 85 | District Administrative data | Procurement process | 14 | 10 | 5 | 29 District local institutions connected to Internet | MINICT 1. Procurement process 2. Connecting of institutions to Internet DISTRICT 1. Facilitation in the process 2. Follow up installation works of internet in selected | Contract signed and Instalation started and 12/29 institutions connected | 50 | 41.4%
|  |  | Cluster | Targets | Green (75%-100%) | Yellow (50%-74%) | Red | Not yet started
(0%-49%)
|  |  | Economy | 30 | 18 | 3 | 9
|  |  | Social | 59 | 34 | 11 | 14
|  |  | Good Gov. | 19 | 13 | 3 | 3
|  |  | TOTAL | 108 | 65 | 17 | 26
|  |  | PREPARED By: |  |  | APPROVED By:
|  |  | MUGIRANEZA David |  |  | GASANA Richard
|  |  | Director of Planning M&E Gatsibo |  |  | MAYOR Gatsibo District