REPUBLIC OF RWANDA

NORTHERN PROVINCE

MUSANZE DISTRICT DEVELOPMENT STRATEGY

(2018 -2024)

November,2018

ACKNOWLEDGEMENTS

The District Executive Committee wishes to express its sincere gratitude, appreciation, recognition and thanks to all the individuals and institutions that have been involved, in one way or another to accomplish this task and without which it would have been difficult to complete this work on time.

We are very grateful for the financial and technical support of Ministry of Finance and Economic Planning (MINECOFIN) and the coordination and collaboration with the Ministry of Local Government (MINALOC). Our profound gratitude goes also to an international organization founded to support green economic growth, the Global Green Growth Institute (GGGI) who provided us with technical staff.

The District Executive committee extends its sincere thanks to the Provincial Steering Committee members for their proficient guidance and support in accordance with their mandate.

The District Leadership highly appreciates the guidance provided by the District Council and JADF during the consultations and validation workshops.

Finally, we would like to extend our sincere thanks to various officials of Musanze District, in particular the District staff coordinated by the DDS facilitator, Miss Diane Umukunzi and Director of Planning, Monitoring and Evaluation, Jean Damascene Iyamuremye for their effective and invaluable efforts during the whole exercise.

Jean Damascene HABYARIMANA

Mayor of Musanze District

Contents

0	Executive summary	1

1	Chapter 1:  Introduction	2

2	Overview of the District	6

2.1	District Profile	6

2.1.1	Geography	6

2.1.2	Socio-Economic Environment	6

2.2	Overview of District Achievements during DDP Implementation	6

2.3	Key District economic potentialities	10

2.4	SWOT Analysis	10

2.5	Stakeholder analysis	14

3	Alignment with national policy framework and methodology	16

3.1	Methodology	16

3.2	Main issues at District level	16

3.2.1	Economic transformation pillar	16

3.2.2	Social transformation pillar	16

3.2.3	Transformational Governance Pillar	16

3.3	Alignment to NST1	17

4	Strategic Framework	27

4.1	The District Vision, Mission and Objectives	27

4.2	Main Priorities at District level	27

4.3	Results Chain	28

4.4	Logical Framework	28

4.5	Cross-Cutting Areas	31

5	DDS Implementation	32

5.1	Sequencing of Interventions (Implementation Plan)	32

5.2	DDS Implementation Strategy	32

5.2.1	Roles and responsibilities of partners and stakeholders	32

5.2.2	Mechanisms for coordination and information sharing	33

5.2.3	Risk mitigation strategies	33

5.2.4	Communication and marketing strategy for the District	33

6	Monitoring and evaluation	34

7	Cost Monitoring and evaluation	35

Annex	1

Figures

Figure 1: Map of Musanze District	7

Figure 2: Population Employment in Musanze	11

Figure 3: Youth employment in Musanze	11

Figure 4:	13

Figure 5: Type of Habitat in Musanze District	15

Figure 6: % of HHs members with Health Insurance	17

Figure 7: % of married people using contraception	17

Figure 8: Map of Musanze District’s Potentialities best agriculture soils	23

Figure 9: Economic Transformation	3

Figure 10: Social Transformation	4

Figure 11: Transformational governance	5

Figure 12: Result Chain (Impact 1)	6

Figure 13: Result Chain (Impact 1I)	9

Tables

Table 1: Population Distribution by sector and sex in Musanze District	9

Table 2:Assessment of the implementation progress of District Development Plan 2013-2018	20

Table 3:Potentialities per administrative sector	24

Table 4:SWOT analysis	26

Table 5: Stakeholder Analysis	33

Table 6: DDS Alignment to NST1	40

Table 7: Logical framework	15

Table 8: Costing of DDS	59

Modification History

| Version | Date | Authors | Summary of Changes |
| --- | --- | --- | --- |
| Draft 2 |  |  | -Addressed comments from quality assurance team |
| Draft 3 | 18/05/2018 | - Diane Umukunzi Uyambaje (Musanze DDS Facilitator) - Jean Damascene Iyamuremye (District Planner) | -Included the Costing and the Financial Chapter |
| Final Draft | 05/06/2018 | - Diane Umukunzi Uyambaje (Musanze DDS Facilitator) - Jean Damascene Iyamuremye (District Planner) | - Addressed Comments from provincial validation meeting |
|  | 29/08/2018 | - Diane Umukunzi Uyambaje (Musanze DDS Facilitator) - Jean Damascene Iyamuremye (District Planner) | - Addressed comments from Resolutions from the exercise on greening the DDS - Addressed comments from Quality Assurance TEam |

Glossary

| Term Name | Definition |
| --- | --- |
| Strategy | A determination of basic long or medium-term goals and objectives of an enterprise, and adoption of courses of actions and the allocation of resources for carrying out these goals |
| Development Strategy | A multi-dimensional process involving reorganization and reorientation of entire economic, social and governance system |
| Transformation | A process of profound and radical change that orients an organizational in a new direction and takes it to an entirely different level of effectiveness |
| Urbanization | A process of change from rural to urban ways of living, in physical-spatial, social and economic terms. Also defined as the process by which towns and cities are formed and increased in numbers and size as more and more people begin living and working in central areas defined as urban |
| Green Urbanization | The urbanization process where negative associations (urban sprawl, informal settlements, inefficient use of resources, public services and traffic congestion) are sustainably prevented to account for poverty alleviation and environmental protection and preservation. |
| Green Growth | A relatively new model of economic growth that is compatible with protecting the environment, reducing carbon and other unwanted emissions, improving the rational use of resources, dealing with climate change, securing access to clean energy and water and simultaneously targeting |

Abbreviations

| Abbreviation | Description |
| --- | --- |
| % | Percentage |
| AGF: | Agriculture Guarantee Fund |
| ANC | Antenatal Care |
| CNLG | National Commission for the Fight Against Genocide |
| CBHI | Community Based Health Insurance |
| BNR | National Bank of Rwanda |
| DR | Democratic Republic |
| DDS | District Development Strategy |
| DDP | District Development Plans |
| DHS | Demographic and Health Survey |
| ECE | Early Childhood Education |
| ECD | Early Childhood Development |
| EICV | Integrated Households Living Conditions |
| EDPRS | Economic Development and Poverty Reduction Strategy |
| EAC | East African Community |
| EUCL | Energy Utility Corporation Limited |
| FARG | Genocide Survivors Assistance Fund |
| FBF | Fortified Blended Food |
| FP | Family Planning |
| FRW | Rwandan Franc |
| GoR | Government of Rwanda |
| HC | Health Centre |
| HP | Health Post |
| HH | House Hold |
| IT | Information and Technology’ |
| ICT | Information and Communication Technology |
| JADF | Joint Action Development Forum |
| LED | Local Economic Development |
| LG | Local Government |
| LODA | Local Administrative Entities Development Agency |
| MDG | Millennium Development Goal |
| M&E | Monitoring and Valuation |
| MINECOFIN | Ministry of Finance and Economic Planning |
| MINALOC | Ministry of Local Government |
| MESC | Musanze Employment Service Centre |
| MININFRA | Ministry of Infrastructure |
| MoH | Ministry of Health |
| MoE | Ministry f Environment |
| MINICT | Ministry of ICT and Innovation |
| MINAGRI | Ministry of Agriculture |
| MINEDUC | Ministry of Education |
| MINICOM | Ministry of Trade and Industry |
| MINISPOC | Ministry of Sports and Culture |
| NST | National Strategy for Transformation |
| NGOs | Non-Governmental Organizations |
| NAEB | National Agricultural Export Development Board |
| NISR | National Institute of Statistics of Rwanda |
| PTA’s | Parents and teachers’ association |
| PHC | Population and Housing Census |
| PSF | Private Sector Federation |
| RALC | Rwanda Academy of Language and Culture |
| RAB | Rwanda Agriculture Board |
| RDB | Rwanda Development Board |
| RIF | Rural Investment Facility |
| REB | Rwanda Education Board |
| REG | Rwanda Energy Group |
| RFTC | Rwanda Federation of Transport Cooperatives |
| REMA | Rwanda Environment Management Agency |
| RGB | Rwanda Governance Board |
| RHA | Rwanda Housing Authority |
| SACCO | Saving and Credit Cooperative |
| SDGs | Sustainable Development Goals |
| STME | Science Technology Engineering and Mathematics |
| SP | Social Protection |
| SSPs | Sector Strategic Plans |
| TV | Tele vision |
| TVET | Technical and Vocational Education and Training |
| UR | University of Rwanda |
| USD | United States Dollar |
| VUP | Vision 2020 Umurenge Programme |
| WASAC | Water and Sanitation Corporation |
| WDA | Workforce Development Authority |

# Executive summary

Musanze District is one of the six secondary cities and one of the 5 districts in the Northern Province of Rwanda. Musanze City is about 94 km from Kigali on the major Kigali-Musanze-Rubavu-Goma road and it borders with Uganda and DR Congo in the North, Gakenke District in the South, Burera District in the East and Nyabihu District in the West. Rwanda's mountain gorillas (Gorilla beringei beringei) are found in the Volcanoes National Park, making Musanze District the most popular tourist destination in the country.

The District development Strategy for Musanze District aims at ensuring the district vision of being ”An excellent centre of Tourism Industry” with three goals; improve attractive Tourist Sites, Promote sustainable Agro processing, basic infrastructure. These goals are coupled with eight objectives: identification of seven new tourist sites, put in place new tourist facilities, increase local revenues; increase food security extend basic infrastructure, facilitate the accessibility to clean water, promote exportations, and creation of new off farm jobs.

Some of the challenges that have been identified throughout the implementation of DDP are limited access to affordable and social housing units, lack of appropriate solid waste treatment facilities and lack of systematic sewerage management, lack of tourist infrastructures and youth unemployment.

Reference was also made to NST1 priorities and the existing potentialities in the District, which have been defined in the Local Economic Development Strategy as to promote new eco-tourism development that will boost the growth of the District by establishing new off farm employment and thus, increase local revenue collection. The key strategic interventions to be focused on throughout the six upcoming years are:  Promote Urban Development by upgrading informal settlements; diversify and create new sites for Eco-Tourism Development, ensure efficient, effective & affordable infrastructure (water, energy and IT), promote urban livelihood; increase agricultural and livestock productivity; empowering youth; develop and promote Public Private Partnership Sector, increase access to sanitation facilities and ensure the recycling of Waste water.

The monitoring and evaluation of Musanze District Development Strategy will ensure an effective monitoring and evaluation system basing on implementation processes of what is highlighted as key pillar of economic growth for the seven years.

The following are some of the sources of funds for Musanze District Development Strategy; the central government transfers, district own revenues from taxes and fees, the private sector, local and external NGOs, faith-based organizations and other development partners. All projects and program will require an estimated budget amounting to 268,462,768,000 Rwandan Francs.

# Chapter 1:  Introduction

This chapter gives a general overview of the District Development Strategy (DDS) for Musanze that is developed from the background of the District, previous development documents and problem identification. It briefly sets out the context and purpose of the DDS, and process undertaken to elaborate the DDS.

## General Introduction

During the elaboration of the National Strategy for Transformation (NST1) and Vision 2050, Districts are required to develop inclusive 6-years Development strategies that will guide different actors in the District development over a medium term (2018/19-2023/24). The elaboration of the District Development Strategies will generate sustainable strategies that will be inspired by and align with the various national policies such as Vision 2020 and other international mandates such as EAC Vision 2050, Africa Agenda 2063, SDGs, and Paris Climate agreement.

  - Context and Purpose of the DDS

The Government of Rwanda in 2000 adopted the Vision 2020 with the primary objective of transforming Rwanda into a middle-income country by the year 2020. The Vision 2020 is being implemented through the medium-term planning framework that began in 2002. This has since been followed by the Economic Development and Poverty Reduction Strategies (EDPRS1 and EDPRS2), which covered the period of 2008-2012 and 2013/14 to 2017/18 respectively.

The Vision 2020 is remaining with two years of implementation while the EDPRS 2 is in its final year. In 2016, The National Dialogue Council “Umushyikirano” recommended the elaboration of the new vision of 30 years. However, the concept note of the Vision 2050 has been presented at the same forum in 2016 at which a target was set for Rwanda to become an upper middle-income country by 2035 and a high-income country by 2050. In the same spirit the implementation instrument for the remainder of Vision 2020 and for the first four years of the journey under Vision 2050 will be the National Strategy for Transformation (NST1), which integrates global and regional planning commitments including: the Sustainable Development Goals (SDGs), the EAC Vision 2050 and the Agenda 2063. The NST1 document builds on a series of interconnected strategies, mainly: Thematic, Sector and District development strategies. It is against this background that the new District Development strategic plans are being elaborated since the existing ones (2013/14 to 2017/18) will end in June 2018.

The elaboration of the Musanze DDS ensured the harmonization of local priorities to national level priorities, by considering unfinished business of the DDP, EDPRS 2 and Vision 2020 and capturing global commitment to sustainable development and cross cutting areas of development. The elaboration process, including dissemination of guidelines to all stakeholders, training on methodologies to be applied in development of District Development Strategies (DDS) is managed by the Ministry of Finance and Economic Planning (MINECOFIN) plus linking the technical consultation forums with the National Steering Committee in conjunction with the Ministry of Local Government (MINALOC) to help the implementation in the local context.

This development strategy will serve as an important instrument that is destined to guide and control the development of Musanze District throughout the NST1 period 2017/18-2023/24 and Vision 2020. This DDS will consequently influence future development of the district.

  - Elaboration Process of DDS

The process of developing this strategy was achieved through participatory process. On the first hand, primary data have been collected through organizing various trainings, workshops and consultative meetings by involving citizens and all district partners. On the second hand. Secondary data were collected from different desk review and analysis whereby the district achievements and challenges during last five years were considered.

  - Short Description of the Contents of each Chapter of the DDS

MUSANZE District Development Strategy (DDS) is composed of seven chapters as described below:

The first chapter is made by the general introduction, and the second one presents an overview of the district and current socio-economic status of the district. Chapter three discusses the alignment with national policy framework and methodology while chapter four is presenting the strategic framework for the next six years that will be undertaken to achieve the objectives of the District Development Strategy by addressing the existing challenges. Chapter Five highlights the implementation phase of the District Development Strategy and introduces chapter six which presents the process to monitor and evaluate the District Development Strategy objectives. Finally, chapter seven is about the costing and financing of the District Development Strategy.

# Chapter 2: Overview of the District

This section presents the profile of Musanze District with key achievements and challenges facing the district as well as the remaining outstanding interventions from planned priorities in the EDPRS 2, as drown from a self-assessment on DDP 2013-2018. Finally, the document emphasises on the stakeholder analysis and key District economic potentialities.

## District Profile

### Geography

Size and Location

Musanze District is one of the six secondary cities and one of the 5 districts in the Northern Province of Rwanda. The total area of the district is 530,4 km², 60 km2 occupied by the Volcanoes National Park and 28 km2 accommodating Lake Ruhondo. Musanze City is about 94 km from Kigali on the major Kigali-Musanze-Rubavu-Goma road and it borders with Uganda and DR Congo in the North, Gakenke District in the South, Burera District in the East and Nyabihu District in the West.  The district has a total urban planning area of 10,000ha.

Figure 1: Map of Musanze District

Source: NISR, 2012

Fauna and Flora

Rwanda's mountain gorillas (Gorilla beringei beringei) are found in the Volcanoes National Park, making Musanze District the most popular tourist destination in the country and in the region. This is one of the sound particular aspects that have prompted the government to promote Musanze as the secondary city for ecotourism.

Biodiversity in this district is under threat since a huge number of the population is daily busy working in agricutural sector. They have stripped away much of the natural vegetation to grow food crops such as potatoes and sorghum or cash crops like pyrethrum.

Forests cover an area of about 11,616 ha in Musanze, broken down as follows: Bamboo forests: 2,517 ha; degraded natural forest: 2,223 ha; Eucalyptus forest plantation: 1,626 ha and mountain humid forest: 5,250 ha. State and district forests comprise 24 and 2 per cent of all forests in the district, respectively, while private forests comprise 74 per cent. The 33 ha Buhanga forest has a high level of biodiversity and cultural significance. It is host to 83 bird species, three of which are endemic to the Albertine Rift. It is also a stopover for the African Pitta, a migratory bird species. There are 189 plant species of which 38 are known medicinals and 13 mammal species. Some of the fauna in the area are the porcupine, jackal, wildcat, mongoose, hyrax and leopard.

Geology and Soil

The District has 2 distinct zones and consequently related types of soils, one being volcanic area with moderate slopes and volcanic ash soils with lava predominant stones. The other part comprises steep hills where erosion is active.

The soils of the City of Musanze can be categorized as volcanic on moderate to steep slopes, with volcanic ash soils and volcanic lava predominating with stones and shallow rocks. Soil erosion and soil nutrient loss are major problems, with only about half the land protected against soil erosion. The rich volcanic soils are ideal for agriculture, especially crops such as the Irish potato, which is commonly grown in Cyuve, Busogo, Gataraga, Kinigi, Muko, Musanze, Nyange and Shingiro. The Irish potato has been proposed for processing into potato chips.

### Socio-Economic Environment

This section focuses on key sector performances indicators achieved and contributed to the district economic development and welfare improvement of MUSANZE citizens. It highlights the overall achievements related to the socio-economic challenges to be addressed by the district in the upcoming seven years period in order to ensure better life to Musanze citizen.

      - Demography

The 4th Rwanda Population and Housing Census (PHC4) of 2012, has enumerated 368,267 inhabitants in Musanze District on a density of 694 Inhabitants/Km2, where 47.4% are males and 52.6% are females; and 27.7% living in urban areas and 72.3% living in rural areas. Musanze population represents 3.5% of the total population of Rwanda. It represents 21.3 % of the Northern Province population (1,726,370 inhabitants). Muhoza is the highest populated (51.878) sector, whereas Nkotsi is the least (13,594).

The recent data from Ubudehe Profiling carried out by LODA in February 2018 shows that there is a likely increase of habitants from 368,267 in 2012 to 406,479 in 2018. The table 2 below is providing EICV 4 demographic data.

Table 1: Population Distribution by sector and sex in Musanze District

| Sectors | Male | Female | Total |
| --- | --- | --- | --- |
| Busogo | 10.203 | 11.309 | 21.512 |
| Cyuve | 18.358 | 20.733 | 39.092 |
| Gacaca | 11.208 | 12.397 | 23.605 |
| Gashaki | 6.509 | 7.139 | 13.648 |
| Gataraga | 10.820 | 11.890 | 22.710 |
| Kimonyi | 7.225 | 8.364 | 15.589 |
| Kinigi | 12.818 | 14.403 | 27.221 |
| Muhoza | 25.377 | 25.377 | 51.878 |
| Muko | 8.959 | 9.978 | 18.937 |
| Musanze | 14.833 | 17.031 | 31.864 |
| Nkotsi | 6.204 | 7.342 | 13,594 |
| Nyange | 12.794 | 14.672 | 27.466 |
| Remera | 9.202 | 9.910 | 19.112 |
| Rwaza | 9.967 | 10.959 | 20.926 |
| Shingiro | 9.922 | 11.240 | 21.162 |
| Total | 174.399 | 193.868 | 368.267 |

Source: NISR, 2012 Population and Housing Census results

2.1.2.2 Musanze District Sectoral Achievements

### Agriculture

Regarding the size of land cultivated per household in Musanze District, the mean size of land cultivated per household is 0.45 ha, which is below the national average (0.59), the rural average (0.6) and the urban average (0.46) and is therefore countrywide among the lowest rates. However, a higher proportion of farmers cultivating larger areas create an enabling environment for the increase in production.

In terms of the percentage of agriculture households purchasing input in Musanze District, the utilization of pesticides (51.9%) and chemical fertilizers (46.5%) is much higher than that of improved seeds (13.8%) and organic fertilizers (13%). Furthermore, the purchase of chemical fertilizers and pesticides in Musanze is significantly higher than the national average (29% for chemical fertilizers and 31.2% for pesticides).

Part of the post-harvest infrastructure of Musanze District is 10 Maize drying grounds. There is also one rehabilitated government-owned warehouse located in the Sector of Cyuve, which has a capacity of 3,500 MT. There is also one Irish Potatoes Collection Centre located in Kinigi Sector.

62.6% of households are raising livestock in the District, which is less than the national average (68.2%). Therefore, the District needs to put more efforts in livestock transformation to reach the national target. Chicken (55%), Cattle (38.4%) and Pigs (30.4%) are the most widespread types of animals raised by households in Musanze. However, the national average shows that in general Goat (55%), Cattle (47%) and Chicken (45%) sound prioritized.

### Private Sector Development and Youth Productivity and Employment

In Musanze District, 82.4% of the population is employed, 2.2% is unemployed and 15.8% is inactive. For those with employment, 15% of them are working in wage farms, 25.8% in wage non-farm, 45.4 % are independent farmer. Unemployment rate in Musanze District is higher in urban (3.1%) than in rural areas (2.0%) and unemployment rate among females is higher than males (2.0%vs 1.9%). (EICV4)

Figure 2: Population Employment in Musanze

Source: NISR, 2012 Population and Housing Census results

In Musanze district, 64.1% of the youth were employed at the time of the census, 2012 (NISR) while 33.6% were out of the labour market. Only 1.7% was unemployed. The high percentages of employed youth are observed in Kimonyi (71.0%), Gashaki (70.6%), and Nyange (70.2%), and the lowest are in Muhoza (53.6%) and Gataraga sectors (61.6%). The high percentage of unemployed youth is in Kinigi Sector (3.4%) while the lowest is in Gashaki (0.3%). At the time of the census, the percentage of youth out of the labour market was high in Muhoza (42.7%) and Busogo sectors (36.9%), and low in Kimonyi (27.6%). Most of youth aged 14-35 currently employed are self-employed (66.1%), followed by employees (22.4%) and contributing family workers (8.0%). Majority of self-employed youth are found in Gacaca sector (82.8%) while the low percentage is found in Muhoza (44.9%).

Figure 3: Youth employment in Musanze

Source: NISR, 2012 Population and Housing Census results

### Transport

In Musanze district, only 10.6% of population possesses bicycles, 0.4% has motorcycle while 0.8% have cars and this is far below the national level which is 15.8 %, 0.9% and 0.8% respectively for bicycle, motorcycle and cars. This indicates how the district still has a long way to go in matters regarding transport facilities. In fact, 61.9% of the district HHs are not satisfied with their nearest roads compared to 23.1% of household’s nationwide. Likewise, 92.0% of the HHs can access roads in 19 minutes and 7.6% in 20-59 minutes. At national level, 87.9% of Rwandan HHs can access road in 20 minutes while 9.3% have access in 20-59 minutes. In terms of usage rates for public transport, 10.1 % regularly use public transport, 51.3% use public transport often, 31.0% use public transport sometimes and the rest 7.6 % do not use public transport at all (EICV4).

### Energy

Musanze District Profile shows that in urban areas, the three main sources of energy for lighting are electricity (54.9 %), kerosene lamp (20.6%) and candle (16.8%). In rural areas, most private households use kerosene lamp (29.5%), candle (18.7%) and firewood (12.5%) for lighting.

The main sources of energy for cooking used by households are firewood (78.3%), charcoal (15.4%) and grass/leaves (5%). In urban areas, households use more firewood (48.6%) and charcoal (48%). In rural areas, private households use mainly firewood (89.6 %).

### Water and Sanitation

95.3% of HHs in Musanze District have access to clean water, this is slightly higher than the National level (84.8%) of HHs using an improved water source with 23.3% of HHs using protected springs, 60.6% using pipe, 9.9% having water piped into their dwelling/yard. On average, 43.9% of households in Musanze District are located within 15 minutes of walking distance to an improved water source. The mean time to an improved water source in Musanze District is 7.5 minutes, which is far below the national average (11.2 minutes). Musanze district ranks first on this indicator within the Northern Province. However, 1.8% of households in Musanze district still walk more than 30 minutes to reach an improved water source.

Figure 3: Distribution (%) of the Private Households of Musanze district by main source of Water and by sector

Figure 4:

Source: Rwanda 4th Population and Housing Census, 2015 (NISR)

The District of Musanze has well performed in term of population with access to basic sanitation (84.27%) compared to national level (83.4%). The majority using protected latrines (82.0%) and 1.8% don’t have latrine, which is a high score compared to national situation (3.2%) (EICV4)

In Musanze District, waste management is still a problem where 52.49% of HHs thrown their domestic wastes in bushes or field and only 43.3% has composts. This is relatively higher than national level where respectively 40.2% thrown waste in bushes and 51.6% of HHs have composts. In the town, the rate of HHs using public rubbish is 3.0% while at national level is 6.2%. (EICV4)

### Urbanization and Human Settlement

According to EICV4, In Musanze District 52.3% of households are living in settlements (Imidugudu) while 3.4% are living in unplanned clustered rural housing, 24.7% are living in isolated rural housing, and 5.6% living in unplanned urban housing. These are far below the national achievements: 49.2%, 8.7%, 25.6%, and 12.8% respectively. 97.7% of households are single house dwelling, 1.5 % are Multiple HH dwelling, 0.6% are group of enclosed dwellings (Multiple HH) and the rest 0.1% are group of enclosed dwellings (single HH).

Figure 5: Type of Habitat in Musanze District

Source: Rwanda 4th Population and Housing Census, 2012 (NISR)

The most common type of habitat in Musanze district is the clustered rural settlement (known as Umudugudu). 66.6% of the private households are of that type, followed by spontaneous/ squatter housing (15.3%) and dispersed/isolated housing (14.2%). The type of habitat in Musanze varies according to the area of residence; In urban areas, the predominant type is spontaneous/squatter housing with 44.9%, followed by clustered rural settlement (umudugudu) (34.6%) and the planned urban housing (12.8%). In rural areas the predominant type is clustered rural settlement (umudugudu) with 78.6% followed by dispersed/isolated housing with 19.9%, and the spontaneous/squatter housing with 4.1%. (Census, 2012)

At the national level, 28.7% of private households are headed by women and in Musanze; the high percentage of private households headed by females are found in the sectors of Kimonyi and Nkotsi (32%), Musanze (31.7%), Shingiro (30.7%), Kinigi (30.4%) and Nyange (30.3%), and the small ones are in Gashaki (23.2%), Gacaca (24%) and Muhoza (25%).

### Information and Communication Technology

EICV4 shows that 92.5% of the population in Musanze district doesn’t know how to use computer against 92.9% at national level. 0.3% of HH use Internet service regularly while 46.2% do not know of the existence of Internet service facilities (EICV4). 67.2% of the private households possess a radio, 58.6% have a mobile phone, 9% a TV and 2.5% a computer and at the district level, households mainly access Internet at cybercafés (71.6%), at office or school (48.3% and at home 38%).

### Environment and Natural resources

94.5 % of land in Musanze District is protected from soil erosion, while it is 78.1% at national level. 29.73% of surface is covered by forest and 28.6% of land in Musanze is protected to maintain biodervisity. Watershed management on the rivers of Mukungwa, Mpenge, Mutobo, Rubindi, Mukinga,etc. have been put in place. As part of the requirements every big project implemented in the district had carried out feasibility studies including Environmental Impact Assessment.

### Financial Sector development

The data indicates that 40.9% of the population of Musanze district has access to finance (EICV4), above the national average of 39%. With regards to access to business development fund’s products, 2 beneficiaries had access to the Agriculture Guarantee Fund (AGF), nine to SME and 146 to Rural Investment Facility (RIF). Based on different reports from different SACCOs of Musanze, as of December 2016 the number of subscribed members in SACCOs were 34,108, having deposited 651,768,760 Rwf. It is essential to note that there are 15 “Umurenge Saccos” available. In addition to the financial services provided by the government, there are other services offered by private companies, such as “Banque Populaire SA” Bank of Kigali, Ecobank, Equity Bank and private microfinance institutions

### Social Protection

In Rwanda 44.9% of the population is below the poverty line against 53.6% in Musanze District whereas 24.1% is in extreme poverty line against 26.2% in Musanze District.  The District has increased and sustained graduation from core social protection programs for male and female-headed households by connecting them to economic opportunities and financial services.

### Health

Musanze District has a total of 18 health facilities, made of: 16 health centres, 13 dispensaries and one referral hospital. According to DHS5 457 Households that responded to the survey, 384 have at least one member covered by health insurance. The mean walking distance to a health centre is one hour countrywide.

Figure 6: % of HHs members with Health Insurance

The Demographic and Health Survey 2014-2015 data on the use of contraceptive methods shows that in Musanze District 70.6% of married women aged 15-49 use any method for family planning and 66.5% of them use modern methods

Figure 7: % of married people using contraception

### Education

The Rwanda 4th Population and Housing Census, 2012 shows that among the population aged 3 years and above in Musanze district, 23.4% have no education, 56.6% attained the primary level and 12.4% attained secondary level while 2.1% attained university. The level of educational attainment varies across sectors; Muhoza sector has a high proportion of population aged 3 years and above that attained the secondary level (23.3%) and a high proportion of residents aged 3 years and above who attained university (7.8%).

The district has a literacy rate of 65.6% among its population aged 15 years and above. At national level, the average literacy rate is 69.7%. Musanze has a high illiteracy rate compared to the average level of the country. In primary school, pupils/teacher ratio in Musanze District is of 62/1 which is lower than the national ratio of 63/1. At the secondary school level the pupil/teacher ratio is 32/1 whereas the national one is 30/1 (2012 education statistical yearbook).

The mean walking distance to a primary school in Musanze District is 21.6 minutes, while it is 27.2 minutes countrywide. 29.8% of households have a walking distance of between 30 and 59 minutes to a primary school. 2.5% of households must walk for more than one hour to reach a primary school.

School attendance among children in Musanze varies across education levels: It is very low (38.6%) for the preschool-age population (3-6 years), widespread (95.4%) for the primary school-age population (7-12 years), and moderate (71.7%) for the secondary school-age population (13-18 years) at the time of the census. School attendance varies also across the sectors:  for the preschool-age, it varies from 23% in Gacaca to 52% in Remera; for the primary school-age, it varies from 91.7% in Shingiro to 97.9% in Remera for the secondary school-age, it varies from 63.1% in Kimonyi to 77.3% in Nkotsi. (Rwanda 4th Population and Housing Census, 2012 (NISR)

### Governance and decentralization

Citizen participation has been improved as mechanisms and processes were established to promote citizen participation; these include “Inteko z’abaturage” (community assemblies), public accountability and open days, Ubudehe, Umuganda, regular free and fair elections among others. The district has a website which contains information on all sectors but needs to be regularly updated. The annual governance month, accountability days and open days are opportunities for accountability practices, whereby the execution of the Performance Contract “IMIHIGO” is shared with the public.

### Promotion of Justice, Reconciliation, Law and Order

In the justice sector, respondents were most satisfied with the justice service provided by National police, local mediators and Judiciary with satisfaction ratings of 79%, 76% and 71% respectively, compared to 77.6%, 81.6% and 63.4% in 2010 respectively. Scores were similar with prosecution, lawyers, and justice access bureaus who received 67%, 60% and 56% respectively compared to 48.1%, 36.2% and 18.4% in 2010 respectively.

Respondents’ opinion has revealed that 73% of them were happy with the role of mediators in settling disputes, 71% were satisfied with the customer care in the justice sector. The most encouraging fact is that all indicators scored more than 60%. Sensitization on the understanding of laws and access to fair justice, both scored 86% and the lowest score (77%) was reached for the role of mediators in settling disputes.

### Public Finance Management

Musanze District budget is funded by five different sources namely: Block Grant, Earmarked Transfers, Own Revenues, Transfers from other GoR agencies and External Grants. Musanze District own revenue generation only represents 19% of the District total budget.

## Overview of District Achievements during DDP Implementation

The recent assessment of MUSANZE District Development Plan (DDP) 2013-2018 stipulated that the District has achieved its targets at 85%. The table below summarises the key achievements accomplished by the District during the implementation of Musanze DDP 2013-2018 by Sector.

## Table 2: Assessment of the implementation progress of District Development Plan 2013-2018

| DDP Output/ Indicator | Baseline 2013/14 | Target 2017/18 | Achievement |
| --- | --- | --- | --- |
| Agriculture and Livestock |  |  |  |
| Land use consolidation | 58,086 (70%) | 100% | 70% |
| Productivity | 56% | 100% | 85% |
| Fertilizers | 120kg/ha=45% | 300kg/ha | 450kg/ha |
| Vaccination | 27% | 380,000 | 225,000 (59.2 %) |
| Girinka | 1,288 | 9,471 (100%) | 4,847 (51.17%) |
| Artificial insemination | 2290 | 100% | 71% |
| Energy |  |  |  |
| New HHs with Access to electricity | 27.8% | 70% | 39.7% |
| Water and Sanitation |  |  |  |
| New HHs with access to clean water | 81% | 100% | 86.4% |
| Transport |  |  |  |
| % of roads in good condition | 42.5% | 85 % | 75% |
| Settlement |  |  |  |
| New HHs resettled in grouped settlement | 17.8% | 30% | 21% |
| Rural and urban settlement |  | 60% | 35% |
| ICT |  |  |  |
| Number of BDCs/Knowledge hubs at Sector levels established | 0 | 7 | 3 |
| Number of offices equipped with computers and internet | 84 | 352 | 341 |
| Environment and Natural Resources |  |  |  |
| Surface covered by forest | 18.2% | 30% | 29.73% |
| Soil protected against erosion | 52.7% | 100 % | 94.5% |
| Land area protected to maintain biodiversity | 0 | 50.3% | 28.6% |
| Private Sector Development |  |  |  |
| Amount of new investments | 1,418,0902,309 |  |  |
| Number of new investments mobilised | 36,965,545 |  |  |
| Number of modern markets constructed | 6 | 15 | 8 |
| Industrial park constructed | 0 | 0 | 0 |
| Integrated craft centre operational (Agakiriro) | 0 | 2 | 0 |
| Number of Community Processing centre operational | 24 | 74 | 68 |
| Number of hotels constructed | 17 |  | 39 |
| Number of tourist sites developed | 2 |  | 6 |
| Number of projects financed | 114 |  | 695 |
| Number new cooperative financial and technical viable | 120 |  | 649 |
| Financial sector Development |  |  |  |
| Number of SACCOs with required facilities | 15 | 15 |  |
| % Of HHs with access to financial services | 59,516 | 74,471 |  |
| Youth |  |  |  |
| Number of playground developed at sector level | 12 |  | 13 |
| Genocide site at good condition | 1 | 2 | 1 |
| Health |  |  |  |
| Access to Health Facilities | 9 | HC in 15 Sectors (100%) | 14 Sectors (96%) |
| Health insurance | 58.7% | 100% | 86% |
| Population used Modern Family Planning Methods | 18.9% | 100% | 60% |
| Education |  |  |  |
| School feeding | 0 | 100% | 85% |
| Adult literacy | 55% | 95% | 75% |
| Drop out | 11.9% | 0% | 4.1% |
| Construction of new classrooms | 679/48 pupils/class | 40pupils/classroom | 40pupils/classroom |
| Education infrastructure improved | 65% | 89% | -Rehabilitation of 30 and replacement of 42 classrooms -Equipment of 19 adult literacy centers -Upgrading and transformation of Cyabagarura building into a VTC |
| Decentralization |  |  |  |
| Increase service delivery and Public finance management | 25% | 97%) | -GoR-VUP Beneficiary sensitization -Planning, budgeting, monitoring and evaluation of district projects and imihigo -Feasibility studies -Construction of Musanze District Head office - Maintenance of public infrastructures -To connect NBAs to Internet (sectors, cells, health centers and schools) - Construct and equip village knowledge hubs Gatovu IDP Model Village |
| Social protection |  |  |  |
| Increased and sustained graduation from core social protection Programs for male and female headed households by connecting them to economic opportunities and financial services |  |  | Provide Direct Support (DS) to 3,897 vulnerable beneficiaries in VUP/DS |
| Job creation |  |  |  |
| SMSs created | 105 | 350 | 251 |
| New Off farm jobs created | 7678 | 49,000 (7000 per year*7) | 31,282 plus 12,630 for 2017-2018 |
| Reduce Unemployment | 11% | 5% | 8% |
| Access to finance | 10.1% | 50% /Sacco | 25% |

## Key District economic potentialities

Refering to LED strategies for Musanze District; District strategic position and high tourism flow give it a strong comparative advantage in tourism. Similarly, the volume of private investment in tourism is likely to boost investor confidence as the district has a generally positive business environment.

However, the bulk of commercial activity is heavily concentrated within the town. As a result, there is a need to devote considerable attention to agricultural activities in rural areas. This will reduce future geographical inequalities. Generally, strong infrastructure indicators will allow for the expansion of future potentialities at a faster rate than that experienced by most districts. The potentialities listed here, as well as others, are examined in greater detail within the district briefing and field report.

Musanze Top 5 Potentialities:

- Suitable land for agriculture

- Availability of tourist attraction sites

- Availability of infrastructures, manufacturing companies, Volcanic stones and Ruhondo lake that attract many people

- Easy cross boarder business

- Hospitality and tour facilities like hotels, financial institutions, High learning institutions

Figure 8: Map of Musanze District’s Potentialities best agriculture soils

The map in figure 8 indicates potential fertile soils in Musanze district. The entire District bordering volcanic mountains have rich soils that support agriculture.

As shown in the figure, Musanze district has a large area with best soils, suitable for agriculture, because of the presence of the water bodies such as the Lake Ruhondo. This district has fifteen sectors at its north area which are rich in best soils of agriculture and provides Stable Production like Maize, irish potatoes, Potatoes, and Pisciculture.

The table below offers an overall view of potentialities per sector. This allows the programming of sector’s strategies based on the development of local economic potentialities.

Table 3:Potentialities per administrative sector

| Sector | Potentiality | Product |
| --- | --- | --- |
| Busogo | High soil fertility | Irish Potatoes |
|  |  | Wheat Transformation |
|  | Mineral deposits | Travertine, Cassiterite and Volcanic Stones (lava) |
|  | Agro-processing | Animal Feed Processing |
| Cyuve | High soil fertility | Irish Potatoes |
|  | Agro-processing | Animal Feed Processing |
| Gacaca | High soil fertility | Irish Potatoes |
|  | Lake for pisciculture | Fish Farming |
|  | Agro-processing | Animal Feed Processing |
| Gashaki | Lake for pisciculture | Fish Farming |
|  | Mineral deposits | Travertine, Cassiterite and Volcanic Stones |
|  | Agro-processing | Animal Feed Processing |
| Gataraga | High soil fertility | Irish Potatoes |
|  | Agro-processing | Animal Feed Processing |
|  | Rivers for energy generation | Hydropower in Mutobo rivers |
| Kimonyi | Agro-processing | Animal Feed Processing |
| Kinigi | High soil fertility | Irish Potatoes |
|  | Agro-processing | Animal Feed Processing |
| Muhoza | High soil fertility | Irish Potatoes |
|  | Mineral deposits | Travertine, Cassiterite and Volcanic Stones |
|  | Agro-processing | Animal Feed Processing |
| Muko | High soil fertility | Irish Potatoes |
|  | Mineral deposits | Coltan and wolfram |
|  | Agro-processing | Animal Feed Processing |
| Musanze | High soil fertility | Irish Potatoes |
|  | Agro-processing | Animal Feed Processing |
| Nkotsi | Mineral deposits | Travertine, Cassiterite and Volcanic Stones |
|  | Agro-processing | Animal Feed Processing |
| Nyange | High soil fertility | Irish potatoes |
|  | Agro-processing | Animal Feed Processing |
| Remera | Lake for pisciculture | Fish farming |
|  | Agro-processing | Animal Feed Processing |
| Rwaza | Lake for pisciculture | Fish Farming |
|  | Mineral deposits | Travertine, Cassiterite and Volcanic Stones |
|  | Agro-processing | Animal Feed Processing |
|  | Rivers for energy generation | Hydropower in Mukungwa Rivers |
| Shingiro | High soil fertility | Irish Potatoes |
|  | Agro-processing | Animal Feed Processing |

Source: LED potentialities in Musanze District

## SWOT Analysis

The Following table presents the analysis of the district by using SWOT-analysis to identify strengths, opportunities, weaknesses and threats.

Table 4:SWOT analysis

| N° | Sector | Strengths | Weaknesses | Opportunities | Threats |
| --- | --- | --- | --- | --- | --- |
| Economic Transformation |  |  |  |  |  |
|  | Agriculture | - The rich volcanic soils (Suitable land for agribusiness) - Fruits and vegetables, - Livestock breeding and transformation, - Sufficient and seasonal rainfalls | - Limited knowledge and involvement in agribusiness; - Unskilled farmers in modern farming techniques - Insufficient skills and capacity in applying modern pisciculture techniques for increasing production - Low number of pisciculture specialists - Insufficient agricultural technicians - Poor internal farming techniques - Inadequacy of farm power and machinery - Low SACCO repayment of loans - Agriculture inputs insufficient and sometimes delay (seeds and fertilizers). - No adequate research on adaptive crops or seeds to specific area of agriculture zones, - Lack of Agriculture data to use in land management, - Low prices to farmers especially in pyrethrum producers, - Low animal quality and productivity - Low sources of proteins from animals and fishes | - Presence of Village Mechanization Service Centres - The predominance of the population in agriculture conducive weather conditions - Presence of financial institutions in Musanze district that can support Pisciculture Business - Land consolidation - NAEB, RAB are availing modern farming techniques, post-harvest - huge proportion of the population working in agricuture | - Soil erosion and land slide - Climate Change - High acidic soil |
|  | Private sector Development & Youth Employment | - The district serves as the tourist hub of Rwanda - Mineral deposits and quarries for mining development - Arts and crafts for manufacturing development - Proximity to Uganda and DRC; - availing of cross-border trade | - Limited resources for youth to start their own business - Limited small factories and SMEs - Uncompetitive firms in urban areas - Private sector not well organized - Inexistence and limited external investors - Limited tourism infrastructures | - Tourist Sites to facilitate the creation of new off-farm jobs - Availability of many Hotels - Availability of good infrastructure | - Climate variability and change; - Poor and unsustainable management of natural resources |
|  | Transport | - Location of the District; - High population in the District; | - Uncoordinated transport services; - Insufficient budget for gap in feeder road budget; - Poor condition of class one road physical conditions; - Insufficient budget for expropriation in road projects | - Availability of Parking car; | - Land slides |
|  | Energy | - Rivers for energy generation; | - Long process during the distribution of Electricity; - Low access to electricity in comparison to the National targets, - Unaffordable off grid electrification specifically biogas and solar energy: need for clear policy on implementation of biogas - Limited of existing electricity lines monophase to triphase, - Insufficient budget of operation and maintenance for all electricity infrastructure - Limited resource for poor households to have accessibility to electricity | - Existence of two hydro power stations | - Environmental calamities - High cost of electricity generation |
|  | Water and Sanitation | - Availability of diversified sources water | - Limited access to clean water - Inexistence of integrated Solid waste management - Weak storm water drainage system - Inadequate water and waste management systems water pollution - Limited households connected to the septic tank System - Limited rainwater harvesting facilities - Poor management of the water infrastructure - Limited access to improved sanitation - No centralized sewage system transporting faecal waste away from households - Insufficient budget for maintenance operation and upgrading of existing water infrastructures, - Poor water supply management systems - Expropriation not always addressed prior to implementation of WATSAN projects | - Availability of Sanitation Master plan - Cooperatives in place for managing wastes - Presence of partners and donor support in water supply - Availability of Policy and regulation on water and Sanitation | - Climate variabilities and climate change |
|  | Urbanization and Rural Settlement | - Availability of Building materials | - The Insufficient budget to implement existing master plan on the side of the district - Budget gap to implement IDP model village, - No basic infrastructures to planned villages (hard and soft infrastructures), - Weakness building inspection, - Insufficient budget to relocate households in high risk zone to planned settlement villages - Limited of green open public spaces - Inexistence of investors in affordable housing | - Presence of partners and donors in the City infrastructure and economic development - Initiated national fund for affordable housing development - Availability of guiding policies and tools for sustainable urban planning and development | - Environmental calamities |
|  | ICT | - Presence of IT service supply (4G) and telecommunication facilities - High rate of IT devices | - Low capacity and awareness on the use of internet and smart devices - Insufficient ICT infrastructures - Low ICT penetration in the whole District. | - Existing The Online Tax payment system - The e-Payment system - Increased number of online public service provision | - High cost of ICT services and equipment - Environmental calamities |
|  | Environment and Natural Resources | - Availability of lakes and rivers - Rich mineral deposits - Coupled with conducive weather conditions - The presence of the water bodies | - Over exploitation of forest resources - Inadequate solid and liquid waste management - Weak Mining and Exploration licensing system and insufficient inspection capacity to enforce good practice - Little participation of local financial institutions in direct investment in the mining sector. - Environment destruction for sustainable development - Low involvement and ownership of decentralized entities - The mining sector is poorly developed. - The forestry sub sector is lacking professionals’ staff at all levels | - Existence of “centre d’élevage” of Mukinga - Presence of environment officer at district level | - Rising temperatures are envisaged to push certain plant species further up the mountains - Floods and landslides caused by rainfall from volcanoes - Environmental degradation Climate change |
|  | Financial Sector Development | - Availability of financial institutions at local level (UNGUKA, DUTERIMBEREUMURENGE SACCOs) - Local initiatives on access to formal and informal savings (Ibimina,) - Availability of Igiceri Program | - Low awareness and limited use of modern financial systems (Online/ mobile systems) - Existence of Bank Lambert | - Musanze city has the highest per capita income in Rwanda - Presence of District partners in capacity building and financial support - Availability of policies and programs for financial sector development | - High interest rate in financial institutions |
| Social Transformation |  |  |  |  |  |
|  | Social Protection | - Increasing rate of poverty graduation - Existence of Social assistance programs (VUP, FARG, CARITAS,..) | - Low mind set of Beneficiaries about existing social assistance Programs. | - Political will of awareness of programs for social assistance programs. | - Increased population growth |
|  | Health | - HHs with access to health insurance - Availability of high standard health facilities (Ruhengeri Hospital) | - Health services are inadequate - Limited budget to purchase all the needed drugs - Inadequate coordination between public and private - Limited health management capacity - Inadequate health infrastructure - Inadequate specialized doctors and general practitioners with special skills - Community insurance scheme policy has its own challenges | - Government policy and programs to increase access to quality health services | - Limited geographical access to health services - Expensive health services |
|  | Education | - Availability of education facilities - Existence of Technical schools (TVETs, IPRC,…) | - High drop-out rates - High repetition rate - High illiteracy rate - An insufficient number of adequate learning spaces- Insufficient playgrounds for physical education in schools - Few TVET schools - Weak Parents and teachers’ association (PTA’s) | - Availability of primary, secondary and tertiary schools and facilities - Government policies and programs to increase access to high quality education - Availability of partners in education services | - Natural calamities destroying basic facilities |
| Transformational Governance |  |  |  |  |  |
|  | Governance and Decentralization | - Existence of local initiatives for public accountability | - Poor connection to ICT and electrification of administrative offices and rural area - Uncoordinated family performance contracts, - No Administrative Office for some Sectors and cells, - Insufficient staff at cell, - Weak LG Capacity development, - Insufficient budget to put in place all staff according to the LG Organization structure - Low motivation for the Village’s committees | - The district has a website which contents information on all sectors - Functioning of JADF at local government level |  |
|  | Justice, Reconciliation, Law and Order | - Presence of home-grown solutions - Increased reconciliation among population | - The quality of Customer care is poor | - Access to fair justice - Sensitization on the understanding of laws - Citizen participation has been improved |  |
|  | Sport and Culture | - Good Weather - Existence of Cultural sites (Ibyiwacu cultural center, Kabuhanga, | - Inexistence of Private investors in Sport and Culture | - Mass sport twice in a month - Existence of Cultural dance troupes - Existence of Talent detection centres Availability of quality Sport facilities (Ubworoherane Stadium, CAVEM stadium, Nyakinama Stadium) | - Natural calamities |
|  | Public Finance management | - Some mineral deposits offer the possibility for developing diverse revenue streams. | - Dishonest Taxable activities | - Safety in the country - Cross-border transactions that can generate additional revenues and create more jobs - High capacity to diversify its revenue base - Use of ICT in Public Financial Management |  |

## Stakeholder analysis

This Strategic Development of Musanze District to be achieved will need an effective collaboration with different stakeholders and partners at all levels, including central government ministries and agencies, private sector and civil society.

The following table provides detailed information on potential and active stakeholders in Musanze District and their respective responsibilities.

Table 5: Stakeholder Analysis

|  | Stakeholder | Intervention sector | Geographic area | Responsibilities |
| --- | --- | --- | --- | --- |
| 1 | MINAGRI | Agriculture | All sectors | - Is a key partner for LODA in promoting agricultural potentialities |
|  | RAB |  |  | - Developing agriculture and animal husbandry through their reform and using modern methods in crop and animal production, research, agricultural extension, education and training of farmers in new technologies |
|  | NAEB |  |  | - Support the elaboration of policies and strategies for agricultural and livestock export product |
| 2 | RDB | Private Sector | All sectors | - Responsible for supporting private investment and business development |
|  | Musanze Employment Service Center (MESC) |  | Muhoza Sector | - Strong partnership and employment opportunities with various companies/institutions created and strengthened |
| 3 | MININFRA | Transport |  | - Transport sector will have to implement some of the projects within this DDS |
|  | RTDA |  | All sectors | - Provide technical and financial support in the construction, rehabilitation and maintenance of transport infrastructure and services |
|  | RFTC |  |  | - Increase the use of public transport services through the provision of customer-focused, safety and cost-effective passenger transport services using modern vehicles recommended in public transport policy. |
| 4 | MININFRA | Energy | All Sectors | - Energy sector will have to implement some of the projects within this DDS |
|  | EUCL/REG |  |  | - Promote sustainable energy use, as well as facilitating the building of energy and construction, rehabilitation and maintenance of energy infrastructure |
|  | MOBISOL |  | Muhoza Sector | - Provide and connect Solar energy to people |
|  | BBOX |  |  |  |
|  | ZOLA ENERGY |  |  |  |
|  | AQUAVIRUNGA |  |  | - Water Supply, treatment and Connection from Mutera Source in Rubavu, Nyabihu and Musanze Districts |
| 5 | MININFRA | Water and Sanitation |  | - WATSAN sector will have to implement some of the projects within this DDS |
|  | WASAC |  |  | - Ensuring access to clean water and adequate sanitation |
|  | MoE |  |  | - Work closely with the district in the protection of mines through tree planting, digging ditches and putting all miners into mining cooperatives - Supports districts for the overall enforcement of the environmental policies, strategies and laws that are implemented at the district level including greening components |
| 6 | MININFRA, RHA | Urbanization and Rural settlement | All sectors | - Design policies and implementation framework for Urban development |
|  | WORLD BANK |  | All sectors | - Financing urban and rural development projects to promote local economic development |
|  | REMA |  | All sectors | - Monitor energy and environment sector projects compliance to environmental standards |
| 7 | MINICT | ICT | All sectors | - Design policies and implementation framework for ICT - Work closely with the district through encouraging an IT adoption at an early stage among the students |
| 8 | REMA | Environment and Natural resources | All sectors | - Ensuring environmental respect to during resources exploitation especially in mining subsector, discharge of regulations and environmental impact assessment of environment and energy sectors projects. |
|  | MoE |  |  |  |
|  | MINILAF |  |  |  |
|  | GGGI |  | Urban Area | - Provision of technical capacity in the efficient use and value addition to natural resources - Resource mobilization for environmental management projects |
| 9 | MINICOM | Financial | All sectors | - Design policies and implementation framework for trade - Facilitation of access to finance |
|  | BNR and Banks |  |  |  |
|  | Umurenge SACCO |  |  |  |
| 10 | VUP | Social Protection | All sectors |  |
|  | MINALOC |  |  | - Ensure that all sectorial and fiscal functions are fully disseminated to the district |
|  | Compassion International, Protestant Churches, Croix Rouge Rwanda, Caritas |  |  | - Support vulnerable children from poorest families - Assistance and reintegration of families from war and disasters - Socio-economic promotion for vulnerable families |
| 11 | MoH | Health | All sectors | - Design the national health policy and strategy, - Responsible for budgeting and resource mobilization, - Develop institutional and legal frameworks as well as overall health sector performance monitoring - Human resource capacity building |
|  | World Vision, Caritas, USAID, MSH,…. |  |  | - Support poor and Vulnerable families and children to access health services - Strengthening health system activities in all health centers and hospitals - HIV counseling and testing, condom education and distribution - Provide Support in nutrition and health facilities for patients in hospital |
| 12 | MINEDUC, REB, UR, WDA | Education | All sectors | - Responsible for policy formulation, educational planning, coordination, monitoring and evaluation and regulation through setting norms and standards for the education sector. |
|  | RHENANIE PALATINAT |  |  | - Support in providing infrastructures for education facilities |
| 13 | MINALOC, RALGA, RGB, MAJ | Governance and Decentralization | All sectors | - Reinforcing the functioning of District Clusters - Enhance capacities of local administration entities and performance |
| 14 | MINIJUSTE, MINALOC, ITORERO, CLADO, UUR | Justice, reconciliation, Law and order | All sectors | - Streamline legal aid provision, Prevent and combat corruption in public services |
|  | CNLG |  |  | - Fight against genocide ideology in the District - Promote unity and reconciliation |
| 15 | MINISPOC | Sport and Culture | All sectors | - Design policy framework for sports and culture |
| 16 | MINECOFIN | Public Finance Management | All sectors | - Responsible for resource mobilization and allocation for public investments, planning and coordinating economic activities across sector Ministries and more recently, ensuring population issues are integrated into sector priority setting |
|  | RRA |  |  | - Increase District revenue capacity |
|  | NGARI |  |  | - Local Revenues collection |

# Chapter 3: Alignment with national policy framework and methodology

## Methodology

The elaboration of District Development Strategy was conducted through a highly participatory and consultative process involving the citizens, central and decentralized institutions, and all development partners (public, non-public, national and international including civil society and the Private Sector).  Also, we conducted workshops and trainings to collect more statistical data during the preparation of this strategy. Normally, we used the primary data and secondary data for collecting statistical data.

Primary data

Primary data of DDS elaboration was collected through a highly participatory and consultative process involving the citizens, and all district development partners (public, non-public, national and international including civil society and the Private Sector)

### - Citizen and stakeholders Engagement

As citizens are at the centre stage of the elaboration process for the district development strategy through provision of ideas and priorities, identification of priorities was guided by principle of participation in elaboration and ownership of the DDS by citizen and district stakeholders.

District priorities were identified from both partners and stakeholders, through community assemblies, and Joint Action Development Forum (JADF), District priorities include specific needs as expressed by the local population were formulated by ensuring what are solicited to shape the future Rwandans want in the long and medium term

### - Interview

Some interviews with District stakeholders were also conducted and helped to collect some information on the future vision of the district during the next six years. Conducted interviews included open interviews with district stakeholders be it from the development partners, private sector, civil society, and District officials

Secondary data

### - Desk review

Secondary data have been collected through a largely desk review to understand the district achievements and challenges during the last five years. Key sources of data identified were the Integrated Households Living Conditions (EICV4) and Demographic and Health Survey (DHS5) and Musanze District Profile. Data from the EDPRS2 assessment report as well as self-evaluation reports on District Development Plan, District Performance Contract and District Annual Reports constituted an important source of information for the elaboration of this District Development Strategy.  The elaboration Process comprised also the analysis of existing development policies, strategies, plans and related progress reports to ensure DDS alignment to National priorities.

Relevant documents reviewed during this elaboration include:

- Rwanda Vision 2020 and Vision 2050

- Sustainable Development Goals (SDGs)

- The African Union Agenda 2063 and its First 10-Year Implementation Plan

- The East African Community (EAC) Vision 2050

- Economic Development and Poverty Reduction Strategy (EDPRS 2)

- The Draft 7Years Government Program/National Strategy for Transformation (NST1)

- Sector Strategic Plans (SSPs)

- Green Growth and Climate Resilient Strategy (GGCRS)

- Detailed Implementation Plan for the Nationally Determined Contributions (NDCs) of Rwanda

- Musanze Local Economic Development Potentialities (LED)

- Sectorial Policies and Strategies, Laws and regulations

- National Statistical and Thematic Surveys, especially the 4th PHC, EICV4& DHS 5 series and district profiles

- National Roadmap for Green Secondary cities Development in Rwanda

- Musanze DDP 2013-2018

- Revised Fiscal and Financial Decentralization Policy;

- Musanze District Profile

- Cross Cutting Areas Guidance Note

### - Consultation meetings

All priorities from villages were consolidated at District level through a consultation workshop with sector and cell leaders, planners, Council members, JDAF and other Key Stakeholders following NST1 guidelines for an effective alignment. District priorities were grouped under three Pillars of NST1. (Economic Transformation, Social Transformation and Transformational Governance).

  - Alignment to NST1

A new seven year plan is required for the direction of the government to cover the period from 2018 to 2024 as EDPRS2 and its associated Sector Strategic Plans (SSPs) and District Development Plan (DDPs) will end in 2018. NST1 is the implementation instrument for the remainder of Vision 2020 and for the first four years of vision 2050 and it will integrate long-range global and regional commitments. To ensure that Musanze District contributes towards three pillars considered in NST1 (economic, social and transformational governance), it is crucial for the DDS to align with the NST1.

Musanze DDS has considered all the specific objectives to accelerate inclusive economic growth and development, built on the Private Sector, knowledge, technical skills and Natural Resources namely by creating decent jobs for economic development and poverty reduction, accelerate Urbanization to boost economic growth; promote industrial development, export promotion and expansion of trade related infrastructure; develop and promote a service-led and knowledge-based economy; increase agriculture and livestock quality, productivity and production; and sustainably exploit natural resources and protect the environment.

With regard to social transformation, Musanze DDS has considered particular objectives like moving towards a Poverty Free Rwanda; ensuring a quality and healthy population, developing a competitive and capable Rwandan population, ensuring quality of education for all with an aim to build a knowledge-based economy; and enable transition to a modern Rwandan household in urban and rural areas to develop Rwandans into a capable and skilled people with quality standards of living and a stable and secure society.

Musanze DDS has also considered the following specific objectives to support the transformation governance; consolidate values and unity of Rwandans, committed to a self-reliant and peaceful Rwanda, strengthen partnerships between government, private sector, citizen and non-state actors to fast track national development and people-centered prosperity; strengthen capable and responsible public institutions committed to citizens advancement and efficient service delivery; strengthen capacity of security institutions/organs to preserve national security and protect Rwandans, as well as actively participate in socio economic development of the nation.

Table 6: DDS Alignment to NST1

| NST-1 Pillar | NST-1 Priority Area | NST-1 Outcome | Musanze DDS Outputs | Musanze DDS Strategic Interventions |
| --- | --- | --- | --- | --- |
| 1. Economic Transformation |  |  |  |  |
| 1.1 Create 1.5m (over 214,000 annually) decent and productive jobs for economic development |  | 1.1.1: Increased number of Rwandans with appropriate skills tailored to labour market demands | Enabling environment for the growth of entrepreneurship created | - Construct industrial zone - Construct Agakiriro - Construct selling points along main road constructed - Construct hydropower - Construct modern markets - Create new model SMSs - Business centres creation and rehabilitation - Heavy trucks park construction - Warehouses construction - Slaughterhouse construction |
|  |  |  | Employment promoted through skills development, entrepreneurship and regulation | - Increase number of TVETs - Strengthen partnership between TVET schools and Private Sector - Increase head teachers and TVET school managers accessing relevant leadership and management course |
|  |  |  | Private and public institution mobilized to offer workplace learning | - Mobilize Private and Public institutions to offer workplace learning |
|  |  | 1.1.2: Increased productive jobs for youth and women | Entrepreneurs (youth and women) accessed to finance | - Mobilization of youth and women for entrepreneurship to enhance through meetings - Mobilization of youth and women for access to finance through BDF and SACCO - To promote cross-border trade - Mobilization of PWD to enhance entrepreneurship and access to finance |
|  |  |  | Talented cyclist and athletes increased | - Development of Talent Detection Centres and creation of the teams. |
|  |  |  | Business financed through BDF and SACCOs | - Financing Business Proposals through BDF and SACCOs |
|  |  |  | Business promoted for women and youth | - Support Youth and Women cooperatives to start operational business |
| 1.2Accelerate Sustainable Urbanization from 17.3% (2013/14) to 35% by 2024 |  | 1.2.1: Developed and integrated urban and rural settlements | Existing major roads provided with street lighting | - Increasing Public Lighting in Musanze Town and rural streets |
|  |  |  | Public transportation within the District Enhanced | - Increase of dedicated bus lines, bus stops and bus terminals |
|  |  |  | Junctions improved to reduce traffic congestion | - Construction of round-about in Musanze City |
|  |  |  | Road networks within the District improved | - Construction of new asphalt roads - Maintenance of feeder roads - Maintenance of Roads by local communities - Construction of pedestrian ways along main roads in Musanze town - Construction of bicycle lanes - Construction of bridges - Construction of rainwater channels/drainages |
|  |  |  | Green urban, rural development plans and detailed physical plans developed | - Update Musanze Master Plan - Develop urban Land use Plans - Develop and finalize all layout plans - Review and Update Local Urban Development plans in the emerging Centres - Settlements viability - Upgrade informal settlements |
|  |  | 1.2.2. Increased economic opportunities in urban areas | Flagship projects developed in Musanze Secondary City | - Establish factory to exploit and process volcanic stones - Develop cement factory - Construct Helipad in Kinigi Sector - Construct Vehicle Assembly Plant - Develop Modern Brick Kilns - Develop Ceramic Industries - Construction of Drinking water treatment Plant (sparkling water) - Establish Building material technology centre - Develop Irish Potato Starch (amidon) factory - Develop trees to modern materials - Construction of Gymnasium - Youth friendly centres construction |
|  |  | 1.2.3. Increased availability of affordable housing | Affordable and social housing developed | - Provide basic infrastructure in new areas for residential housing through PPP - Construct real estates and affordable housing with 40% of green space |
|  |  |  | Current informal settlements are upgraded | - Upgrade informal settlements |
| 1.3 Establish Rwanda as a Globally Competitive Knowledge-based Economy |  | 1.3.2: Developed anchor firms and entrepreneurs in priority value chains and new sectors | Ensure digital literacy for all youth | - Increase the literacy level at 100% through sensitizing the dropouts to join the TVET school |
|  |  |  | Increase of broadband coverage up to 47% of all citizens | - increase in smart devices penetration |
|  |  | 1.3.3: Increased business development services for entrepreneurs | Business development center facilities established | - Promote Backbone Services, and Priority Service Sector VCs - Promote Technology, Innovation, Standards and High-Growth Entrepreneurship |
|  |  |  | High ICT quality skills leveraging knowledge developed | - Enhance quality of knowledge in ICT |
|  |  | Enabling platforms developed for productivity | MV electrical line and water pipe extended, and 1 ha of lorry parking space constructed to serve the industrial park | - MV and LV making |
|  |  | Export growth sustained at 17% annually | Establish Agro-processing plants trough PPP | - Establish Agro-processing plants trough PPP |
| 1.4 Promote Industrialization and attain a Structural Shift in the export base to High-value goods and services with the aim of growing exports by 17% annually |  | 1.4.3: Upgraded minerals, oil & gas sector | Value addition for minerals and quarry products increased | - Link existing mining cooperatives with financial institutions and potential investors to increase production for district economic development - Afforestation of exploited mining sites - Add value to minerals for export |
|  |  |  | Mines and quarries sustainably exploited | - Protection of mines and quarry sites. - Enforce the policy on exploitation of mines and quarries |
|  |  | 1.4.2: Increased and improved tourist destinations and hospitality | Projects developed for improving tourist destination and hospitality | - Develop twin lakes - Creation of artificial tourist sites - Create and develop camping sites - Construct International and upgrade local stadiums - Implement Feasibility study for tourism - Creation of District traditional dance groups - Diversify attractions and entertainment poles for tourism purpose |
|  |  | Increased exports of value-added goods | Agro-processing plants for meat, maize, leather, milk constructed and operationalized | - Construction of agro-processing plant |
|  |  |  | Handcraft cooperatives established and operationalized | - Establish Handcraft cooperatives |
| 1.5 Increase Domestic Savings and position Rwanda as a hub for financial services to promote investments |  | 1.5.2: Enhanced long-term savings and innovative financing mechanisms | People with access to innovative finance and saving increased | - Promote and support innovative mechanisms for financing - Support MSMEs through BDCs to develop projects that are financially viable and support them to acquire finance from financial institutions - Sensitise SMEs on other source of financing opportunities including capital market - Mobilize the financially excluded Rwandans to join financial institutions through financial education and literacy programs - Mobilise Rwandans to join the Long- term Savings Scheme - Enhance the good governance and performance of financial institutions in district - Support the linkage of VSLAs (existing and new ones) to formal financial institutions through access to finance forums - To mobilise people to save through capital market products and bonds and other saving instruments - Enhance agriculture financing through mobilising farmers to acquire agriculture insurance premium |
|  |  |  | Umurenge SACCOs automated | - Promote the automation of U- SACCOs, Establishment of the District SACCO |
|  |  |  | Saving and access to agriculture credit by women and men Increased | - Adults using financial services |
|  |  |  | Cashless economy and electronic payments promoted | - Conduct awareness campaigns on electronic payments |
| 1.6 Modernize and increase productivity and livestock |  | 1.6.1: Increased agricultural production and productivity | Productivity increased, and resilience strengthened | - Increase crops on consolidated land |
|  |  |  | Use of Fertilizer (organic manure and chemical) and use improved seeds increased | - Distribute and use mineral and chemical fertilizers - Increase the use of improved seeds |
|  |  |  | Effective and efficient irrigation developed under an IWRM framework | - Mechanization in farm operations - Irrigation of hillside - Supply and use motor pumps in small scale irrigation |
|  |  |  | Soil conservation, climate smart agriculture | - Construct and operate green houses |
|  |  |  | Enhanced food security and nutrition | - Construction of new store houses and operationalize drying facilities - Increase quantity of milk produced per day - Enhance new technology in Irish Potatoes storage (cold-room) |
|  |  |  | Ha of land consolidated under CIP for maize, Irish Potatoes, Wheat and Beans. | - Average yields of priority crops on Consolidated land |
|  |  |  | Enhanced and production in horticulture, vegetables fruits increased | - Increase flowers and vegetables production - Intensification of passion fruits - Intensification of banana plantation - Establish banana processing factories for making banana Juice and wine - Establishments of permanent fruits nurseries - Construct and equip juice and jam factory - Strengthen cooperatives capacity to add value to their products to excel in export opportunities - Strengthen professional traders investing in formal cross border trade |
|  |  | 1.6.2.I ncreased traditional and non-traditional export crops | Production of traditional export crops increased | - Construction of pyrethrum dryer - Increase production of pyrethrum |
|  |  | 1.6.4. Enabled environment and responsive institutions | Capacity building of farmers improved | - Reinforce training centres for farmers |
|  |  | 1.6.5 Improved livestock sector | Private investment in agri-business mobilized | - Organization and training of cooperatives and farmers in pig production and processing techniques - Intensification of poultry farming |
|  |  |  | Animal Products produced | - Increase quantity of milk production - Increase fish production - Increase honey production |
|  |  |  | Large and small livestock increased especially within poorest families increased | - Distribute cattle (Girinlka) and small livestock to poor families. |
|  |  |  | Animal diseases prevented and controlled | - Vaccinate cows and other domestic animals - Increase improved veterinary pharmacies - Increase veterinary clinics |
|  |  |  | Animal feeding ensured, and domestication improved | - Increase improved animal feed processing plants |
|  |  |  | animal products produced | - Increase the fish production - Increase honey production - Increase improved pigs race |
|  |  |  | 1 modern slaughterhouse constructed and operationalized | - Construction and operationalization of modern slaughterhouse |
| 1.7 Sustainable Management of Natural Resources and Environment to Transition Rwanda towards a Carbon Neutral Economy |  | 1.7.1:Increased sustainability and profitability of forestry management | Improved land use administration and management for optimal allocation | - Rehabilitation of Forestry - Planting Agroforestry - Sensitization of forest owners for proper management of forests and efficient use of forest products - Increase the area of private forests converted into productive forests and managed by forests owners’ associations - Increase the area of public forests allocated to private operator. |
|  |  | 1.7.3: Integrated water resource management | Managed water flows from volcanoes and improve water resource management | - Protection of land slide caused by water from VNP - Protect river banks (Mukungwa river, Rwebeya, Susa, Muhe and Cyuve ravines) - Construct erosion control ditches |
|  |  | 1.7.4: Accelerated growth in Green Innovation | Reduced Number of households depending on firewood as a source of energy for cooking | - Mobilize people and public institutions to use biogas and cooking gas. |
|  |  |  |  | - Mobilize Community on renewable/solar energy usage |
|  |  |  | Rainwater management improved | - Installation of rainwater harvesting facilities |
|  |  | Increased sustainability of land use system | Land covered by radical and progressive terraces increased | - Increase land area covered by radical terraces and plant agroforestry trees - Increase land area covered by progressive terraces and plant agro-forestry trees - Protection and maintenance of marshland |
| 2. Social Transformation |  |  |  |  |
| 2.1 Enhancing graduation from extreme Poverty and promoting resilience |  | 2.1.1 Increased graduation from Extreme poverty | Increased social protection coverage of extremely poor households | - VUP expanded public work for women headed HHs and PWD - Support poverty family through Girinka Program - Support poor families through small livestock (goats, pigs, poultry) - Strengthening the capacity building through training District officers on how to best target and support vulnerable people |
|  |  |  | Provision of Social Care Services and sensitization for the most vulnerable people strengthened | - Provision of Social Care Services - Sensitization of the most vulnerable people |
|  |  | Reduced poverty among Rwandans | Houses to homeless provided in planned settlement | - Construction of Houses for Homeless and support them with small projects. |
|  |  |  | Houses for vulnerable genocide survivors reconstructed and rehabilitated | - Construction Houses for vulnerable genocide survivors - Rehabilitate Houses for vulnerable genocide survivors - Monitor and Evaluate the vulnerable genocide survivors life conditions |
|  |  | Enhanced resilience of Rwandans | CBOs and NGOs engaged in social protection strengthened and increased | - Facilitate the engagement of CBO and NGOs in social protection |
|  |  |  | Capacity for disaster risk reduction and social economic | - Organize a disaster risk capacity building management and social economic transformation |
|  |  |  | Social protection beneficiaries sensitized on the culture of self-reliance and savings | - Organize capacity building sessions on the culture of self-reliance and savings |
| 2.2 Eradicating Malnutrition |  | 2.2.1 Reduced malnutrition among children | Village based ECD used as an entry point for education/provision of health services | - Mobilize people to invest in ECDs - Organize capacity building sessions on the culture of self-reliance and savings - Mobilize campaign for nutritional education to attend ECDs / Quarter |
|  |  |  | Knowledge on good nutrition practices increased | - Introduce nutrition counselling (including peer learning) sessions |
|  |  |  | Provision of FBF and milk for affected children continued | - 100% of eligible under two years received FBF - Maintain provision of 1 cup of milk program for affected children |
| 2.3 Enhancing demographic dividend through ensuring access to quality Health for all |  | 2.3.1 Improved healthcare services | Human resources for health increased | - Increase the number of doctors at health centres - Increase the number of specialists at District hospital and Ruhengeri referral hospital - Increase the number of Midwives at health centres - Ensure capacity building of medical staff in hospital, health centres, and health posts |
|  |  |  | Community health Enhanced | - Raise awareness on reproductive health and increase contraceptive prevalence - Increase the number of women (15-49 age) using family planning methods - Equip maternity wards with adequate equipment - Reduce the under 5 years mortality rate - Increase quality in ANC Services |
|  |  |  | Healthcare workers enabled to use ICT and Equip healthcare facilities with electronic medical records | Organize Training sessions for health workers and Equip Healthcare Facilities |
|  |  |  | Health facilities constructed and upgraded by ensuring access to electricity and water for health facilities | - Construction of health post at cell level and increase the number of health centres - Upgrading of Ruhengeri District hospital - Feasibility study of construction, Rehabilitation and extension of health infrastructures - Feasibility study of constructing District Hospital (Oscillatory) in Muhoza Sector |
|  |  |  | Access to electricity and water for health facilities ensured | - Connection of all HCs and HP to water and electricity |
|  |  | 2.3.2 Increased financial sustainability for the health sector | Ensured coverage of health insurance scheme to 100% | - Sensitize and support the population to acquire health insurance and train CBHI committees |
|  |  | 2.3.3 Increased health of workforce | Improved quality and increased quantity of health workforce | - Advocating for investment in clinical and health educational opportunities |
|  |  | 2.3.4 Reduced Communicable and non-communicable diseases (NCDs) | Disease prevention awareness | - NCDs prevention awareness creation through community mobilizations - HIV community mobilization for testing and prevention |
|  |  | 2.3.5 Increased contraceptives prevalence | Use of FB Strengthened | - Integrate Postpartum FP (PPFP) into ANC and maternity and PNC services - Encourage male engagement in the use of FP services - Promote the multi-sectoral and stakeholder’s collaboration to improve the demand and delivery of FP services |
| 2.4 Enhancing demographic dividend through improved access to quality education |  | 2.4.1 Increased access to pre-primary education | All children completed pre-primary programme before entering Primary Education | - Provide standardized ECE schools - Extend ECDs at cell level - Put in place PPP models for ECE and ECDs |
|  |  | 2.4.2 Improved education quality in primary and secondary education | Increased access to quality education up to secondary level | - Construct New Schools (Classrooms) - Organize Continuous Professional development for teachers - Strengthening Umwalimu SACCO - Provide affordable houses to teachers - Increase number of Science Laboratories - Introduce STEM (Science, Technology, engineering and Mathematics) research centres |
|  |  | 2.4.3 Increased Technical and Vocational Education and Training (TVET) schools and graduates | Increase access to adult basic education | - Ensure that each sector has a TVET - Strengthen STEM in TVET training |
|  |  | 2.4.4 Enhanced quality of higher education system | Barriers to education completion rates especially primary and secondary avoided | - Introduce education councillors (Abajyanama b’uburezi) at cell level |
|  |  | 2.4.5 Increased adult literacy rates | Improve adult literacy and numeracy | - Increase the literacy level at 100% through sensitizing those who dropped out to join the TVET school |
|  |  |  | Increased participation and achievement of learners with disabilities at all levels | - Avail suitable special needs education materials in schools - Build the capacity of teachers in favour of disabled children - Ensure accessibility of infrastructure |
| 2.5 Moving towards a Modern Rwandan Household |  | 2.5.1 Universal access to infrastructure (water, sanitation, electricity, ICT, shelter) | Households connected to grid and off-grid solutions | - Support to rural electrification |
|  |  |  | Ensure 100% access to clean water | - Feasibility study of extending water supply system - Detailed study of rehabilitation and extension of water supply system - Identification of water sources |
|  |  |  | Increased access to sanitation facilities | - Implement District Sanitation Master Plan - Construct public toilets - Encourage PPPs in construction of Public Toilets in Public Places |
|  |  |  | Improved management of Solid waste | - Develop Integrated Solid Waste Management (lEg: landfill) - Inspection of Companies dealing with waste collection - Sensitize the population on waste management |
|  |  |  | Recycling of Waste water ensured | - Construct Semi centralized sewerage systems - Construct Faecal Sludge treatment plants - Construct waste treatment plant - Secondary stormy water drainage networks constructed - Stormwater drainages constructed |
|  |  |  |  | - Construct IDP model villages |
|  |  |  | Promote recreational, sports and culture activities | - Develop public green open spaces - Organize Mass sport activities |
| 3. Transformational Governance |  |  |  |  |
| 3.1 Reinforce Rwandan culture and values as a foundation for peace and unity |  | 3.1.1: Enhanced unity among Rwandans | Kinyarwanda Language and Rwandan values preserved especially among the youth | - Reinforce values and culture of excellence and patriotism - Reinforce “Ndi Umunyarwanda” program - Reinforce Unity clubs at village level |
|  |  |  | Fight against genocide ideology intensified | - Strengthen conservation and preservation of proofs of the Genocide against Tutsis |
|  |  |  |  | - Construct Standard Memorial Site |
|  |  |  | Awareness campaign on the culture of problem solving conducted | - Conduct awareness campaign on the culture of problem solving through cell committees, Inshuti z’Umuryango and Umugoroba w’ababyeyi |
|  |  |  | Itorero program strengthened in Schools and Villages | - Operationalize and monitor Itorero in all villages and schools - Conduct impact assessment of Itorero Program - Conduct awareness and mobilization campaign of the youth to participate in National Service/Urugerero |
|  |  | Increased innovations and sustainability across Home Grown Solutions | Unity and reconciliation mechanisms of Rwandans strengthened | - Create unity and reconciliation clubs |
|  |  |  | Programmes for Home grown solutions enhanced and sustained | - Availing and operationalize programmes of Inteko y’Abaturage - Availing and operationalize programmes of Abunzi - Availing and operationalize programmes of Umugoroba w’ababyeyi (Parents’ evening program) - Availing and operationalize programmes of Umuganura - Availing and operationalize programmes of Umuganda |
| 3.2 Ensure Safety and Security of citizens & property |  | Enhanced Peace and Security | Community policing strengthened, and security organs Strengthened | - Strengthen Night Patrol - Urugerero Program at District - Security meeting at all levels |
|  |  |  | Strengthen crime prevention | - Organize drug abuse fighting awareness campaigns - Organize awareness campaign in order to enhance crime prevention among population - Construct rehabilitation centres |
|  |  |  | Checking alarm and camera system to prevent cross-border crimes | - Security camera installed in Musanze City |
| 3.4 Strengthen Justice, Law and Order |  | 3.4.2: Sustained respect for human rights and civil liberties | Deepened awareness and respected human rights by implementing the national human rights action plan | - Train ABUNZI in order to inform their legal knowledge - Put in place Abunzi Management Information System - Decentralize MAJ up to the sector Level |
|  |  | 3.4.3: Zero corruption across government services and institutions achieved and maintained | Mechanism to fight against corruption at all levels | - Create and train anti-corruption clubs - Organize awareness campaign to fight against Corruption |
| 3.5 Strengthen Capacity, Service delivery and Accountability of public institutions |  | 3.5.1: Enhanced accountability across public institutions |  | - Engage and develop capacity for JADF members - Organize public accountability days |
|  |  | 3.5.3: Reinforced efficient service delivery | Online service delivery reinforced | - Increase online service delivery |
|  |  |  | Constructed and maintained government assets that support the national economy Increased JADF participation in District development, democratic governance and citizens’ welfare | - Rehabilitation of Musanze District Office - Construction and rehabilitation of all Sectors - Construction and rehabilitation of all cells - Construction and rehabilitation of all villages - Engage and develop capacity for JADF members - Organize public accountability days |
|  |  | 3.5.4: Enhanced effective Public Financial Management System | Improved and increased district revenue | - Reinforcing tax collection system including inventory of taxable District assets and taxpayers - Mobilization of sectors to increase revenues collected at their levels - Strengthen the technical capacity of districts to prioritize budget allocations to important socio- economic development programs through trainings |
|  |  |  | Increased the Implementation of Auditors’ recommendation | - Implement Audits’ recommendations - Continuous training for all staff to achieve clean audit |
| 3.6 Increased Citizens Participation and Engagement in Development activites |  | Developed Capacity for Civil Society and the Media | Home grown solution of mediators to solve problems | - Promote community work and community assembly - Engage the citizen at village level in participatory planning/prioritization as well as budgeting - Strengthen the national youth Council and National Women Council at district and sector levels |
|  |  | Enhanced decentralisation system | Partnership in planning, monitoring and evaluation of District partners’ activities Reinforced Participative planning sessions with all District stakeholders organized | - Engage the citizen at village level in participatory planning/prioritization as well as budgeting - Involving District stakeholders into planning sessions and M&E activities of the District |
|  |  |  | Mediators, community works, Ubudehe, Inteko z’abaturage and other homegrown solution initiatives promoted | - Training Mediators - Promoting value added from community works program |

# Chapter 4: Strategic Framework

After analysing the current situation of Musanze District, its achievements and challenges, this chapter forms the core part of Musanze District development strategy since it presents the priorities and innovations proposed and strategies/interventions to ensure that these priorities are realized. Considering that this DDS is elaborated in line with NST1 which strongly focuses on emerging priorities of economic, social transformation and transformational governance; this DDS contributes to these emerging priorities as well as it mainstreams the crosscutting areas.

## The District Vision, Mission and Objectives

Vision

The vision of Musanze District in the next six years was formulated as

“ Musanze as an excellent centre of Tourism Industry”

Mission

The District Mission is embodied in the following goals to support the vision achievement:

Goal 1: “Improve attractive Tourist Sites”

Goal 2: “Promote sustainable Agro processing”

Goal 3: “Promote sustainable Basic infrastructure”

Objectives

With available resources aligned under each defined goal. Formulated objectives are;

- Objective 1: In the next six years, Musanze District will identify seven new tourist sites;

- Objective 2: In the next six years, Musanze District will put in place new Tourism facilities by 50%;

- Objective 3:  In the next six years, Musanze District will increase by 70% its Local Revenues from 40 %;

- Objective 4: In the next six years, Musanze District will increase food security by 70% from 49%;

- Objective 5:  In the next six years, Musanze District will extend basic infrastructure by 50 % from 27%;

- Objective 6: In the next six years, Musanze District will facilitate accessibility to clean water by 100% from 89.5%;

- Objective 7: In the next six years, the District will promote exportations through transformation by 60% from 17%;

- Objective 8: In the next six years, the District will facilitate the creation of new off farm jobs;

## Main Priorities at District level

Figure 9: Economic Transformation

Create enabling environment for the growth of entrepreneurship and Develop PPPs mechanism to mobilize private investments

Employment promotion through skills development, entrepreneurship and regulation

Increase entrepreneurs (youth, women) access to finance.

Developing and producing an increased number of talented cyclist and athletes

Job creation

Provide existing major roads with street lighting

Enhance public transportation within the District

Reduce Traffic Congestion through improvement of junctions

Improve road networks within the District

Development of green urban and rural development plans and detailed physical plans

Develop Flagship projects in Musanze city

Development of affordable estates and social housing

Promote urbanization

Increase value addition for minerals and quarry products

Sustainable exploitation of mines and quarries

Increase and improve touristic destinations and hospitality

Industrialization

Increase the average productivity

Enhance and facilitate access to improved seeds and fertilizers and increase production in horticulture, vegetables, fruits

Increase value addition upgrading of traditional and non-traditional export crops

Ensure sustainable land management

Mobilization of private investment in agri-business

Modernize and increase agricultural productivity and livestock

Improve land use administration and management for optimal allocation and use of land

Manage water flows from volcanoes and improve water resource management

Reduce number of households depending on firewood as a source of energy for cooking

Reinforce the policy on rain water harvesting system

Sustainable Management of Natural Resources and Environment

Priorities

the abovementioned objectives, an overview of the main priorities are to be outlined in this section.

Length: max. 1 page

The DDS of Musanze will focus on the potentialities from the unfinished opportunities for job creation, accelerate Sustainable urbanization, develop and promote industrialization, the district will focus also efforts in improving agricultural productivity the efficiency of livestock.

Figure 10: Social Transformation

Increase social protection coverage of extremely poor households

Provision of small live stock to the poorest

Graduation from extreme poverty and resilience

Use village based ECD as an entry point for education/provision of health services

To increase knowledge on good nutrition practices

Continue provision of FBF and milk for affected children

Eradicate malnutrition

Increase workforce in the health sector

Enhance the community health

Construct and upgrade, Health facilities by ensuring access to electricity and water for health facilities by 2024

Disease prevention awareness

Access to good quality health services and facilities

Ensure all children (boys and girls) complete pre-primary programme before entering Primary Education

Increase access to quality education up to secondary level

Increase access to adult basic education

Avoid barriers to education completion rates especially primary and secondary

Improve adult literacy and numeracy

Increase participation and achievement of learners with disabilities at all levels

Access to good quality education

Connect households to on and off-grid solutions

Ensure 100% access to clean water

Increase access to sanitation facilities

Ensure the recycling of Waste water

Modern Rwandan households

Priorities

Figure 11: Transformational governance

Promote and Preserve Kinyawanda Language and Rwandan values especially among the youth

Institutionalization of “Ndi Umunyarwanda and Abarinzi b’Igihango” programmes in Local government

Intensify fight against genocide ideology

Awareness campaign on the culture of problem solving conducted

Values, home grown solutions and innovations streamlined into all institutions for transformational governance

Reinforcing Rwandan Culture

Strengthen community policing and support security organs

Strengthen crime prevention

Safety and security

Deepen awareness and respect human rights by implementing the national human rights action plan

Mechanism to fight against corruption at all levels

Strengthen Justice, Law and order

Enhance capacity of individuals and institutions to attain the required level of professionalism

Reinforce online service delivery

Construction of public buildings and maintenance of government assets that support the national economy

Greater use of new technologies and communication in enhancing sports and recreation experience

Capacity, Service delivery and Accountability of public institutions

Improve implementation and monitoring of sectorial decentralization process

Home-grown solution of mediators to solve problems

Increase citizens’ participation, engagement and partnerships in development

Priorities

## Results Chain

The result chain for the Musanze DDS is presented below and it is organized around three impact goals.

Figure 12: Result Chain (Impact 1)

Impact 1: Inclusive and sustainable economic development founded on the Private Sector, knowledge and Rwanda’s Natural Resources

Outcomes:

Outcome 1: Off-farm jobs created per year

Outcome 2: Increased productive jobs for youth and women

Outcome 3: Street lighting expanded to all national and district roads

Outcome 4: Improved public transport services, effective and safe traffic management

Outcome 5: Integrated human settlement planning and coordination

Outcome 6: Facilitated development of affordable and social housing and access to housing

Outcome 7: Developed anchor firms and entrepreneurs in priority value chains and new sectors

Outcome 8: Increased business development services for entrepreneurs

Outcome 9: Enabling platforms developed for productivity

Outcome 10: Export growth sustained at 17% annually

Outcome 11: Increased exports of value-added goods

Outcome 12: Vibrant, Efficient and responsible mining spurring sustainable economic development

Outcome13: Increased exports of high value services

Outcome 14: Enhanced long-term savings and innovative financing mechanisms

Outcome 17: Increased agricultural production and productivity

Outcome 18: Increased traditional and non-traditional export crops

Outcome 19: Improved livestock sector

Outcome 20: Enabled environment and responsive institutions

Outcome 21: Scale up the production of high value crops

Outcome 15: Sustainable and productive forest management ensured

Outcome 16: Integrated water resource management

Outputs:

Output 1: Employment promoted through skills development, entrepreneurship and regulation

Output 2: Enabling environment for the growth of entrepreneurship created

Output 3: private and public institution mobilized to offer workplace learning

Output 4: business financed through BDF and SACCOs

Output 5: business promoted for women and youth

Output 6: Talented cyclist and athletes increased

Output 7: Entrepreneurs (youth and women) accessed to finance

Output 8: Provided existing major roads with street lighting

Output 9: Public transportation within the District Enhanced

Output 10: Junctions improved to reduce traffic congestion

Output 11: Road networks within the District improved

Output 12: Green urban and rural development plans and detailed physical plans developed

Output 13: Flagship projects developed in Musanze City

Output 14: affordable and social housing developed

Output 15: current informal settlements are upgraded

Output16: Ensure digital literacy for all youth

Output 17: Increase of broadband coverage up to 47% of all citizens

Output 18: High ICT quality skills leveraging knowledge developed

Output 19: MV electrical line and water pipe extended, and 1 ha of lorry parking space constructed to serve the industrial park

Output 20: Establish Agro-processing plants trough PPP

Output 21: Agro-processing plants for meat, maize, leather, milk

Output 22: Handcraft cooperatives established and operationalized

Output 23: Value addition for minerals and quarry products increased

Output 24: mines and quarries sustainably exploited

Output 25: 6 projects developed for improving touristic destination and hospitality

Output 26: Saving and access to agriculture credit by women and men increased

Output 27: Annual awareness campaigns conducted in all sectors about online transactions

Output 28: Productivity increased and resilience strengthened

Output 29: Use of fertilizer (organic manure and chemical) and improved seeds increased

Output 30: Effective and efficient irrigation developed under an IWRM framework

Output 31: Soil conservation, climate smart agriculture

Output 32: Enhanced food security and nutrition

Output 33: Ha of land consolidated under CIP for maize, Irish Potatoes, Wheat and beans.

Output 34: Enhanced and production in horticulture, vegetables fruits increased

Output 35: Production of traditional export crops increased

Output 36: Large and small livestock especially within poorest families

Output 37: Animal diseases prevented and controlled

Output 38: Animal feeding ensured and domestication improved

Output 33: animal products produced

Output 34: 1 modern slaughterhouse constructed and operationalized

Output 35: Capacity building of farmers improved

Output 36: Increased production of cash crops

Output 37: Improved land use administration and management for optimal allocation

Output 38: Managed water flows from volcanoes and improve water resource management

Output 38: Land weeks conducted

Output 39: Land covered by radical and progressive terraces increased

Activities:

- Increase number of TVETs

- Strengthen partnership between TVET schools and Private Sector

- Increase head teachers and TVET school managers accessing relevant leadership and management course

- Construct industrial zone

- Construct Agakiriro

- Construct Celling points along main road

- Construct hydropower

- Create new model SMSs

- Mobilize Private and Public institutions to offer workplace

- Financing Business Proposals through BDF and SACCO

- Support Youth and Women cooperatives to start operational business

- Development of Talent centres

- Mobilization of youth and women to enhance entrepreneurship trough meetings

- Establish Public lighting in Musanze Town street

- Increase of dedicated bus lines, bus stops and Bus terminals

- Construction of Modern round about in Musanze City

- Construction of mini round about in Musanze City

- Construction of new asphalt roads

- Maintenance of feeder roads

- Participation of local communities in maintenance of Roads

- Construction of bicycle lanes

- Construction of bridges

- Construction of rainwater channel/drainages

- Update Musanze Master Plan

- Develop urban Land use Plans by using advanced technology

- Develop and finalize all layout plans

- Review and Update Local Urban Development plans in the emerging Centres

- Settlements viabilization

- Establish factory to exploit and process volcanic stones

- Develop cement factory

- Construct an Helipad in national volcano Park

- Construction of Heavy truck Transit centre

- Construct Vehicle assembly plant

- Develop modern brick kilns

- Develop Ceramic Industries

- Construction of Drinking water treatment Plant (sparkling water)

- Construct of Modern warehouses

- Establish Building material technology centre

- Develop Irish potato starch (amidon) factory

- Construct Oscillatory Hospital_ District Hospital

- Construction of Gymnasium

- Provide basic infrastructure in new areas for residential housing through PPP

- Construct real estates and affordable housing with 40%of green space

- Upgrade informal settlements

- Increase the literacy level at 100% through sensitizing the dropouts to join the TVET school

- Increase in smart devices penetration

- Roll out of the 4G network

- Enhance quality of knowledge in ICT

- MV and LV making

- Establish Agro-processing plants trough PPP

- Construction of agro-processing plant

- Establish Handcraft cooperatives

- Link existing mining cooperatives with financial institutions and potential investors to increase production for district economic development

n

- Afforestation of exploited mining sites

- Dissemination of mining law

- Protection of mines and quarry sites

- Enforce the policy on exploitation of mines and quarries

- Develop twin lakes

- Creation of artificial touristic sites

- Create and develop camping sites

- Construct and upgrade local stadiums

- Creation of District traditional dance groups

- Adults using financial services

- Create awareness campaigns

- Increase crops on consolidated land

- Distribute and use mineral fertilizers and chemical fertilizers

- Increase the use of improved seeds

- Supply and use moor pumps in small scale irrigation

- Construct and operate green houses

- Construction of new store houses and Operationalize drying facilities

- Increase Quantity of milk produced per day

- Promotion of Kitchen garden in community

- Increase crops on Consolidated land

- Average yields of priority crops on Consolidated land

- Increase flowers and vegetables production

- Intensification of passion fruit

- Intensification of banana

- Establish banana processing factories for making banana Juice and wine

- Establishments of permanent fruits nurseries

- Construct and Equip juice and jam factory

- Strengthen cooperatives capacity to add value to their products to excel in export opportunities

- Strengthen professional traders investing in formal cross border trade

- Construction and Operationalize of pyrethrum dryers

- Increase volumes of pyrethrum

- Construct and upgrade Irish potatoes collection centres and new store houses

- Strengthen Girinka program

- Distribute small livestock to poor families

- Vaccinate cows and other domestic animals

- Increase improved veterinary pharmacy

- Establish veterinary clinics

- Establish improved animal feed processing plants

- Increase ha of forage fields

- Increase the fish production

- Increase honey production

- Increase improved pigs race

- Construction and operationalization of modern slaughterhouse

- Training sessions organised for farmers

- Increase production of cash crop intensification

- Rehabilitation of Forestry

- Planting Agroforestry

- Sensitization of forest owners for proper management of forests and efficient use of forest products

- Increase the area of private forests converted into productive forests and managed by forests owners associations

- Planting bambous along Mukungwa river, Rwebeya, Susa, Muhe and Cyuve ravine

- Installation of public garden along Kigombe stream

- Protect Mukungwa catchment by land husbandry technics

- Construct Erosion control ditches

- Installation of rainwater harvesting facilities

- Increase conduction of land weeks

- Increase land area covered by radical terraces and plant agroforestry trees

- Mobilize Community on renewable energy  usage

Inputs

- Fund available

- Availability of youth and women;

- Human resources (Humana capacity development, Technical assistance)

- Natural resources (Construction materials, …)

Figure 13: Result Chain (Impact 1I)

Impact II:  Capable and skilled Rwandan with quality standard of living, stable and secure society

Outcomes:

Outcome 1: Productivity increased and household resilience

Outcome 2: Reduced poverty among Rwandans

Outcome 3: Enhanced resilience of Rwandans

Outcome 4: Reduced malnutrition among children

Outcome 5: Improved healthcare services

Outcome 6: Increased financial sustainability for the health sector

Outcome 7: Increased health of workforce

Outcome 8: Reduced Communicable Diseases and Non-Communicable Diseases (NCDs)

Outcome 9: Increased contraceptives prevalence

Outcome 10: Enhanced access to quality education for all

Outcome 11: Increased Technical and Vocational Education and Training (TVET) schools and graduates

Outcome 12: Enhance quality of teaching and learning at all levels of education

Outcome 13: Increased adult literacy rates

Outcome 14: Equitable opportunities to all levels of learning irrespective of gender, socio-economic or other status

Outcome 15: Household access to electricity increased to 100%

Outcome 16: Increased and sustained urban and rural households access to 100 % of safe drinking water

Outcome 17: Improved and sustained household access to basic sanitation services

Outcome 17: Improved and sustained household access to basic sanitation services

Outcome 18: Integrated and sustained Waste Management Services

Outputs:

Output 1: Increased social protection coverage of extremely poor households

Output 2: Provision of Social Care Services and sensitization for the most vulnerable people strengthened

Output 3: Houses to homeless provided in planned settlement

Output 4: Houses for vulnerable genocide survivors reconstructed and rehabilitated

Output 5: CBOs and NGOs engaged in social protection strengthened and increased

Output 6: Capacity for disaster risk reduction and social economic transformation improved

Output 7: Social protection beneficiaries sensitized on the culture of self reliance and savings

Output 8: Village based ECD used as an entry point for education/provision of health services

Output 9: Knowledge on good nutrition practices increased

Output 10: Provision of FBF and milk for affected children continued

Output 11: Health facilities Constructed and upgraded by ensuring access to electricity and water for health facilities

Output 12: Access to electricity and water for health facilities Ensured

Output 13: Healthcare workers enabled to use ICT and Equip healthcare facilities with electronic medical records

Output 14: Community health Enhanced

Output 15: Human resources for health increased

Output 15: Ensured coverage of health insurance scheme to 100%

Output 15: Improved quality and increased quantity of health workforce

Output 16: Diseases prevention awareness strengthened

Output 17: Use of FB Strengthened

Output 18: Promote recreational, sports and culture activities

Output 19: All children completing pre-primary programme before entering Primary Education ensured

Output 20: Increased access to quality education up to secondary level

Output 21: Improve adult literacy and Numeracy

Output 22: Increased participation and achievement of learners with disabilities at all levels

Output 23: Connection to electricity for all households increased

Output 24: Ensure 100% access to clean water

Output 25: Increased access to sanitation facilities

Output 26: Recycling of Waste water ensured

Output 27: Improved management of solid waste

Activities:

- VUP expanded public work for women headed HHs

- Support poverty family through Girinka Program

- Support poverty family through small livestock (goats, pigs, poultry)

- Provision of Social Care Services

- Sensitization for the most vulnerable people

- Construction of Houses for Homeless

- Support Homeless with small projects

- Construction Houses for vulnerable genocide survivors

- Rehabilitate Houses for vulnerable genocide survivors

- Monitor and Evaluate   the vulnerable genocide survivors’ life conditions

- Facilitate the engagement of CBO and NGOs in social protection

- Organize a disaster risk capacity building management and social economic transformation

- Organize capacity building sessions in Culture of self-reliance and savings

- Monitor and Evaluate the population savings

- Mobilize people to invest in ECDs

- Construction of ECDs in each cell by reinforcing the partnership ( PPP)

- Mobilize campaign for nutritional education to attend ECDs / Quarter

- Introduce nutrition counselling (including peer learning) sessions

- Establish model kitchen gardens at village level

- Provide FBF to eligible children under two years

- Maintain provision of 1 cup of milk program for affected children

- Construction of Gacaca health centre

- Construct Health posts

- Connection to water and electricity to all HPs

- Organize Training sessions for health workers and Equip Healthcare facilities

- Raise Awareness on reproductive health and increase contraceptive prevalence

- Increase the number of women (15-49) using family planning methods

- Equip maternity wards with adequate equipment

- Reduce the under 5 years mortality rate

- Increase quality in ANC services

- Increase number of doctors at health centres

- Increase the number of specialists at Ruhengeri hospital

- Increase the number of Midwives at health centre

- Ensure capacity building of medical staff in hospital, health centres, and health posts

- Sustain CBHI-Mutuel de santé

- Sensitize and support the population to acquire health insurance

- Train CBHI committees

- Strengthening a comprehensive, hands-on pre-service training, regulation of clinical practice and skills enhancement applying in-service mentorship

- NCDs prevention awareness creation through community mobilizations

- HIV community mobilization for testing and prevention

- Integrate Postpartum FP (PPFP) into ANC and maternity and PNC services

- Encourage male engagement in the use of FP services

- Promote the multi-sectoral and stakeholder’s collaboration to improve the demand and delivery of FP services

- Organize Mass sport activities

- Provide standardized ECE schools

- Extend ECDs at cell level

- Put in place PPP models for ECE and ECDs

- Ensure that each sector has a TVET

- Strengthen STEM in TVET training

- Construct New Schools (Classrooms)

- Organize Continuous Professional development for teachers

- Increase number of Science Laboratories

- Introduce STEM (Science, Technology, Engineering and Mathematic research Centre

- Suitable special needs education materials availed in schools

- Mobilization of Community to connect to electricity

- Feasibility study of water supply system

- Detailed study of rehabilitation water supply system

- Identification of water sources

- Construction of Public toilets

- Construct semi centralized sewerage system

- Construct faecal sludge treatment plant

- Construct waste water treatment plan

- Develop integrated Solid Waste Management

- Sensitize the population on waste management

- Fund available

- Availability of youth and women;

- Human resources (Humana capacity development, Technical assistance)

- Natural resources (Construction materials, …)

Figure 14: Result Chain (Impact III)

Impact 3: Transformational Governance that build on a capable, united, safe and built on Rwandan Values

Outcomes:

Outcome 1: Enhanced unity among Rwandans

Outcome 2: Values, home grown solutions and innovations streamlined into all institutions for transformational governance

Outcome 3: Cultural heritage at District and community level conserved and promoted

Outcome 4: Enhanced Peace and Security

Outcome 5: Control of Corruption, Transparency and Accountability Improved

Outcome 6: Sustained respect for human rights and civil liberties

Outcome 7: Reinforced efficient service delivery

Outcome 8: Enhanced accountability across public institutions

Outcome 9: Improved Local Government revenue mobilization and management for self-service

Outcome 10: Improved scores for citizen participation

Outcome 11: Developed Capacity for Civil Society and the Media

Outcome 12: Enhanced decentralisation system

Outputs

Output1: Itorero program strengthened in schools and Villages

Output2: Awareness campaign on the culture of problem solving conducted

Output3: Historical sites Developed and protected

Output4: Kinyarwanda Language and Rwandan values preserved especially among the youth

Output5: Fight against genocide ideology intensified

Output6:  Unity and reconciliation mechanisms of Rwandans strengthened

Output7: programmes for Home grown solutions enhanced and sustained

Output8: Culture Centers upgraded

Output9: 100% Memorial sites Managed, operational zed and developed

Output10: Community policing Strengthened and g security organs Strengthened

Output11: Checking alarm and camera system to prevent cross-border crimes, cybercrimes, human and drug trafficking installed on boarders and airport bus stations

Output12: Strengthen crime prevention

Output13: Mechanism to fight against corruption at all levels

Output14: Deepened awareness and respected human rights by implementing the national human rights action plan

Output15: Online service delivery reinforced

Output16: Constructed and maintained government assets that support the national economy

Output17: District, sectors and cells equipped with ICT devices (laptops & software) and connected to the Internet

Output18: Increased    JADF participation in District development, democratic governance and citizens’ welfare

Output19: Improved and increased district revenue

Output19: Participative planning sessions with all District stakeholders organized (Imihigo)

Output19: Mediators, community works, Ubudehe, Inteko z’abaturage and other home-grown solutions promoted

Output19: Home grown solution of mediators to solve problems

Output20: Partnership in planning, monitoring and evaluation of District partners’ activities Reinforced

Activities:

- Operationalize and monitor  itorero in all villages and Schools

- Conduct awareness and mobilization campaign of the youth to participate in National Service/ Urugerero

- Conduct impact assessment of Itorero program

- Conduct awareness campaign on the culture of problem solving through Cell- committees, Inshuti z’Umuryango and Umugoroba w’ababyeyi

- Protect Buhanga Forest

- Protect Musanze Caves

- Reinforce values and culture of excellence and patriotism

- Reinforce “Ndi Umunyarwanda” program

- Reinforce Unity clubs at village level

- Strengthen conservation and preservation of Genocide against Tutsi Proof

- Create unity and reconciliation clubs

- Availing and operationalize programmes of  Inteko y’abaturage

- Availing and operationalize programmes of  Abunzi

- Availing and operationalize programmes of   Umugoroba w’ababyeyi(Parents’ evening program

- Availing and operationalize programmes of   Umuganura

- Availing and operationalize programmes of Umuganda

- Upgrade ibyiwacu cultural Center

- Construct Standard memorial Site

- Strengthen Night Patrol(Irondo ry'umwuga)

- Security meeting at all levels

- Urugerero Program at District

- Security camera installed in Musanze City

- Organize drug abuse fighting awareness campaigns

- Organize awareness campaign to enhance crime prevention among population

- Construct rehabilitation Centres

- Create and train anti-corruption clubs

- Organize awareness campaign to fight against Corruption

- Train ABUNZI in order to inform their legal knowledge

- Put in place the Abunzi Management Information System

- Increase service delivery online

- Rehabilitation of Musanze District Office

- Construction and rehabilitation of all Sectors

- Construction and rehabilitation of all cells

- Equip District with ICT devices

- Equip Sectors with ICT devices

- Equip Cells with ICT devices

- Engage and develop capacity for JADF members

- Organize public accountability days

- Reinforcing tax collection system including inventory of taxable District assets

- Mobilization of sectors to increase   revenues collected at sector level

- Strengthen the technical capacity of districts to prioritize budget allocations to important socio-economic development programs through trainings

- Involving District stakeholders into planning sessions and M&E activities of the District

- Training Mediators

- Promoting Value added from community works program

- Promote community work and community assembly

- Strengthen the national youth Council and National Women Council at district and sector level

- Engage the citizen at village level in participatory planning/prioritization as well as budgeting

- Fund available

- Availability of youth and women;

- Human resources (Humana capacity development, Technical assistance)

- Natural resources (Construction materials,)

Table 7: Logical framework

| INDICATOR including Unit Measurement | BASELINE |  |  | OVERALL TARGET |  |  | TARGET |  |  | TARGET | TARGET | TARGET |  | TARGET |  |  | TARGET |  |  | MEANS OF VERIFICATION |  | ASSUMPTIONS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2017/18 |  |  | 2024 |  |  | 2018/19 |  |  | 2019/20 | 2020/21 | 2021/22 |  | 2022/23 |  |  | 2023/24 |  |  |  |  |  |
| PILLAR1: ECONOMIC TRANSFORMATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGRICULTURE SECTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA: Modernized and increased agricultural productivity and livestock |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 1: Increased agricultural production and productivity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT1.1: productivity increased and resilience strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Average yields of priority crops on Consolidated land (per sex of land owners) | Maize: 5.82 t/ha |  |  | 6t/ha |  |  | Maize: 5.85 t/ha |  |  | Maize: 5.86 t/ha | Maize: 5.88 t/ha | Maize: 5.88 t/ha |  | Maize: 6 t/ha |  |  | Maize: 6 t/ha |  |  | District Annual report |  | Availability of funds |
|  | Wheat: 3.16t/ha |  |  | 4ha/ha |  |  | Wheat: 3.20t/ha |  |  | Wheat: 3.30t/ha | Wheat: 3.40t/ha | Wheat: 3.60t/ha |  | Wheat: 3.80t/ha |  |  | wheat4t/ha |  |  | District Annual report |  | Availability of funds |
|  | Irish potatoes:29.53 t/ha |  |  | 32t/ha |  |  | Irish potatoes:29.58 t/ha |  |  | Irish potatoes:30 t/ha | Irish potatoes: 30.5 t/ha | Irish potatoes: 31 t/ha |  | Irish potatoes: 31.5 t/ha |  |  | Irish potatoes:32t/ha |  |  | District Annual report |  | Availability of funds |
|  | Climbing Beans: 3.38 t/ha |  |  | 3.5t/ha |  |  | Climbing Beans: 3.40 t/ha |  |  | Climbing Beans: 3.41 t/ha | Climbing Beans: 3.42 t/ha | Climbing Beans: 3.43 t/ha |  | Climbing Beans: 3.44 t/ha |  |  | Climbing Beans: 3.5 t/ha |  |  | District Annual report |  | Availability of funds |
| OUTPUT 1.2: Use of Fertilizer (organic manure and chemical) and use improved seeds increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Tones of mineral fertilizers distributed and used | DAP:753,350T |  |  | DAP:1,130,025T |  |  | DAP:791,017T |  |  | DAP:828,685T | DAP: 904,020T | DAP:979,355T |  | DAP:1,054,690T |  |  | DAP:1,130,025T |  |  | District Annual reports |  | Availability of funds |
|  | UREA:289,400T |  |  | UREA:434,100T |  |  | UREA:303,870T |  |  | UREA:318,340T | UREA:347,280T | UREA:376,220T |  | UREA:405,160T |  |  | UREA:434,100T |  |  |  |  |  |
|  | NPK:1,499,250T |  |  | NPK:2,248,875T |  |  | NPK:1,574,212T |  |  | NPK:1,649,175T | NPK:1,799,100T | NPK:1,949,025T |  | NPK:2,098,950T |  |  | NPK:2,248,875T |  |  |  |  |  |
| % of HHs headed by women and men using chemical fertilizers | 20% |  |  | 40% |  |  | 25% |  |  | 28% | 30% | 32% |  | 37% |  |  | 40% |  |  | District Annual reports |  | Farmers willingness and availability of funds |
| % of farmers' HHs headed by women and men using organic fertilizers | 30% |  |  | 50% |  |  | 35% |  |  | 37% | 38% | 40% |  | 45% |  |  | 50% |  |  | District Annual reports |  | Increase of farmers willingness and availability of funds |
| % of farmers' HHs headed by women and men using improved seeds | 20% |  |  | 40% |  |  | 25% |  |  | 28% | 30% | 32% |  | 37% |  |  | 40% |  |  | District report |  | Farmers willingness and availability of funds |
| Tons of improved seed produced | 15280T |  |  | 85000T |  |  | 14000T |  |  | 16000 | 16000 | 13000T |  | 13500 |  |  | 11500 |  |  | District report |  | Mobilization of Farmers |
| Number of seeds multipliers increased | 8 |  |  | 55 |  |  | 20 |  |  | 25 | 30 | 35 |  | 45 |  |  | 75 |  |  | District report |  | Farmers willingness and availability of funds |
| Output 1.3: Effective and efficient irrigation developed under an IWRM framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ha of land irrigated | 61ha |  |  | 600 ha |  |  | 140ha |  |  | 181ha | 269ha | 450ha |  | 500ha |  |  | 600ha |  |  | District report |  | Availability o funds |
| Output 1.4: Soil conservation, climate smart agriculture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ha of land area covered by progressive terraces increased and trees planting (per sex of HH owner’s head) | 2447.13ha |  |  | 3797ha |  |  | 50ha |  |  | 100ha | 450 | 650ha |  | 750ha |  |  | 3797ha |  |  | Report of number of ha create |  | Availability of funds |
| Ha of land area covered by radical terraces increased and trees planting (per sex of head of HH owner) | 1817.87ha |  |  | 2317.87ha |  |  | 0 |  |  | 100ha | 100ha | 150ha |  | 100ha |  |  | 50ha |  |  | Report of number of ha created |  | Availability of funds |
| Output 1.5: Enhanced and production in horticulture, vegetables fruits increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ha for agriculture land for flowers increased per sex of owner | 5ha |  |  | 10ha |  |  | 0 |  |  | 1ha | 1ha | 1ha |  | 1ha |  |  | 1ha |  |  | District report |  | mobilization |
| Ha for agriculture land for vegetables increased per sex of owner | 60ha |  |  | 200ha |  |  | 10ha |  |  | 22ha | 23ha | 25ha |  | 26ha |  |  | 34ha |  |  | District report |  | mobilization |
| Number of steams of flowers produced per sex of owner | 28.000 steams |  |  | 40.000Steams |  |  | 1000steams |  |  | 5000steams | 7000steams | 8000steams |  | 9000steams |  |  | 10000steams |  |  | District report |  | Availability of funds |
| Ha of essential oil crop intensified | 1ha |  |  | 50ha |  |  | 1ha |  |  | 5ha | 8ha | 10ha |  | 10ha |  |  | 15ha |  |  | District report |  | Availability o funds |
| Kg of vegetables produce per sex of producer | 0 |  |  | 60MT |  |  | 10MT |  |  | 10MT | 10MT | 10MT |  | 10MT |  |  | 10MT |  |  | Increased production |  | Mobilization |
| Ha of passion fruit Cultivated per sex of HH head | 0ha |  |  | 4ha |  |  | 0 |  |  | 1ha | 1ha | 1ha |  | 1ha |  |  | 0 |  |  | District report |  | Availability o funds |
| Ha of banana intensified | 25ha |  |  | 25ha |  |  | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  | District report |  | Availability o funds |
| Number of banana processing factories for making banana Juice and wine established per sex of owner) | 3 |  |  | 5 |  |  | 0 |  |  | 0 | 0 | 1 |  | 1 |  |  | 0 |  |  | District report |  | Mobilization and monitoring |
| Number of permanent fruits nurseries established (per sex of owner) | 0 |  |  | 4 |  |  | 1 |  |  | 1 | 1 | 1 |  | 0 |  |  | 0 |  |  | District report |  | Mobilization and monitoring |
| Number of juice and jam factory constructed and equipped per sex of owner | 0 |  |  | 1 |  |  | Identification |  |  | 0 | 0 | 1 |  | Verification |  |  | Verification |  |  | District report |  | Availability of funds |
| Outcome2: Improved livestock sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1: Large and small livestock increased especially within poorest families |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of cows distributed on behalf of Girinka program | 5116 |  |  | 11459 |  |  | 943 |  |  | 1000 | 1100 | 1100 |  | 1100 |  |  | 1100 |  |  | District report |  | Availability o funds |
| Number of new small livestock distributed to poor families | 700 |  |  | 1400 |  |  | 900 |  |  | 1000 | 1100 | 1200 |  | 1300 |  |  | 1400 |  |  | District report |  | Availability o funds |
| Output 2.2: Animal diseases prevented and controlled |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Nbr of cows and other domestic animals vaccinated | 31975 |  |  | 39500 |  |  | 34500 |  |  | 35500 | 36500 | 37500 |  | 38500 |  |  | 39500 |  |  | District Report |  | Availability of funds |
| Nbr of women and men owning improved veterinary pharmacie | 4 |  |  | 10 |  |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  | 1 |  |  | District Report |  | Availability of funds |
| Number of veterinary clinics established | 1 |  |  | 3 |  |  | 0 |  |  | 0 | 1 | 0 |  | 1 |  |  | 0 |  |  | District Report |  | Availability of funds |
| Output2.3: Animal feeding ensured and domestication improved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of ha with forage fields | 11 |  |  | 75 |  |  | 12 |  |  | 13 | 13 | 13 |  | 13 |  |  | 75 |  |  | District report |  | Mobilization and Monitoring |
| Number of improved animal feed processing plants established | 1 |  |  | 4 |  |  | 0 |  |  | 0 | 1 | 1 |  | 1 |  |  | 0 |  |  | District Report |  | Availability of funds |
| Output2.4: Animal Products produced |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quantity of milk produced per day (litters) increased | 7500 |  |  | 12000 |  |  | 8300 |  |  | 8700 | 9500 | 10500 |  | 11000 |  |  | 12000 |  |  | District report |  | Mobilization and Monitoring |
| Tones of fishes produced (per sex of producers) | 86,3 |  |  | 110 |  |  | 88,4 |  |  | 90 | 94 | 98 |  | 104 |  |  | 110 |  |  | District report |  | Mobilization |
| MT of honey produced per sex of owner | 8.6 MT |  |  | 14 MT |  |  | O |  |  | 1MT | 1MT | 1MT |  | 1.2MT |  |  | 1.2MT |  |  | District report |  | Mobilization |
| Number of fish ponds increased | 26 |  |  | 35 |  |  | 0 |  |  | 2 | 2 | 1 |  | 2 |  |  | 2 |  |  | District report |  | Mobilization and Monitoring |
| Number of improved pigs race intensified per sex of owner | 50 |  |  | 200 |  |  | 50 |  |  | 50 | 50 | Verification |  | Verification |  |  | Verification |  |  | District report |  | Mobilization and monitoring |
| Number of Milk collection Centres upgraded per sex of owner | 3 |  |  | 4 |  |  | 1 |  |  | 0 | Operationalization | Operationalization |  | Operationalization |  |  | Operationalization |  |  | District report |  | MoU with partners |
| Outcome3: Increased traditional and non-traditional export crops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome3.1: Production of traditional export crops increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Kg of pyrethrum produced per ha | 600kg/ha of dried flowers |  |  | 1000kg/ha of dried flowers |  |  | 700kg/ha of dried flowers |  |  | 800kg/ha of dried flowers | 900kg/ha of dried flowers | 1000kg/ha of dried flowers |  | Operationalization |  |  | Operationalization |  |  | District report |  | MoU signed and mobilization |
| Number of pyrethrum dryer constructed per sex of owner | 6 |  |  | 8 |  |  | 0 |  |  | 0 | 1 | 1 |  | 0 |  |  | 0 |  |  | District report |  | MoU signed |
| Number of Irish potatoes collection centres constructed per sex of owner | 1 |  |  | 20 |  |  | 3 |  |  | 3 | 3 | 4 |  | 4 |  |  | 2 |  |  | District report |  | Availability of funds |
| Irish potato starch (amidon) factory constructed (with specification of owner’s sex) | 0 |  |  | 1 |  |  | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 1 |  |  | District report |  | Availability of funds |
| Number of new store houses constructed per sex of investor | 2 |  |  | 5 |  |  | 0 |  |  | 0 | 1 | 1 |  | 1 |  |  | 0 |  |  | District report |  | Availability of funds |
| Number of drying facilities operationalized per sex of owner | 13 |  |  | 13 |  |  | Mobilization |  |  | Mobilization | Mobilization | Mobilization |  | Mobilization |  |  | Mobilization |  |  | District report |  | Availability o funds |
| Outcome4: Enabled environment and responsive institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome4.1: Capacity building of farmers improved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of trainings organized for farmers |  |  |  | 6 1/year |  |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  | 1 |  |  |  |  |  |
| PRIVATE SECTOR DEVELOPMENT AND YOUTH DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA: Create decent and productive jobs for economic development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME1: Off-farm jobs created per year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.1 : employment promoted through skills development, entrepreneurship and regulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of TVET/VET centres constructed | 7 |  |  | 15 |  |  | 3 |  |  | 2 | 2 | 1 |  |  |  |  | Operationalization |  |  | Reports |  | Equipment |
| Number of TVET/ VET centres rehabilitated | 7 |  |  | 8 |  |  |  |  |  |  |  | 1 |  | Operationalization |  |  | Operationalization |  |  | Reports |  | Budget |
| Number of head teachers and TVET school managers accessed relevant leadership and management course (per sex) | 0 |  |  | 45 3 /year |  |  | 45 |  |  | 45 | 45 | 45 |  | 45 |  |  | 45 |  |  | Reports |  | Budget |
| Number of TVETs schools and Private sector with partnership strengthened | 6 |  |  | 7 |  |  | 1 |  |  | 2 | 2 | 2 |  | 2 |  |  | 2 |  |  | Reports |  |  |
| Output 1.2: Enabling environment for the growth of entrepreneurship created |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of work executed in construction of Industrial park | 15% |  |  | 100% |  |  | 45% |  |  | 60% | 75% | 100% |  |  |  |  |  |  |  | Reports |  |  |
| Agakiriro Constructed | 20% |  |  | 100% |  |  | 30% |  |  | 50% | 100% | Operationalization |  | Operationalization |  |  | Operationalization |  |  | Reports |  | Expropriation Study of Utilities |
| Number of selling points along main road constructed per sex of owner | 2 |  |  | 7 |  |  | Study |  |  | 1 | 2 | 2 |  | Operationalization |  |  | Operationalization |  |  | Reports |  |  |
| Number of hydropower constructed | 3 |  |  | 6 |  |  | 1 |  |  | 1 | 1 | Operationalization |  | Operationalization |  |  | Operationalization |  |  | Reports |  |  |
| % of work executed in constructruction of Karwasa modern market | 0 |  |  | 100% |  |  | 30% |  |  | 100% | Operationalized | Operationalized |  | Operationalized |  |  | Operationalized |  |  | Reports |  | Expropriation, Utilities |
| New model SMEs created and supported |  |  |  | 200 |  |  | 100 |  |  | 100 | 100 | 100 |  | 100 |  | 100 |  |  | Reports |  |  | Evaluation |
| Number of operating cooperatives and other businesses (including SMEs) registered farmers | 149 SMEs |  |  | 100 SMEs |  |  | 100 SMEs |  |  | 100 SMEs | 100 SMEs | 100 SMEs |  | 100 SMEs |  | 100 SMEs |  |  | Reports |  |  | Mobilization |
| Output 1.3: Private and public institution mobilized to offer workplace learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of meeting organized to mobilize private an Public institutions to offer workplace |  |  |  | 12 2/year |  |  | 2 |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  | Reports |  | Mobilization |
| PRIORITY AREA: Promote Industrialization and attain a Structural Shift in the export base to High-value goods and services with the aim of growing exports by 17% annually |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME2: Increased exports of high value services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT2.1: projects developed for improving touristic destination and hospitality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of work executed to develop twin lakes | Study in place |  |  | 20% |  |  | 25% |  |  | 35% | 45% | 75% |  | 80% |  |  | 100% |  |  | Availability of investors |  | Budget |
| Number of artificial touristic sites created | 3 |  |  | 6 |  |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  | 1 |  |  | Availability of touristic sites |  | Mobilization |
| Number of camping site created and developed per sex of owner | 0 |  |  | 4 |  |  |  |  |  |  | 1 | 1 |  | 1 |  |  | 1 |  |  | Availability of camping sites |  | mobilization |
| OUTCOME 3: Improved private sector Financing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.1:Entrepreneurs (youth and women) accessed to finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of meeting organized for mobilizing of youth and women to enhance entrepreneurship |  |  |  | 24 |  |  | 4 |  |  | 4 | 4 | 4 |  | 4 |  |  | 4 |  |  | Reports |  | Mobilization |
| % of men and women and youth trained in financial literacy |  |  |  |  |  |  | 300 |  |  | 300 | 300 | 300 |  | 300 |  |  | 300 |  |  | Reports |  |  |
| Number of youth and women accessed finance trough BDF | 649 |  |  | 1489 |  |  | 300 |  |  | 300 | 289 | 200 |  | 200 |  |  | 200 |  |  | Reports |  | Mobilization |
| Number of youth and women accessed finance trough SACCO | 65.024 |  |  | 72.000 |  |  | 1.476 |  |  | 1.000 |  | 1.500 |  | 3.000 |  |  |  |  |  | Reports |  | Mobilization |
| Business centres creation and rehabilitation | 10 |  |  | 30 |  |  | 5 |  |  | 5 | 5 | 5 |  | 5 |  |  | 5 |  |  | Reports |  | Mobilization |
| Warehouses construction | 0 |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  | Reports |  | Mobilization |
| Modern heavy truck Transit centre constructed | 0 |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  | Reports |  | Mobilization |
| % Of women and youth who acquired formal credits |  |  |  | 30 |  |  | 30 |  |  | 30 | 30 | 30 |  | 30 |  |  | 30 |  |  | Reports |  | Mobilization |
| SPORT AND CULTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA: Create 1.5m (over 214,000 annually) decent and productive jobs for economic development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 4: Off-farm jobs created per year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4.1: Talented cyclist and athletes increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Talent centers constructed | 0 |  |  | 4 |  |  |  |  |  | 1 |  | 1 |  | 1 |  |  | 1 |  |  | Reports |  |  |
| PRIORITY AREA: Promote Industrialization and attain a Structural Shift in the export base to High-value goods and services with the aim of growing exports by 17% annually |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 4: Increased exports of high value services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4.1: projects developed for improving touristic destination and hospitality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Musanze Stadium constructed | 0 |  |  | 100% |  |  | 10% |  |  | 25% | 30% | 50% |  | 75% |  |  | 100% |  |  | Report |  | Budget |
| Ubworoherane Stadium upgraded | 50% |  |  | 100% |  |  | 60% |  |  | 75% | 100% |  |  |  |  |  |  |  |  | Report |  | Budget |
| Number of district traditional dance group created | 0 |  |  | 1 |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  | Availability of dance group |  |  |
| PRIORITY AREA: Accelerate Sustainable Urbanization from 17.3% (2013/14) to 35% by 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Secondary cities developed as poles of socio-economic growth |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Flagship projects developed in Musanze City |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Musanze Regional Stadium constructed | 0 |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |
| Gymnasium constructed | 0 |  |  | 1 |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  | Report |  |  |
| ENERGY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA: Accelerate Sustainable Urbanization from 17.3% (2013/14) to 35% by 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 1: Street lighting expanded to all national and district roads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.1: Provided existing major roads with street lighting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Km Public lighting established | 39.78km |  |  | 30km |  |  |  |  | 5km | 5km | 5km | 5km |  | 5km |  |  | 5km |  |  | Reports |  | Budget |
| Extension of Electrical lines (MV) |  |  | 89.1km |  |  | 119.1km |  |  | 0 | 6km | 6km |  | 6km |  | 6km |  |  | 6km | Report |  |  | Budget |
| Extension of Electrical lines (LV) |  |  | 247.6km |  |  | 5km |  |  | 322.6km | 10km | 15km |  | 15km |  | 15km |  |  | 15km |  |  |  |  |
| % of HHs grouped in villages ( IDP, imidugudu) having electrified per sex of HH head |  |  | 4 |  |  | 11 |  |  | 1 | 2 | 2 |  | 2 |  | 2 |  |  | 2 | District report |  |  |  |
| PRIORITY AREA: Sustainable management of Natural Resources and Environnement to transition Rwanda towards Green economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Increased green growth and climate resilience for socio-economic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT : Reduced Number of households depending on firewood as a source of energy for cooking |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of public institutions using biogas | 5 |  |  | 30 |  |  | 5 |  |  | 5 | 5 | 5 |  | 5 |  |  | 5 |  |  |  |  | Mobilization |
| Number of meeting organized to mobilize households to use cooking gas | 0 |  |  | 24 4/year |  |  | 4 |  |  | 4 | 4 | 4 |  | 4 |  |  | 4 |  |  |  |  | Mobilization |
| % of households using cooking gas per sex of HH heads | 1540 4,25%of HHS |  |  | 60% oh HHs |  |  | 10% |  |  | 10% | 10% | 10% |  | 10% |  |  | 10% |  |  |  |  | Mobilization |
| TRANSPORT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA: Accelerate Sustainable Urbanization from 17.3% (2013/14) to 35% by 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Improved public transport services, effective and safe traffic management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 2.1: Public transportation within the District Enhanced |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of bus lines constructed | 0 |  |  | 5lines |  |  | 0 |  |  | 1 | 1 | 1 |  | 1 |  |  | 1 |  |  | Reports |  | Budget |
| Number of Bus stop created | 0 |  |  | 5 |  |  | 0 |  |  | 1 | 1 | 1 |  | 1 |  |  | 1 |  |  | Report |  | Budget |
| Number of Bus terminals constructed | 0 |  |  | 5 |  |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  | 1 |  |  | Reports |  | Budget |
| OUTPUT 2.2: Junctions improved to reduce traffic congestion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| One modern round about constructed | 0 |  |  | 1 |  |  | 0 |  |  | 1 | 0 | 0 |  | 0 |  |  | 0 |  |  | Reports |  | Budget |
| Number of mini round about constructed in Musanze City | 0 |  |  | 2 |  |  | 0 |  |  | 1 | 0 | 0 |  | 1 |  |  | 0 |  |  | Report |  | Budget |
| OUTPUT 2.3: Road networks within the District improved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Km of asphalt roads constructed | 68.25km |  |  | 98.25km |  |  | 5km |  |  | 5km | 5km | 5km |  | 5km |  |  | 5km |  |  | Reports |  | Expropriation, Construction |
| Km of feeder roads constructed | 168km |  |  | 236km |  |  | 6km |  |  | 12km | 12km | 12km |  | 13km |  |  | 13km |  |  | Reports |  | Expropriation, Construction |
| Km of unpaved roads | 2.38km |  |  | 8.38km |  |  | 0 |  |  | 2km | 0 | 2km |  | 0 |  |  | 2km |  |  | Reports |  | Expropriation, Construction |
| Km of pedestrian ways along main roads in Musanze town and round about. | 24km |  |  | 54km |  |  | 5km |  |  | 5km | 5km | 5km |  | 5km |  |  | 5km |  |  | Reports |  | Construction |
| Km of Bicycle lanes constructed | 0 |  |  | 18km |  |  | 0 |  |  | 0 | 3km | 5km |  | 5km |  |  | 5km |  |  | Report |  | Construction |
| Number of bridges constructed | 11 |  |  | 26 |  |  | 5 |  |  | 2 | 2 | 2 |  | 2 |  |  | 2 |  |  | Reports |  | Expropriation, Construction |
| Km of rainwater channel/Drainages constructed | 4.5km |  |  | 19.5km |  |  | 2.5km |  |  | 2.5km | 2.5km | 2.5km |  | 2.5km |  |  | 2.5km |  |  | Reports |  | Expropriation, Construction |
| OUTCOME: Secondary cities developed as poles of socio-economic growth |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Flagship projects developed in Musanze City |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Helipad Constructed IN national volcano Park | 0 |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  | Emergency rescued/H |  | Mobilization |
| URBANIZATION AND RURAL SETTLEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA: Accelerate Sustainable Urbanization from 17.3% (2013/14) to 35% by 2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Integrated human settlement planning and coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT : Green urban and rural development plans and detailed physical plans developed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Musanze Master plan updated | 0 |  |  | 100% |  |  | 100% |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  |  | Mobilization |
| Number of physical and layout plans developed and finalized | 3 |  |  | 8 |  |  |  |  |  | 2 | 3 |  |  |  |  |  |  |  |  | Final Report |  | Mobilization |
| Number of Local urban development plans developed and reviewed | 5 |  |  | 11 |  |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  | 1 |  |  | Final Report |  | Mobilization |
| Number of settlements viabilized | 3 |  |  | 68 |  |  | 0 |  |  | 8 | 15 | 15 |  | 15 |  |  | 15 |  |  | Community participation |  | Mobilization |
| Number of Informal settlement upgraded | 0 |  |  | 2 |  |  | 0 |  |  | 0 | 1 | 0 |  | 1 |  |  | 0 |  |  |  |  | Mobilization |
| Beautification in Musanze city | 0 |  |  | 6ha |  |  | 0 |  |  | 2ha | 0 | 2ha |  | 0 |  |  | 2ha |  |  |  |  | Mobilization |
| Land banking |  |  |  | 25ha |  |  | 2.5ha |  |  | 2.5ha | 5ha | 5ha |  | 5ha |  |  | 5ha |  |  | Budget |  | Expropriation |
| OUTCOME: Secondary cities developed as poles of socio-economic growth |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4.1:Flagship projects developed in Musanze City |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of factory to exploit and process volcanic stones (stoves, bricks, fertilizers, handcrafts, etc.) established | 0 |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  | Productivity report |  | Mobilization |
| Number of Cement factory per sex of owner | 1 |  |  | 2 |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  | Productivity report |  | Mobilization |
| Vehicle assembly plant constructed (with specification of owner’s sex) | 0 |  |  | 1 |  |  | study |  |  | MoU | 1 |  |  |  |  |  |  |  |  | Productivity report |  | Mobilization |
| Number of modern brick kilns developed (with specification of owner’s sex) | 0 |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  | Productivity report |  | Mobilization |
| Number of Ceramic Industries developed | 0 |  |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | Productivity report |  | Mobilization |
| Drinking water treatment Plant (sparkling water) constructed (with specification of owner’s sex) | 0 |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  | Productivity report |  | Mobilization |
| Oscillatory and Disrrict hospital constructed | 0 |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  | Report |  | Mobilization |
| Building Material technology center established | 0 |  |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  | Mobilization |
| OUTCOME 5: Facilitated development of affordable and social housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 5.1: affordable and social housing developed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of plots with Basic infrastructure developed in new areas for residential housing through PPP | 0 |  |  | 250 Plots |  |  | 25 |  |  | 25 | 50 | 50 |  | 50 |  | 50 |  |  | Budgets |  | Mobilization |  |
| Households living in scattered settlements relocated | 89.2% |  |  | 100% |  |  | 900 |  |  | 1200 | 1200 | 1200 |  | 1200 |  | 1200 |  |  |  |  | Mobilization |  |
| Number of affordable real estates constructed in partnership with private sector | 50HHs |  |  | 110 HHs |  |  | 75HHs |  |  | 10HHs | 25HHs | 25HHs |  | 25HHs |  | 25HHs |  |  |  |  | Mobilization |  |
| Number of existing brick kilns upgraded per sex of owners | 12 |  |  | 12 |  |  | 2 |  |  | 2 | 2 | 2 |  | 2 |  | 2 |  |  | Quality of Products |  | Mobilization |  |
| Plot servicing in urban areas | 10Km |  |  | 25Km |  |  | 0 |  |  | 5 | 5 | 5 |  | 5 |  | 5 |  |  | Budget |  | Mobilization |  |
| ENVIRONMENT AND NATURAL RESOURCES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA: Sustainable Management of Natural Resources and Environment to Transition Rwanda towards a Carbon Neutral Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 7.1: Sustainable and productive forest management ensured. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 7.1.1 Improved land use administration and management for optimal allocation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ha of forestry rehabilitated per sex of owner | 4403ha |  |  | 45949ha |  |  | 4843ha |  |  | 5327ha | 5860ha | 6446ha |  | 7091ha |  | 7800ha |  |  | Annual report |  | Mobilization |  |
| Ha of Agroforestry planted per sex of owner | 4529ha |  |  | 10729ha |  |  | 4000ha |  |  | 500ha | 500ha | 400ha |  | 400ha |  | 400ha |  |  | Annual report |  | Mobilization |  |
| Percentage of forests converted into productive forests and managed by forests owners/DFMP per sex of owner | 28% |  |  | 35% |  |  | 29% |  |  | 30% | 31% | 32% |  | 33% |  | 35% |  |  | Annual reports |  | Mobilization |  |
| Percentage of Public Forest managed by Private operators per sex of operator | 0 |  |  | 80% |  |  | 20% |  |  | 20% | 20% | 20% |  | 20% |  |  |  |  | Annual report |  | Mobilization |  |
| OUTCOME: Integrated water resource management ensuring availability of renewable water resources for sustainable development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Managed water flows from volcanoes and improve water resource management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of km of Planted bamboos along Mukungwa river, | 20km |  |  | 50km |  |  | 5km |  |  | 5km | 5km | 5km |  | 5km |  | 5km |  |  | Annual report |  | Mobilization |  |
| Number of km of Planted bamboos along Rwebeya ravine | 20km |  |  | 50km |  |  | 5km |  |  |  | 5km | 5km |  | 5km |  | 5km |  |  | Annual report |  | Mobilization |  |
| Number of km of Planted bamboos along Susa ravine | 20km |  |  | 50km |  |  | 5km |  |  | 5km | 5km | 5km |  | 5km |  | 5km |  |  | Annual report |  | Mobilization |  |
| Number of km of Planted bamboos along Muhe ravine | 20km |  |  | 50km |  |  | 5km |  |  | 5km | 5km | 5km |  | 5km |  | 5km |  |  | Annual report |  | Mobilization |  |
| Number of km of Planted bamboos along Cyuve ravine | 20km |  |  | 50km |  |  | 5km |  |  | 5km | 5km | 5km |  | 5km |  | 5km |  |  | Annual report |  | Mobilization |  |
| Km of public garden installed along Kigombe stream | 0 |  |  | 5km |  |  | 0.5km |  |  | 1km | 1km | 0.5km |  | 0.5km |  | 0.5km |  |  | Annual report |  | Mobilization |  |
| Number of ha of Mukungwa catchment protected by land husbandry technics | 10ha |  |  | 360ha |  |  | 50ha |  |  | 50ha | 50ha | 50ha |  | 50ha |  | 50ha |  |  | Annual report |  | Mobilization |  |
| Erosion control ditches constructed per sex of head of HH owner the land | 13816ha |  |  | 15599ha |  |  | 415ha |  |  | 421ha | 433ha | 413ha |  | 101ha |  | Rehabilitation |  |  | Annual report |  | Mobilization |  |
| PRIORITY AREA: Promote Industrialization and attain a Structural Shift in the export base to High-value goods and services with the aim of growing exports by 17% annually |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Vibrant, efficient and responsible mining spurring sustainable economic development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Value addition for minerals and quarry products increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of mining cooperatives linked with financial institutions and potential investors to increase production for district economic development with specification of women and men among cooperative members | 1 |  |  | 1 |  |  | Mobilization |  |  | 1 | Mobilization | Mobilization |  | Mobilization |  | Mobilization |  |  | Volume of Production |  | Mobilization |  |
| Number of meeting organized for Dissemination of mining law to Enforce the policy on exploitation of mines and quarries |  |  |  | 12 2/year |  |  | 2 |  |  | 2 | 2 | 2 |  | 2 |  | 2 |  |  | Service delivery |  |  |  |
| OUTPUT1.2: XX mines and quarries sustainably exploited |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of mines and quarry sites protected | 7 |  |  | 3 |  |  | 1 |  |  | 2 |  |  |  |  |  |  |  |  | Increase of mining sites |  |  |  |
| WATER AND SANITATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA: Sustainable Management of Natural Resources and Environment to Transition Rwanda towards a Carbon Neutral Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 7.3: Increased green growth and climate resilience for socio-economic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 7.3.2 Rain water management improved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Households with rainwater harvesting facilities installed per sex of HH heads | 7650 |  |  | 15000 |  |  | 1.225 |  |  | 1.225 | 1.225 | 1.225 |  | 1.225 |  |  | 1.225 |  | EROSION CONTROL IMPROVED |  |  | Mobilization |
| Increase households access to clean water in urban areas | 98.8% |  |  | 100% |  |  | 900 |  |  | 1200 | 1200 | 1200 |  | 1200 |  |  | 1200 |  |  |  |  | Mobilization |
| Extension and rehabilitation of pipe lines in rural areas |  | 89% |  |  | 100% |  |  | 13km |  | 25km | 25km | 25km |  | 25km |  |  | 25km |  | Report |  |  | Mobilization |
| Extension and rehabilitation of pipe lines in urban areas |  | 98.8% |  |  | 100% |  |  |  |  | 5km | 5km | 5km |  | 5km |  |  | 5km |  | report |  |  | Mobilization |
| Improve central sewage system (Waste water treatment plant) |  | 0 |  |  | 3 |  |  |  |  | 1 |  | 1 |  |  |  |  | 1 |  | Report |  |  | Mobilization |
| Financial sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority area: Increase Domestic Savings and position Rwanda as a hub for financial services to promote investments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Enhanced long-term savings and innovative financing mechanisms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT:: Annual awareness campaigns conducted in all sectors about online |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of awareness campaign organized | NA |  |  | 6 1/year |  |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  | 1 |  |  |  |  |  |
| OUTPUT: Saving and access to agriculture credit by women and men Increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of literacy campaigns organized | NA |  |  | 6 1/year |  |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  | 1 |  |  |  |  |  |

| SOCIAL TRANSFORMATION PILLAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INDICATOR | BASELINE (2017/18) | DDS Target 2024 | TARGET 2018/19 |  |  |  | TARGET 2019/20 |  |  | TARGET 2020/21 |  |  |  | TARGET 2021/22 |  |  | TARGET 2022/23 |  |  |  |  | TARGET 2023/24 |  |  |  |  | MEANS OF VERIFICATION |  |  | ASSUMPTION |  |  |  |  |
| ENERGY SECTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NST1 PRIORITY AREA: Moving Towards a Modern Rwandan Household |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Household access to electricity increased to 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.1.1: Connection to electricity for all households increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of meeting organized for mobilization |  | 6 1/year | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | District report |  |  |  |  |  |
| Number of households have access to electricity per sex of HH head | 34,248 | 50,000 |  |  |  | 4,000 |  |  | 6,000 |  | 10,000 |  |  |  |  |  |  | 10,000 |  |  | 10,000 |  | 10,000 |  |  |  |  | District report |  |  |  | Number of household have access to electricity per sex of HH head |  |  |
| URBANIZATION AND RURAL SETTLEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NST1 PRIORITY AREA: Moving Towards a Modern Rwandan Household |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Facilitated development of affordable and social housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: social housing developed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of IDP model villages constructed | 3 | 15 |  |  |  | 2 |  |  | 2 |  | 2 |  |  |  |  |  |  | 2 |  |  | 2 |  | 2 |  |  |  |  |  |  |  |  |  |  |  |
| SOCIAL PROTECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 1: Enhancing graduation from extreme Poverty and promoting resilience |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 1.1: Productivity increased and household resilience strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.1.1 Increased social protection coverage of extremely poor households |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of households who benefit from VUP expanded | 507 | 4,467 | 693 |  |  |  | 713 |  |  | 734 |  |  |  | 753 |  |  | 776 |  |  |  |  | 798 |  |  |  | Report on number of beneficiaries |  |  |  |  |  |  |  |  |
| Number of poor families supported through girinka program per sex of HH head | 5471 | 9430(100%) | 900 |  |  |  | 1420 |  |  | 1000 |  |  |  | 1000 |  |  | 1000 |  |  |  |  | Girinka Package |  |  |  | Reports |  |  |  |  |  |  |  |  |
| Number of poor families supported through small Livestock per sex of HH head | 324 | 324 | 324 |  |  |  | 324 |  |  | 324 |  |  |  | 324 |  |  | 324 |  |  |  |  | 324 |  |  |  | Reports |  |  |  |  |  |  |  |  |
| Output: Provision of Social Care Services and sensitization for the most vulnerable people strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of training organized to strengthen the capacity building of district officers on how to best target and support vulnerable people per sex of participants |  | 12 2/year | 2 |  |  |  | 2 |  |  | 2 |  |  |  | 2 |  |  | 2 |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 1.2: Reduced poverty among Rwandans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.2.1 Houses to homeless provided in planned settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Houses for Homeless constructed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.2.2 Houses for vulnerable genocide survivors reconstructed and rehabilitated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Houses for vulnerable genocide survivors constructed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Houses for vulnerable genocide survivors rehabilitated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 1.3: Enhanced resilience of Rwandans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.3.1 CBOs and NGOs engaged in social protection strengthened and increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of meetings organized for mobilization |  | 6 | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.3.2 Capacity for disaster risk reduction and social economic transformation improved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of disaster risk capacity building management and social economic organized |  | 12 | 2 |  |  |  | 2 |  |  | 2 |  |  |  | 2 |  |  | 2 |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.3.2 Social protection beneficiaries sensitized on the culture of self reliance and savings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of capacity building sessions in Culture of self-reliance and savings |  | 12 | 2 |  |  |  | 2 |  |  | 2 |  |  |  | 2 |  |  | 2 |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 2: Eradicating Malnutrition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 2.1: Reduced malnutrition among children |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 2.1.1 Village based ECD used as an entry point for education/provision of health services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of meeting organized to mobilize people to invest in ECDs per sex of participants | 0 | 6 1/year | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | reports |  |  |  |  |  |  |  |  |
| Number of ECDs constructed at cell level by reinforcing the partnership |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Mobilization campaign for nutritional education to attend ECDs |  | 12 2/year | 2 |  |  |  | 2 |  |  | 2 |  |  |  | 2 |  |  | 2 |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 2.1.2 Knowledge on good nutrition practices increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of nutrition counselling (including peer learning) sessions Introduced per sex of beneficiaries | 0 | 6 (1per year) | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  | reports |  |  |  |  |  |  |  |  |  |  |
| Number of modern kitchen gardens at village level constructed | 0 | 6 (1per year) | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  | reports |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 2.1.3 Provision of FBF and milk for affected children continued |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of eligible under two years received FBF | 75% | 100% | 80% |  | 85% |  |  | 90% |  |  |  | 95% |  |  | 100% |  |  |  | 100% |  |  |  |  | reports |  |  |  |  |  |  |  |  |  |  |
| Number of mobilization meetings organized to maintain provision of 1 cup of milk program for affected children |  | 12 | 2 |  | 2 |  |  | 2 |  |  |  | 2 |  |  | 2 |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HEALTH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 3: Enhancing demographic dividend through ensuring access to quality Health for all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 3.1: Improved healthcare services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.2.1 Health facilities Constructed and upgraded by ensuring access to electricity and water for health facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of works executed in the construction of Gacaca health centre | 0% | 100% | 30% |  | 75% |  |  | 85% |  |  |  | 95% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | health centre constructed |  |  |
| Number of health post constructed | 17 | 68 | 10 |  | 10 |  |  | 10 |  |  |  | 10 |  |  | 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | health post constructed |  |  |
| Upgrade Ruhengeri District hospital | 0% | 100% | 20% |  | 40% |  |  | 50% |  |  |  | 60% |  |  | 80% |  |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |  | Ruhengeri district hospital constructed and equipped with adequate equipment |  |  |
| Feasibility study of constructing, Rehabilitation and extending Health infrastructures | 0% | 100% | 20% |  | 30% |  |  | 40% |  |  |  | 60% |  |  | 80% |  |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |  | health centres with adequate infrastructure |  |  |
| OUTPUT 3.2.2 Access to electricity and water for health facilities Ensured |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Health centres connected to water and electricity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Health posts connected to water and electricity | 12 | 17 |  |  | 13 |  |  | 14 |  |  |  | 15 |  |  | 16 |  |  |  | 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.1.3 Healthcare workers enabled to use ICT and Equip healthcare facilities with electronic medical records |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Health centres connected to internet | 10 | 15 | 11 |  | 12 |  |  | 13 |  |  |  | 14 |  |  | 15 |  |  |  |  |  |  |  |  | All health posts connected to electricity |  |  |  |  |  |  |  |  |  |  |
| Number of Post centres connected to internet | 12 | 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | All health post connected to internet |  |  |  |  |  |  |  |  |  |  |
| Number of training sessions for health workers |  | 6 1/year | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  | All health post connected to internet |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.1.2 Community health Enhanced |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of women (15-49) and men using family planning methods | 1/2886 | 1/3500 | 1/4500 |  | 5000 |  |  | 6000 |  |  |  | 7000 |  |  | 8000 |  |  |  | 1/8500 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Maternal Mortality Ratio/100, 000 | 210 | 126 | 168 |  | 165 |  |  | 145 |  |  |  | 135 |  |  | 130 |  |  |  | 125 |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| Neonatal Mortality Rate/1000 LB | 20 | 15.2 | 18 |  | 17 |  |  | 16.5 |  |  |  | 16 |  |  | 15 |  |  |  | 14 |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| Under five mortality rate | 50 | 35 | 48 |  | 47 |  |  | 40 |  |  |  | 38 |  |  | 36 |  |  |  | 35 |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| Infant Mortality Rate/1000 LB | 32 | 22.5 | 28 |  | 26 |  |  | 25 |  |  |  | 24 |  |  | 23 |  |  |  | 22 |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| % of births attended by skilled health professionals | 91 |  | >92 |  | >100 |  |  | >94 |  |  |  | >95 |  |  | >98 |  |  |  | >100 |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| % of Children 12-23 months fully immunized | 93 | 100 | >96 |  | >97 |  |  | >98 |  |  |  | >99 |  |  | >100 |  |  |  | >100 |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| Prevalence of Stunting | 38 | 19 | 29.9 |  | 28 |  |  | 27 |  |  |  | 20 |  |  | 19 |  |  |  | 18 |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| Modern contraceptive prevalence rate | 48 | 60 | 54.6 |  | 55 |  |  | 56 |  |  |  | 56.5 |  |  | 59 |  |  |  | 62 |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| % HFs with < 5% of vital medical products stock-outs | 87 | 100 | 98 |  | 97 |  |  | 94 |  |  |  | 90 |  |  | 88 |  |  |  | 87 |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| Proportion of persons diagnosed with HIV infection receiving sustained ART | 82.7 | 90% | 83% |  | 85% |  |  | 86% |  |  |  | 87% |  |  | 88% |  |  |  | 90% |  |  |  |  | Report from Health centers |  |  |  |  |  |  |  |  |  |  |
| Number of maternity wards with adequate equipment | 14 | 17 |  |  | 14 |  |  |  |  |  |  | 15 |  |  | 16 |  |  |  | 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of awareness campaign on vaccination organised |  | 6 | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of increased quality in ANC services | 37% | 85% | 50% |  | 60% |  |  | 70% |  |  |  | 80% |  |  | 85% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.1.1 Human resources for health increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of doctors at health centers increased per sex | 0 | 15 | 2 |  | 2 |  |  | 2 |  |  |  | 3 |  |  | 2 |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  | report of Service delivery improved |  |  |
| OUTPUT 3.1.1 Human resources for health increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of doctors at health centers increased per sex | 0 | 15 | 2 |  | 2 |  |  | 2 |  |  |  | 3 |  |  | 2 |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  | report of Service delivery improved |  |  |
| Number of specialists at Ruhengeri hospital increased | 7 | 10 | 1 |  | 1 |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | report of Service delivery improved |  |  |
| Number of Midwives at health center increased per sex | 0 | 30 | 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | report of Service delivery improved |  |  |
| Numbers of training organize for medical staff in hospital, health centers and health posts per sex of participant. |  | 24 4/year | 4 |  | 4 |  |  | 4 |  |  |  | 4 |  |  | 4 |  |  |  | 4 |  |  |  |  |  |  |  |  |  |  |  |  | report of Service delivery improved |  |  |
| OUTCOME 3.2: Increased financial sustainability for the health sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.2.1 Ensured coverage of health insurance scheme to 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of people with mutual de santé per sex | 84% | 100% | 95% |  | 100% |  |  | 100% |  |  |  | 100% |  |  | 100% |  |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number Sensitization meetings organized to support the population to acquire health insurance |  | 6 1/year | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of trainings organized for CBHI committees |  | 6 1/year | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 3.3: Increased health of workforce |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.4.1 Improved quality and increased quantity of health workforce |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of campaign organized for Advocating for investment in clinical and health educational opportunities |  | 6 | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 3.4:Reduced Communicable Diseases and Non-Communicable Diseases (NCDs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.4.1 Diseases prevention awareness strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Community mobilizations organized for NCDs prevention |  | 6 | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of HIV community mobilization for testing and testing |  | 6 | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 3.5: Increased contraceptives prevalence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.5.1 Use of FB Strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of mobilization meetings organized to Integrate Post partum FP (PPFP) into ANC and maternity and PNC services |  | 6 | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of mobilization meetings organized to encourage male to use FP services |  | 6 | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of mobilization meetings organized to promote the multi-sectorial and stakeholder’s collaboration to improve |  | 6 | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SPORT AND CULTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 3: Enhancing demographic dividend through ensuring access to quality Health for all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Promotion of sports and culture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Promote recreational, sports and culture activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mass sport activities Organized |  | 1/month | 12 |  | 12 |  |  | 12 |  |  |  | 12 |  |  | 12 |  |  |  | 12 |  |  |  |  |  |  |  |  |  |  |  |  | health centre constructed |  |  |
| EDUCATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 4: Enhancing demographic dividend through improved access to quality education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Enhanced access to quality education for all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: All children completed pre-primary programme before entering Primary Education ensured |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of standardized ECE schools provided | 30 | 90 | 10 |  | 10 |  |  | 10 |  |  |  | 10 |  |  | 10 |  |  |  | 10 |  |  |  |  | Reports |  |  |  |  |  |  |  | Construction and Equipment |  |  |
| Number of cells having operational ECD | 5 | 63 | 5 |  | 10 |  |  | 12 |  |  |  | 13 |  |  | 11 |  |  |  | 12 |  |  |  |  | Reports |  |  |  |  |  |  |  | Construction and Equipment |  |  |
| Number of PPP models for ECE and ECDs put in place | 2 | 5 |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  | Reports |  |  |  |  |  |  |  | meeting with JDADF |  |  |
| OUTCOME 4.3: Increased technical and vocational education and training (TVET) schools and graduates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Increase access to adult basic education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of TVET constructed at sector level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of training organized to strengthen STEM in TVET | 0 | 18 | 3 |  | 3 |  |  | 3 |  |  |  | 3 |  |  | 3 |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  | Construction and Equipment |  |  |
| OUTCOME 4.2: Enhanced quality of teaching and learning at all levels of education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT : Increased access to quality education up to secondary level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of classrooms constructed | 48 | 117 | 12 |  | 12 |  |  | 12 |  |  |  | 12 |  |  | 11 |  |  |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  | Construction and Equipment |  |  |
| Number of science laboratories constructed | 10 | 22 | 2 |  | 2 |  |  | 2 |  |  |  | 2 |  |  | 2 |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  | Construction and Equipment |  |  |
| Number of Continuous Professional development (trainings) organized for teachers per sex | 2 | 20 | 3 |  | 3 |  |  | 3 |  |  |  | 3 |  |  | 3 |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  | Construction and Equipment |  |  |
| Number of STEM (Science, Technology, Engineering and Mathematics) research centres introduced | 0 | 1 |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Increased adult literacy rates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Improve adult literacy and Numeracy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of meeting organized to sensitize the dropouts to join TVET school |  | 18 | 3 |  | 3 |  |  | 3 |  |  |  | 3 |  |  | 3 |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Equitable opportunities to all levels of learning irrespective of gender, socio-economic or other status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4.6.1: Increased participation and achievement of learners with disabilities at all levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of suitable special needs education materials(Toilets) availed in schools | 62 | 71 | 2 |  | 2 |  |  | 2 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of capacity building conducted to teachers in favour of disable children per sex |  | 12 | 2 |  | 2 |  |  | 2 |  |  |  | 2 |  |  | 2 |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WATER AND SANITATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 5: Moving towards a Modern Rwandan Household |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME: Improved and Sustained urban and rural households access to safe drinking water |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Ensure 100% access to clean water |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of households that have access to clean water (per sex of HH head) | 88% | 100% | 89% |  | 90% |  |  | 93% |  |  |  | 96% |  |  | 98% |  |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |  | reports |  |  |
| Number of Feasibility study of extending water supply system | 1 | 4 | 1 |  | 1 |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | reports |  |  |
| Number of detailed study of rehabilitation water supply system |  | 2 | 3 |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | reports |  |  |
| OUTCOME: Improved and Sustained household access to basic sanitation Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Increased access to sanitation facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of public toilets constructed (Eco-friendly) per sex of users |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Public toilets available |  |  |  |  |  |  |  |  |  |
| OUTPUT: Recycling of Waste water ensured |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of semi centralized sewerage system constructed |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Sewerage system available |  |  |  |  |  |  |  |  |  |
| Number of faecal sludge treatment Plant constructed | 0 | 2 |  |  |  | Study |  |  | 10% |  |  |  | 20% |  |  | 50% |  |  |  | 100% |  |  |  |  | faecal sludge treatment plants available |  |  |  |  |  |  |  |  |  |
| Number of waste water treatment Plant constructed |  | 0 |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Waste water treatment plant available |  |  |  |  |  |  |  |  |  |
| OUTCOME: Integrated and sustained Waste Management Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT: Improved management of Solid waste |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of work executed to construct landfill | 0% | 100% | 25% |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Landfill available |  |  |  |  |  |  |  |  |  |  |
| Mobilization meetings organized to sensitize the population on waste management |  | 6 1/year | 1 |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TRANSFORMATIONAL GOVERNANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GOAL/IMPACT: Transformational Governance that build on a capable, united, safe and Rwandan Values |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INDICATOR | BASELINE |  | DDS Target |  | TARGET |  | TARGET |  | TARGET |  | TARGET |  | TARGET |  | TARGET |  | MEANS OF VERIFICATION |  | ASSUMPTIONS |  |
|  | (2017/18) |  |  |  | 2018/19 |  | 2019/20 |  | 2020/21 |  | 2021/22 |  | 2022/23 |  | 2023/24 |  |  |  |  |  |
| JRLO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 1: Reinforce Rwandan culture and values as a foundation for peace and unity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 1.1: Enhanced Unity among Children |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.1.1 Itorero program strengthened in schools and Villages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of training organized to operationalize Itorero in all villages and School |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | District Report |  |  |  |
| OUTPUT 1.1.1 Kinyarwanda Language and Rwandan values preserved especially among the youth |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number NDUMUNYARWANDA dialogues s organized at all levels within the District | 60 |  | 3290 |  | 450 |  | 500 |  | 550 |  | 570 |  | 600 |  | 620 |  | District Report |  |  |  |
| Number of unit clubs established per sex of participants | 15 |  | 84 |  | 7 |  | 11 |  | 15 |  | 17 |  | 20 |  | 25 |  | District Report |  |  |  |
| Number of ABARINZI b' IGIHANGO trained per sex of trainees | 0 |  | 21 |  | 21 |  | 21 |  | 21 |  | 21 |  | 21 |  | 21 |  | District Report |  |  |  |
| PRIORITY AREA 3: Strengthen Justice, Law and Order |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 3.1: Enhanced Adherence to Human Rights |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.1.1 Deepened awareness and respected human rights by implementing the national human rights action plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number Of ABUNZI trained In order to inform their legal knowledge per sex | 498 |  | 498 |  | 498 |  | 498 |  | 498 |  | 498 |  | 498 |  | 498 |  | District Report |  |  |  |
| Number of ABUNZI trained per sex and used Abunzi Management Information System for data collection and sharing | 498 |  | 498 |  | 498 |  | 498 |  | 498 |  | 498 |  | 498 |  | 498 |  | District Report |  |  |  |
| Number of sectors with MAJ Outreach activities | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | District Report |  |  |  |
| Output: GBV preventive and management measures enhanced through the strengthening of Umugoroba w’ababyeyi, and the involvement of CSO/FBO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of reconciled couples and resolved domestic conflicts through FBOs initiatives | 135 |  | 674 |  | 142 |  | 148 |  | 138 |  | 112 |  | 74 |  | 60 |  | District Report |  |  |  |
| Sport and Culture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA : Reinforce Rwandan culture and values as a foundation for peace and unity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 1.1: Enshrined Kinyarwanda language and Rwandan values among Rwandans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.2.2 Fight against genocide ideology intensified |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Standard Memorial Site constructed | Study available and Site extension expropriated |  | 100% |  | 30% |  | 70% |  | 100% |  | operatinationalization |  |  |  |  |  | District Report |  |  |  |
| Number of Fight against Genocide ideology campaign organized | 2 |  | 12 2/year |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | District Report |  |  |  |
| number of Genocide memorial sites Rehabilitated | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | District Report |  |  |  |
| OUTCOME 1.3: Enhanced Citizen Participation, empowerment and inclusiveness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 1.3.1 Awareness campaign on the culture of problem solving conducted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of awareness campaign conducted on the culture of problem solving trough cell committees | 2 |  | 72 6/year |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | Reports |  |  |  |
| Number of awareness campaign conducted on the culture of problem solving trough inshuti z umuryango | 180 |  | 180 reports from sectors |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | Reports |  |  |  |
| Number of awareness campaign conducted on the culture of problem solving through Umugoroba w’Ababyeyi |  |  | 12 2/year |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | Reports |  |  |  |
| OUTCOME 1.4: Values, home grown solutions and innovations streamlined into all institutions for transformational governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of awareness and mobilization campaign conducted for the youth to participate in National Service/ Urugerero | 1 |  | 6 1/year |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | Reports |  |  |  |
| Number of impact assessment conducted for Itorero program conducted | 1 |  | 6 1/year |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | Reports |  |  |  |
| Number of ITORERO session organized within the District | 1 |  | 90 1Itorero/sector/year |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  | Reports |  |  |  |
| Governance and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 2: Ensure Safety and Security of citizens and property |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 2.1: Enhanced peace and security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 2.1.1 Community policing Strengthened and g security organs Strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IRONDO RY'UMWUGA initiated | 1 |  | 7 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | Reports |  |  |  |
| Number of Training organized in favour of Community Policing members per sex of trainees | 1 |  | 12 2/year |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | Reports |  |  |  |
| OUTPUT 2.1.2 Strengthen crime prevention |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Drug abuse fighting awareness campaigns organized | 2 |  | 12 2/year |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | Reports |  |  |  |
| Number of Awareness campaign organized in order to enhance crime prevention among population | 2 |  | 12 2/year |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | Reports |  |  |  |
| Number of Rehabilitation Centers Constructed | 1 |  | 3 |  |  |  | 1 |  |  |  | 1 |  | 1 |  |  |  | Reports |  |  |  |
| Output: Effectiveness and accountability in preventing and responding to GBV and human trafficking increased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of GBV victims who benefited from psychological, legal and economic services | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  |  |  |  |  |
| % of victims of human trafficking resettled | N/A |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | Reports |  |  |  |
| % of perpetrators convicted with GBV crime (human trafficking, child abuse, ) | N/A |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | Reports |  |  |  |
| % of reported GBV cases by gender | 531 |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | Reports |  |  |  |
| Number of institutions /organisations certified with gender equality seal | 3 |  | 24 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | Reports |  |  |  |
| PRIORITY AREA 3: Strengthen Justice, Law and Order |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 3.2: Control of Corruption, Transparency and Accountability Improved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 3.1.2 Mechanism to fight against corruption at all levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Anti-corruption clubs created and trained | 2 |  | 11 |  | 2 |  | 2 |  | 3 |  | 2 |  | 1 |  | 1 |  | Reports |  |  |  |
| Number of Organized awareness campaigns to fight against corruption | 1 |  | 12 2/year |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | Reports |  |  |  |
| PRIORITY AREA 4: Strengthen Capacity, Service delivery and Accountability of public institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 4.5: Effective and efficient management of government assets and public buildings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4.5.1 Constructed and maintained government assets that support the national economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Musanze District Office rehabilitated | NA |  | 100% |  | Study |  | Works 25% |  | Works 75% |  | Works 100% |  | finishing |  | Operationalization |  | reports |  |  |  |
| Number of sector administrative offices constructed | 3 |  | 9 |  | 1 |  | 1 |  | 2 |  | 1 |  | 2 |  | 2 |  | Reports |  |  |  |
| Number of sector administrative rehabilitated | 3 |  | 3 |  |  |  | 1 |  |  |  | 1 |  | 1 |  |  |  | Reports |  |  |  |
| Number of cells administrative offices constructed | 2 |  | 66 |  |  |  | 5 |  | 10 |  | 13 |  | 18 |  | 20 |  | Reports |  |  |  |
| Number of villages offices constructed | 6 |  | 165 |  | 5 |  | 30 |  | 30 |  | 30 |  | 35 |  | 35 |  | Reports |  |  |  |
| PRIORITY AREA 5: Increase citizens’ participation, engagement and partnerships in development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 5.1: Implementation and monitoring sectorial decentralization process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of Specific sessions organized in favour of Women and Youth involvement in Planning | 1ssession/Year for Youth and Women |  | 6 1/year |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | Reports |  |  |  |
| % of women, men and youth involved in district planning and prioritization | 70% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | Reports |  |  |  |
| % of women and men in leadership positions at different levels | 27% |  | 30% (at least) |  | 30% |  | 30% |  | 30% |  | 30% |  | 30% |  | 30% |  | Reports |  |  |  |
| Public Financial Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 4: Strengthen Capacity, Service delivery and Accountability of public institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 4.1: Enhanced accountability across public institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4.1.1 Transparency and accountability enforced |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of capacity development for JADF members organized | 1 |  | 6 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | Reports |  |  |  |
| Number of Public Accountability days organized | 1 |  | 102 |  | 17 |  | 17 |  | 17 |  | 17 |  | 17 |  | 17 |  | Reports |  |  |  |
| OUTPUT ensured qualified staff in public administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of new qualified staff recruited by sex | 12 |  | 294 |  | 26 |  | 136 |  | 35 |  | 39 |  | 31 |  | 27 |  | Staff recruited |  |  |  |
| OUTCOME 4.2: Improved service delivery across all sectors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4.2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of capacity development of individuals and institutions to attain the required level of professionalism in terms of service delivery standards organized | 9 |  | 848 |  | 161 |  | 136 |  | 128 |  | 139 |  | 143 |  | 141 |  | reports |  |  |  |
| OUTCOME 4.3: Enhanced sector capacity and coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4.3.1 online service delivery reinforce |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Percentage of Services delivered online |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | Reports |  |  |  |
| PRIORITY AREA 4: Strengthen Capacity, Service delivery and Accountability of public institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 4.6 Improved local government revenue mobilization and management for self-service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4.6.1 Improved and increased district revenue |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Amount of revenues collected at district level | 1,616,632,042 |  | 29,262,552,114 |  | 2,182,829,370 |  | 2,881,334,768 |  | 3,803,361,894 |  | 5,020,437,670 |  | 6,626,977,764 |  | 8,747,610,648 |  | Reports |  |  |  |
| OUTPUT 4.6.2 Increased the Implementation of Auditors recommendation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of continuous trainings organized for all staff to achieve clean audit per sex of trainees |  |  | 6 1/year |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | Reports |  |  |  |
| Sport and culture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRIORITY AREA 4: Strengthen Capacity, Service delivery and Accountability of public institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OUTCOME 4.4: Mainstreamed governance for production across sectors and enhance capacities of public institutions and performance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of campaign organized to promote sports as a healthy and active national capital | 12 |  | 144 |  | 24 |  | 24 |  | 24 |  | 24 |  | 24 |  | 24 |  | Reports |  |  |  |
| Number of training organized to support sport in the District per sex of trainees | N/A |  | 6 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | Reports |  |  |  |

## Cross-Cutting Areas

Seven cross cutting areas namely capacity development, gender and family, environment and climate change, disaster management, disability and social inclusion, HIV/AIDS and non-communicable disease, regional integration have been mainstreamed into Musanze District Development Strategy.

Capacity Development

Capacity development at the district level is at the core of the success in the implementation of this strategy, especially for service delivery. Capacity development mechanisms will be developed at all levels of the district governance to ensure achievement of targets and objectives. Capacity development will be focused on, mostly for improving cooperative performance through entrepreneurial trainings and workshops to ensure they create their income generating projects and add value to their products to excel in export promotion, district staff to deliver on efficient and effective budget execution by best targeting and supporting vulnerable people. JADF, individuals and institutions will also be targeted to attain the required level of professionalism in terms of service.

Gender and Family Promotion

The District will make sure that men and women, boys and girls are all involved in the district development programs and interventions. All district programs and interventions will be designed in line with district priorities fed by NST1 as a gender sensitive document at all district levels since specific sessions were organized in favour of women involvement in planning and promoting women headed households to benefit from VUP.

Environment and Climate Change

The District will ensure that environmental conservation becomes a priority; environmental impact assessment will be undertaken before big constructions projects are executed to reduce the risk of environmental deterioration.

Disaster Management

The district will ensure that water flows from volcanoes and landslides are well managed and the people living in high-risk zones will be relocated to curb environmental disasters.

Disability and Social inclusion

This strategy considers people with disabilities and people with serious social problems who will be mostly taken care of by putting up friendly public structures like markets, roads, schools and recreational centres. The District will continue to avail suitable special needs including education materials to ensure that people with disabilities are able to start school and move on attaining all levels of education.

HIV/AIDS and non-communicable diseases

Musanze district will need other efforts from all district stakeholders to combat the spread of HIV and AIDS through different interventions and to address factors contributing to NCDs. There will be community mobilization to prevent diseases through maintaining hygiene, promoting physical exercises for all age groups, regular health check-ups, scaling up screening services in communities and health facilities. Improved understanding of the risk factors and their determinants will provide opportunities for the prevention and control of the NCDS.

Regional integration

The RI offers the chance to become linked with neighbouring countries and international ports; to increase potential market. Musanze District will strengthen professional traders to invest in formal cross border trade   and will increase the volume of traditional agriculture export ofcrops and products.

# DDS Implementation

This chapter concentrates on how Musanze DDS will be implemented in the 6 years by describing key partners, stakeholders, their roles and responsibilities and explaining the mechanisms for co-ordination and information sharing in the District.

## Sequencing of Interventions (Implementation Plan)

Sequencing of projects is necessary to implement this DDS because, due to resource constraints, no projects can be implemented at once or looked at out of unforeseen challenges. Musanze DDS will be implemented considering projects that will promote rapid growth in the District and while accomplished, this will bring about other projects to start.

Development and tourism support, agro- processing, agriculture and livestock, construction, craft industry, value addition and processing of mining products will be the major focus because they are with high potentials for growth and employment. This will increase income for savings and will support youth and women to create new businesses through entrepreneurship and access to finance. More investments will focus on capacity development by working with the private sector to identify critical skills required in the labour market to inform training programs in TVET.

Urban development and establishment of infrastructure will support the development of the District by enabling good environment for business. Related interventions will focus on the transport sector by improving rural and urban transportation services, construction of modern markets and selling points along the road to facilitate trade within the district, development of industries for local construction materials to boost construction sector and the affordable housing programs, update district city master plan and ensure its implementation, upgrade informal settlements within the City of Musanze and provide related facilities like water, electricity, roads and fibre optics to these areas.

A waste management system will be developed in Musanze city by constructing faecal sludge treatment plants, sanitary landfill and semi centralized sewerage system.

Within DDS period, another set of priorities for Musanze District is fed by the Sustainable Development Goals related interventions aimed at eradicating poverty and improving the quality of life.  As a Referral Hospital, Ruhengeri Hospital will be constructed, and a district hospital will be constructed alongside with specialization in oscillatory and action taking in activities regarding prevention of non-communicable diseases and fighting HIV/AIDS. The remaining health centres and health posts will be constructed with adequate infrastructure and equipment. The district will facilitate sectors to provide standardized ECE schools in all villages and ECDs in all cells. To eradicate extreme poverty, the district will focus on extending the coverage of social programs to extreme poor and vulnerable groups. In the same period the district will focus on managing water flows from volcanoes to mitigate related disasters and improving water resource management and the governance is set as the last category of priority.

## DDS Implementation Strategy

### Roles and responsibilities of partners and stakeholders

This DDS, to undergo a translation into reliable results will depend on close collaboration of central and local level governing organs towards the implementation. This part describes partners and stakeholders’ roles and responsibilities.

### Roles of Central Government Ministries and Agencies

  - Provincial administration

The provincial administration has the overall coordination responsibility in the implementation of DDS. As a representative of central Government; its role is to coordinate all decentralized activities from sector to district.

It monitors and evaluates progress and annual district performance aligned to the set annual targets. It coordinates and monitors the works of all the district development partners to ensure that their operations are in line with government policies and district set priorities. It also monitors the implementation of government policies and programmes at the district level.

MINALOC

The role of the Ministry of Local government (MINALOC) is to ensure that all sectorial and fiscal functions are fully disseminated to the district. MINALOC oversees policy formulation as well earmarked funds that will ease the implementation of this development strategy. MINALOC also supports the coordination of activities for different stakeholders of the District.

MINECOFIN

MINECOFIN is responsible for resource mobilization and allocation for public investments, planning and coordinating economic activities across sector ministries and more recently ensuring population issues are integrated into sector priority setting. MINECOFIN will assist to link the district strategic outcomes with the NST1. MINECOFIN will also be critical in funding for projects initiated by the District. This same ministry will coordinate the sector transfers to finance specific sector activities to be implemented at the district level. MINECOFIN will monitor the implementation of the development strategy and ensure that the priorities within the DDS are in line with sector priorities to ensure harmonized development and reduce duplication of efforts.

Ministry of Infrastructure (MININFRA)

Infrastructure development is the second priority of Musanze district, which is an important driver towards sustainable economic development and poverty reduction. The Ministry of Infrastructure (MININFRA) provided the strategic guidance through its own SSP for formulating roads, energy, water and sanitation and urbanization in this DDS. The ministry will take overall responsibility for integrating infrastructure activities under this DDS in their priority areas. As the Ministry of infrastructure has several sectors, each sector will have to implement some of the projects within this DDS.

Ministry of Natural Resources (MINERENA)

MINERENA, as part of the central government entity, it will be responsible for environment policy formulation and implementation, coordination and monitoring.

For sustainable exploitation of existing mines, MINIRENA will work closely with the district in the protection of mines through tree planting, digging ditches and putting all miners into mining cooperatives, hence ensuring an organized and sustainable exploitation of minerals and quarries.

Ministry of Agriculture (MINAGRI)

The Ministry of Agriculture and Animal Resources main mandate is to increase animal production, modernize farming, ensure food security and promote surplus for the market. Given the importance of agriculture in the lives of the Rwandan population, and the scope for improving agricultural production by using modern techniques and agricultural inputs including irrigation, fertilizer and quality seeds, MINAGRI plays an essential role in improving the success of the agricultural sector across districts.

MINAGRI is a key partner for LODA in both promoting agricultural potentialities, such as key crops for local consumption and exports, as well as the development of agri-businesses and production and use of agricultural and animal by-products, such as leather.

Ministry of Education (MINEDUC)

MINEDUC is the lead Ministry for the education sector with responsibility for policy formulation, educational planning, coordination, monitoring and evaluation and regulation through setting norms and standards for the education sector. MINEDUC works closely with several government agencies including The Rwanda Education Board (REB)  which  has oversight for coordinating and implementing education activities at pre-primary, primary and secondary level and. The Workforce Development Authority (WDA) with the main functions now including developing TVET standards; monitoring implementation; policy dissemination and playing an advisory role to all TVET implementers.

Ministry of ICT and Innovation (MINICT)

The role of MINICT is to work closely with the district through encouraging an IT adoption at an early stage among the students to raise computer literacy levels within the district. Trainings aimed to equipping people with IT skills is very important in raising computer literacy.

Rwanda Environment Management Authority (REMA)

REMA will play an important role since it is the national authority responsible for overseeing the implementation of environmental policy and law. Strategies to use include education and sensitization on environmental conservation through formal and informal education as well as practical demonstration, law enforcement and monitoring, as well as capacity building support to other institutions.   Some of the projects proposed by Musanze will require environmental certification from REMA.

Ministry of Public Service and Labour (MIFOTRA)

The Ministry of Labour is responsible for reinforcing national labour standards, promoting job creation and developing a framework that enables high performance of private and public-sector organizations.  The strategic objectives of MIFOTRA are improving institutional capacity, efficiency and effectiveness, promoting gender equality, promoting capacity building and skills development in the public and private sectors, eliminating corruption, promoting employment creation and ensuring compliance with labour standards.

Rwanda Development Board (RDB)

The Rwanda Development Board is responsible for supporting private investment and business development in Rwanda.  RDB’s role relates to developing the private sector, including through addressing the needs of companies and investors. RDB should identify investors and link them to potentialities at the district level, as well as supporting the development of private businesses.

Ministry Trade and Industry (MINICOM)

The Ministry of Trade and Industry will help in improving the production capacity and investment in small and medium enterprises, and creating a positive business environment for large businesses, including mining operators and agribusiness firms.

Water and Sanitation Corporation and (WASAC) and Rwanda Energy Group (REG)

Water and Sanitation Corporation and Rwanda Energy Group are responsible for ensuring access to clean water and adequate sanitation, and promoting sustainable energy use, as well as facilitating the building of energy, water and sanitation infrastructures. Infrastructure is a key priority of Musanze district and the development of sustainable energy sources, expansion of electrification, and facilitation of access to water and sanitation are essential to economic growth.

### Roles of the District

Musanze District has the overall responsibility in the implementation of the development strategy. The district has, within its mandate to coordinate, monitor and evaluated development actions of the district. The district will ensure that the implementation of DDS is in line with NST1 orientations and other GoR policies by harmonizing the DDS interventions of both governmental and non-governmental actors at local level and in creating synergies between DDS and different sectoral programmes in line with NST1. This will help administrative Sectors to deliver quality services in line with DDS, promote cooperation, harmonization and synergy with other Districts in the implementation of their respective DDS, especially for big projects.

In collaboration with partners, the district will draw up an annual implementation plan for the DDS and monitor progress against it, drawing on information collected from different relevant sectors and stakeholders. The district will oversee the operational programmes implemented by stakeholders and will ensure that the district has the capacities required to deliver the DDS objectives

### - Roles of the District Technicians

District technicians will be the key mentor of implementation of policies set by either central or local government. They are responsible of demonstration, sensitization and monitoring of set activities. They should be involved in different activities on behalf of the district executive committee.

### - Roles of Private Sector

The private sector has critical roles to play in the implementation of the DDS, creating an enabling environment to them will be very instrumental. Private sector agencies will be mobilized and sensitized, through the Private Sector Federation (PSF) and its District offices, to integrate the DDS priorities into their activities and strategies for development. The private sector will help to train entrepreneurs, hence ensuring increased employment creation within the district.

### - Roles of Civil Society

Civil society organizations intervening in the district will be encouraged to continue to actively participate in JADFs, helping to ensure a coordinated approach to DDS implementation. The District will need to work together with civil society to strengthen Sector level JADFs, so that JADFs are enabled to undertake detailed co-ordination

### Mechanisms for coordination and information sharing

The successful implementation and realization of the objectives of this DDS is secured on effective coordination and communication systems within the Musanze District and stakeholders. The Executive Committee led by the Mayor of Musanze District will play a crucial role in providing leadership, planning, execution, and monitoring and evaluation of the DDS. Every year, each non-governmental actor operating in the district will present a detailed plan of its respective domains of interventions in the District, disaggregated for each sector. The JADFs will ensure that these programmes are aligned with district development priorities.

The Musanze District will be required to strengthen existing database system for capturing data and processing. The portal should be integrated with the Management Information System to ensure timely data capture and dissemination not only to district actors but also the stakeholders.  Different stakeholder reporting templates and defined reporting timelines shall be formulated to ensure that an elaborated and standard reporting and monitoring system is in place.

The sharing of information will enhance participatory planning and implementation as envisaged in the decentralization policy, increase transparency and accountability, and create a sense of ownership and pride among the district stakeholders as well as the residents while the information will be posted on Musanze district website, executive meetings, city councillors’ meetings (Njyanama), community work (Umuganda) meetings and other channels as determined by the Executive Committee on need basis.

### Risk mitigation strategies

This DDS has been developed with the knowledge that its implementation will be countermanded by many internal and external factors that may delay its implementation.

Therefore, risk identification, measuring, control and managing or mitigation has been integrated. The source of risk could emerge from internal operations (e.g. from staff, poor internal controls, systems) or external shocks (economic and environment businesses).                                       This DDS has been developed with the assumption that the internal and external risks are minimal, and they will be mitigated through hiring new staff or developing capacity for existing staff regularly while strengthening the MIS.

For the successful implementation of this DDS, everyone involved in implementation of this DDS will need to have an opportunity to learn and get skills that can help them in the effective implementation of it. Capacity development at all levels in the district will be necessary to show new ways of doing things. Private sector involvement in the implementation of this DDS will be very helpful. The District will need to provide a better environment to the private people to resolve resources constraints. Efficient data collection to facilitate realistic targeting, setting realistic financial objectives will be also necessary.

# Monitoring and evaluation

The successful implementation of the DDS will be supported by an effective monitoring and evaluation system. The existing Monitoring and Evaluation Information System in Musanze District is only operational for LODA projects. To facilitate regular monitoring and evaluation, the district will need to establish a comprehensive management of Information System including a well-structured and computerized database with quantitative and qualitative indicators, which will support annual monitoring of the evolution of achievements and changes.

To be able to effectively monitor progress against targets of the DDS, the District will establish annual operational plans, containing agreed upon objectives, activities, targets and indicators to be achieved within a fiscal year; and consistently leading to the achievement of the DDS objectives. It will be important for the district to monitor and evaluate at the district level, sector and cell levels to see whether the implementation is being done accordingly. The Cell Development Committees, Sector Development Committees, District committees and other development partners will ensure monitoring and evaluation.

Central government, through its respective ministries especially MINECOFIN and MINALOC, government agencies and institutions will ensure the implementation of NST1 in the whole country. Moreover, they will ensure the availability of required resources and elaboration and application of relevant policies. The province will ensure the execution of planned activities of districts and advocate for some through performance districts’ contracts.  It will analyse all reports from district executive committee and advise the later for the success of this DDS.

NGOs and other partners will contribute immensely in financing the implementation of the DDS. Therefore, they will jointly participate to monitor the projects in which they are directly involved to ensure timeliness and accountability. Public institutions will jointly implement and monitor the cross-cutting issues in the DDS.

# Cost and Financing of the DDS

To achieve the district priorities, there is need for funds to enable the development Strategy implementation. Without financial resources, the implementation of the current development strategy cannot be possible. It is in this context that the estimates for the implementation of this development Strategy are set.

The overall projected cost to satisfy Musanze District priorities within the DDS period of 6 years is 265,462,768,000 Rwandan Francs, mobilization of these funds is critical, and bulk of this money will come from private sector through the PPP mechanism

To achieve the objectives of this DDS as well as the national objective of accelerating economic growth and poverty reduction, financing of the DDS is critical. Funds mobilization is key to the implementation of the District priorities. The following are some of the sources of funds for the DDS.

- Government Block Grants

- Earmarked Transfers)

- Own Taxes and Revenues

- Donor funding

- Private sources

| 3 |  | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Yr6 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N | Priority Areas | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | 2022/2023 | 2023/2024 | Total |
| Total (RWF) |  | 24.115.768.000 | 70.099.148.000 | 42.353.628.000 | 33.485.548.000 | 14.865.968.000 | 16.327.708.000 | 201.247.768.000 |
| 1 | Pillar1: Economic Transformation | 20.813.528.000 | 57.918.328.000 | 21.904.928.000 | 30.171.228.000 | 11.457.628.000 | 13.313.428.000 | 155.579.068.000 |
| 2 | Pillar 2: Social Transformation | 2.837.240.000 | 9.915.820.000 | 19.606.700.000 | 2.524.320.000 | 2.618.340.000 | 2.224.280.000 | 39.726.700.000 |
| 3 | Pillar 3: Transformational Governance | 465.000.000 | 2.265.000.000 | 842.000.000 | 790.000.000 | 790.000.000 | 790.000.000 | 5.942.000.000 |

Table 8: Costing of DDS